## 13-09-19
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 17
[7 empty] | Current Date: |  | 2019-09-13
[7 empty] | 2019-09-13 |  | 2019-09-13
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Abimbola Akindiilete
1 | SOP |  |  | M | FEEDING AND WELFARE OF EXPATRIATES | AO | Done. Expatriates are back to their destinations for now | 9th Sept 2019 | 12th Sept 2019 | Closed
2 | SOP |  |  | H | DATA RECAPTURING FOR OLD STAFF | AO | Data recapturing form has been printed and given to old staff to fill and submit for Pal pension recapturing of data | 9th Sept 2019 |  | Closed
3 | SOP |  |  | H | SATISH'S SALARY AND TELEX COPY | AO | Notice and reminders has been sent to GMA for processing | 9th Sept 2019 |  | Open
4 | SOP |  |  | M | MR. MIKE'S ACCOUNT | AO | BVN has been done and the pin has been sent to the accoiunt officer. Currently working on him getting an ATM. | 13th Sept 2019 |  | Open
5 | SOP |  |  | H | KHAIRAT'S MEDICALS | AO | Done | 9th Sept 2019 |  | Closed
6 | SOP |  |  | H | EXPATRIATE QUARTERS DEMANDS AND ISSUES | AO | Items have been purchased as requested, quotations have been recived from vendor for bathroom renovation and other needed work. | 9th Sept 2019 | 10th Sept 2019 | Open
7 | SOP |  |  | M | ELECTRICAL ISSUES AT SECURITY HOUSE | AO | Done | 11th Sept 2019 |  | Closed
8 | SOP |  |  | M | CHANDLING FOR LEKKI BASE | AO | Done | 9th Sept 2019 |  | Closed
9 | SOP |  |  | M | RESCHEDULING AND ARANGEMENT OF EXPATRIATES' FLIGHTS TO THEIR DESTINATION | AO | Done | 9th Sept 2019 | 12th Sept 2019 | Closed
10 | SOP |  |  | M | MAKING AND SORTING PAYMENTS AND REQUISITIONS | AO | Done for the week | 9th Sept 2019 | 13th Sept 2019 | Closed
11 | SOP |  |  | M | BOOKING OF TICKET FOR PERSONNELS | AO | Done | 11th Sept 2019 |  | Closed
12 | SOP |  |  | M | RUNNING ERANDS ON DMD'S INSTRUCTIONS | AO | Done | 9th Sept 2019 | 13th Sept 2019 | Closed
13 | SOP |  |  | H | MAKING SURE EXPATRIATES ARE CONVEY TO AIRPORT ON TIME FOR THEIR FLIGHTS | AO | Done | 10th Sept 2019 | 13th Sept 2019 | Closed
14 | SOP |  |  | M | PISCES INV 1089 | AO | Done. | 12th Sept 2019 |  | Closed
15 | SOP |  |  | H | DIRECTING JUNIOR STAFF ON KEEPING THE OFFICE CLEAN AND MAKING SURE COMPANY RULES ARE UPHELD | AO | Done | 9th Sept 2019 | 13th Sept 2019 | Open
16 | SOP |  |  | H | SORTING LEKKI BASE NEEDS FOR THE WEEKEND | AO | Done | 13th Sept 2019 |  | Closed
17 | PA |  |  | M | SURVEY DEPARTMENT REQUISITION AND NEEDS FOR IMA AMNI | AO | Done | 11th Sept 2019 | 12th Sept 2019 | Closed
[9 empty] | Open: | 4
[9 empty] | Closed: | 13
| Actionees (Key): | [7 empty] | Info:
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding
|  |  |  | L | Low Finding
|  |  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 10 Closed Info

## 11-10-19
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 21
Current Date:
2019-10-11
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Abimbola Akindiilete
1 | SOP |  |  | H | Zenith account opening for staff | AO | In progress | 7th Oct |  | Open
2 | SOP |  |  | H | HR software training and test running | AO | Training concluded, Test running on going | 7th Oct |  | Open
3 | SOP |  |  | M | Visa's expiry dates for expats | AO | All expat's visas' collated and expiration kept in check | 7th Oct |  | Closed
4 | SOP |  |  | H | NSITF | AO | Payment made, working on certificate | 7th Oct |  | Open
5 | PA |  |  | M | Hotel accomodation for personnel | AO/FO | Done | 7th Oct |  | Closed
6 | SOP |  |  | M | NYSC posting | AO | Done | 7th Oct | 9th Oct | Closed
7 | SOP |  |  | M | Lekki base needs for the week | AO/FO | Done | 7th Oct |  | Closed
8 | SOP |  |  | H | Access control | AO | Done, Biometrics for clocking in and out in progress | 8th Oct |  | Closed
9 | PA |  |  | H | James flight and logistics to PHC | AO | Done | 8th Oct |  | Closed
10 | SOP |  |  | H | Solar house Engineer | AO | Popoola said he got another offer, Collins has no hands on knowledge, will be sending out advert for renewable engineer | 8th Oct |  | Open
11 | PA |  |  | H | Azuka's medicals and certification | AO | Certification and medicals done. TB test to be received tomorrow morning | 9th Oct |  | Closed
12 | SOP |  |  | M | Electricity bill | AO/FO | Bill sent to FO and Part payment made | 9th Oct |  | Closed
13 | SOP |  |  | H | Solar house equipment transfer | AO | In progress | 9th Oct |  | Open
14 | SOP |  |  | H | Twp for Satish | AO | In progress | 9th Oct |  | Open
15 | SOP |  |  | M | Refund for printer | AO | Done | 10th Oct |  | Closed
16 | SOP |  |  | H | New recruitement | AO | In progress | 10th Oct |  | Open
17 | SOP |  |  | H | DMD's office | AO/FO | In progress | 11th Oct |  | Open
18 | SOP |  |  | M | Tundra and Escalade issues | AO/FO | In progress | 11th Oct |  | Open
| SOP |  |  | M | Expat Quarter's issues | AO/FO | In progress | 11th Oct |  | Open
| SOP |  |  | M | Office waste disposal | AO | Done | 11th Oct |  | Closed
| SOP |  |  | M | Flight booking and arrangement for 3 personnel | AO | Done | 11th Oct |  | Closed
[9 empty] | Open: | 10
[9 empty] | Closed: | 11
| Actionees (Key): | [7 empty] | Info:
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding
|  |  |  | L | Low Finding
|  |  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 10 Closed Info

## 18-10-19
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 18
Current Date:
2019-10-18
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Abimbola Akindiilete
1 | SOP |  |  | M | flight for GMO | AO | Done | 14th Oct |  | Closed
2 | PA |  |  | H | Issues with Azuka's training certification | AO | Done | 14th Oct |  | Closed
3 | SOP |  |  | H | Safety Boot for Azuka | AO | Done | 14th Oct |  | Closed
4 | SOP |  |  | H | Solar engineer recruitment | AO | In progress | 14th Oct |  | Open
5 | SOP |  |  | H | Procurement officer recruitment | AO | In progress | 14th Oct |  | Open
6 | SOP |  |  | M | HSE officer interview | AO | Done | 14th Oct | 16th Oct | Closed
7 | PA |  |  | M | James demobilisation and travelling processes | AO/FO | Done | 14th Oct | 18th Oct | Closed
8 | PA |  |  | H | Twp for Satish | AO | Done | 14th Oct |  | Closed
9 | PA |  |  | H | Expatriates's retrun tickets reminder and opening | AO | Done | 15th Oct |  | Closed
10 | SOP |  |  | M | DMD's office | AO | In progress. Requisition sent | 15th Oct |  | Closed
11 | PA |  |  | H | TWP for MATARA | AO | Done | 15th Oct |  | Closed
12 | SOP |  |  | M | Zenith account opening for new staff | AO | Done. Awaiting acount numbers of PHC staff | 16th Oct |  | Closed
13 | SOP |  |  | H | Solar house equipement transfer | AO | Done | 16th Oct | 19th Oct | Closed
14 | PA |  |  | H | Prashant's demobilisation and travelling arrangement | AO | Done | 17th Oct |  | Closed
15 | SOP |  |  | M | Accountant's new office space | AO | Done | 17th Oct | 18th Oct | Closed
16 | PA |  |  | H | Matara's business visa and traveeling arrangement | AO | Done | 17th Oct |  | Closed
17 | PA |  |  | H | Matara's medicals and logistics to the vessel | AO | Done | 18th |  | Closed
18 | SOP |  |  | M | Brone policy handbook | AO | In progress | 18th Oct |  | Open
[9 empty] | Open: | 3
[9 empty] | Closed: | 15
| Actionees (Key): | [7 empty] | Info:
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding
|  |  |  | L | Low Finding
|  |  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 10 Closed Info