## Operations Tracker
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 1
[7 empty] | Current Date: |  | 13.01.2015
[7 empty] | Last updated on: 13/01/2015 |  | 2015-01-13
Item No |  | Ref | Section or Page | Priority | What | Action Party | Update | By When | Days to Close | Status
1 |  | Oriental Hotel |  | H | Follow up on refunds from the rooms booked and the Hall for the Divas White Ball | SA to the DMD | Refund of 36,150.00 was collected for the rooms but the refund for the Hall is still outstanding. | 2015-04-05 | 2015-05-11 | Open
is still outstanding and awaiting a manager for signature.
2 |  | DDC 2015 |  | H | Cheque collection for a ticket to the ball. | SA to the DMD | A cheque of 12,500 was collected and deposited in the Pink Hearts initative account. | 2015-05-07 |  | Closed
3 |  | Guardian News |  | H | Follow up on the publication of the Daisies day Talk show | SA to the DMD | To be Published on Tuesday the 12th of May | 2015-05-05 | 2015-05-12 | Open
4 |  | Thisday News |  | H | Publication of the Daisies day and Divas white ball | SA to the DMD | Daiseis day was published on the 7th of May and the Ball will be published over the weekend | 2015-06-05 | 2015-05-12 | Open
5 |  | Souvenir |  | M | Souvenirs from DDC 2015 | SA to the DMD | Souvenirs were sent to Diva Jumoke as requested by Diva Yomi | 2015-05-05 | 2015-07-05 | Closed
6 |  | Appreciation Letters |  | H | Drafting of the letters for the sponsors and partipants of DDC 2015 | SA to the DMD | the letters are ready and will be sent out on Monday. | 2015-05-06 | 2015-05-11 | Open
7 |  | Budget for DDC |  | H | Update of the Budget | SA to the DMD | the update is still ongoing | 2015-05-06 | 2015-05-11
[9 empty] | Open: | 3
[9 empty] | Closed: | 2
| Actionees (Key): | [7 empty] | Info: | 0
`H
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding
|  |  |  | L | Low Finding
|  |  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open Closed Info

## Action Tracker
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 1
[7 empty] | Current Date: |  | 15.05.2015
[7 empty] | Last updated on: 15/01=5/2015 |  | 2015-05-15
Item No |  | Ref | Section or Page | Priority | What | Action Party |  | By When | Days to Close | Status
1 |  | Oriental Hotel |  | H | Follow up on refunds from the rooms booked and the Hall for the Divas White Ball | SA to the DMD | Received 25,500:00 for hall | 2015-05-12 |  | Closed
2 |  | The News |  | H | Follow up on publication |  | Publication will be out on Monday | 2015-05-18 |  | Open
3 |  | New Membership |  | H | Invite to group BBM | SA to the DMD | 1 invite sent and accepted | 2015-05-14 |  | Closed
4 |  | Guardian News |  | H | Follow up on the publication of the Daisies day Talk show | SA to the DMD | To be Published on Tuesday the 12th of May | 2015-05-15 | 2015-05-19 | Open
5 |  | Thisday News |  | H | Publication of the Daisies day and Divas white ball | SA to the DMD | The White Ball will be published on Sunday | 15/5/2015 | 2015-05-17 | Open
6 |  | WIGPA Flier |  | M | Reprint and waybil to Abuja | SA to the DMD | Mr.Ayo is not reachable I will keep at it | 2015-05-13 | 18/5/2015 | Open
7 |  | Budget for DDC |  | H | Update of the Budget | SA to the DMD | Sent to the DMD and awaiting her review | 2015-05-11 | 2015-05-15 | Open
8 |  | Platinum Number |  | H | To get a new number for the group | SA to the DMD | Unable to get MTN working on Etisalat | 2015-05-13 | 2015-05-19 | Open
9 |  | Report from ANIM IX |  | H | To send report | SA to the DMD | Report sent to the DMD | 2015-05-11 | 2015-05-13 | Closed
[9 empty] | Open: | 3
[9 empty] | Closed: | 2
| Actionees (Key): | [7 empty] | Info: | 0
`H
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding
|  |  |  | L | Low Finding
|  |  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open Closed Info ...

## Tracker week3
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 1
[7 empty] | Current Date: |  | 22.05.2015
[7 empty] | Last updated on: 15/01=5/2015 |  | 2015-05-15
Item No |  | Ref | Section or Page | Priority | What | Action Party |  | By When | Days to Close | Status
1 |  | Collection of DDC photos and video documentary |  | H | Follow up on the delivery from the photography and video team | SA to the DMD | awaiting Haykay to deliver | 2015-05-22 | 2015-05-27 | Open
2 |  | The News |  | H | Follow up on publication |  | Publication was not published | 2015-05-18 | 2015-05-27 | Open
3 |  | New Membership |  | H | No new invite for the week | SA to the DMD | To ensure a positive change next week | 2015-05-22 | 2015-05-29 | Open
4 |  | Guardian News |  | H | Follow up on the publication of the Daisies day Talk show | SA to the DMD | DDC 2015 was Published on Tuesday the 12th of May | 2015-05-19 | 2015-05-19 | Closed
5 |  | Thisday News |  | H | Publication of the Daisies day and Divas white ball | SA to the DMD | Awaiting Mr. Mubi's confirmation | 24/5/2015 | 2015-05-25 | Open
6 |  | WIGPA Flier |  | M | Reprint and waybil to Abuja | SA to the DMD | Mr.Ayo did not deliver but we sent the first set | 2015-05-18 | 20/5/2015 | Closed
7 |  | Budget for DDC |  | H | Update of the Budget | SA to the DMD | DMD formatted and sent back to me | 2015-05-22 | 2015-05-28 | Open
8 |  | Platinum Number |  | H | To get a new number for the group | SA to the DMD | To compare GLO and Etisalat before making a choice | 2015-05-22 | 2015-05-28 | Open
9 |  | Membership list |  | H | To send report | SA to the DMD | Report sent to the DMD and working on the update | 2015-05-11 | 2015-05-22 | Open
10 |  | Souvenir |  | M | To deliver to Mrs Oduntan and Princess | SA to the DMD | delivered to Mrs Oduntan Princess not reachable | 2015-05-22 | 2015-05-28 | Open
[9 empty] | Open: | 3
[9 empty] | Closed: | 2
| Actionees (Key): | [7 empty] | Info: | 0
`H
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding
|  |  |  | L | Low Finding
|  |  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open Closed Info

## TRACKER WK4
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 1
[7 empty] | Current Date: |  | 12.06.2015
2015-06-12
Item No |  | Ref | Section or Page | Priority | What | Action Party |  | By When | Days to Close | Status
1 |  | DMD's Office |  | H | Outstanding repairs,installation of the Blinds and repainting of the private room | SA to the DMD | Repair of the window is ongoing,painting to be done soon and quote for Blind has been sent for approval | 5/0/2015 | 2015-06-03 | Closed
2 |  | Nape Exhibition Stand |  | H | To get a new Vendor and quote | SA to the DMD | To get a new quote and follow up with the Vendor | 2015-06-12 | 2015-06-15 | Open
3 |  | Membership Update |  | H | 1 new member joined the club and 3 old ones are now active in the house | SA to the DMD | The new members are active on the BBM Chat rooms | 2015-06-08 | 2015-06-08 | Open
4 |  | Platinum Number |  | H | To Activate a new number for the club | SA to the DMD | Activated and awaiting the current suscriprtion on the old number to expire. | 2015-06-02 | 2015-06-08 | Closed
5 |  | Starter Packs for Divas |  | H | Distribution of 20 starter packs for Lagos Divas | SA to the DMD | Distribution is still ongoing for 5 more Divas | 2015-12-06 | 2015-06-12 | Open
6 |  | WIGPA Publication and Stationary |  | M | Collection from Mr.Ayo | SA to the DMD | Production is yet to be completed but we are following up with Mr Ayo to speed it up | 2015-05-12 | 2015-06-15 | Open
7 |  | Staionary for G.O.D |  | H | Mr. Tope to is yet to send in the designs | SA to the DMD | awaiting his mail and further instructions from the DMD | 2015-06-04 |  | Open
8 |  | Collection Of Roll Up Banner and other DDC Materials |  | H | To pick up from Diva Funmi | SA to the DMD | colleceted for safe keeping | 2015-06-11 | 2015-11-06 | Closed
[9 empty] | Open: | 3
[9 empty] | Closed: | 2
| Actionees (Key): | [7 empty] | Info: | 0
`H
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding
|  |  |  | L | Low Finding
|  |  |  | Info | Information
Note on C5: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on L5: Statuses are: Open Closed Info

## WEEK5
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 1
[7 empty] | Current Date: |  | 12.06.2015
2015-06-12
Item No |  | Ref | Section or Page | Priority | What | Action Party |  | By When | Days to Close | Status
1 |  | DMD's Office Repairs |  | H | Outstanding repairs,installation of the Blinds and repainting of the private room | SA to the DMD | Repair of the window is ongoing,painting to be done soon and quote for Blind has been sent for approval | 5/0/2015 | 2015-06-03 | Closed
2 |  | Nape Exhibition Stand |  | H | To get a new Vendor and quote | SA to the DMD | To get a new quote and follow up with the Vendor | 2015-06-12 | 2015-06-15 | Open
3 |  | Membership Update |  | H | 1 new member joined the club and 3 old ones are now active in the house | SA to the DMD | The new members are active on the BBM Chat rooms | 2015-06-08 | 2015-06-08 | Open
4 |  | Platinum Number |  | H | To Activate a new number for the club | SA to the DMD | Activated and awaiting the current suscriprtion on the old number to expire. | 2015-06-02 | 2015-06-08 | Closed
5 |  | Starter Packs for Divas |  | H | Distribution of 20 starter packs for Lagos Divas | SA to the DMD | Distribution is still ongoing for 5 more Divas | 2015-12-06 | 2015-06-12 | Open
6 |  | WIGPA Publication and Stationary |  | M | Collection from Mr.Ayo | SA to the DMD | Production is yet to be completed but we are following up with Mr Ayo to speed it up | 2015-05-12 | 2015-06-15 | Open
7 |  | Staionary for G.O.D |  | H | Mr. Tope to is yet to send in the designs | SA to the DMD | awaiting his mail and further instructions from the DMD | 2015-06-04 |  | Open
8 |  | Collection Of Roll Up Banner and other DDC Materials |  | H | To pick up from Diva Funmi | SA to the DMD | colleceted for safe keeping | 2015-06-11 | 2015-11-06 | Closed
[9 empty] | Open: | 3
[9 empty] | Closed: | 2
| Actionees (Key): | [7 empty] | Info: | 0
`H
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding
|  |  |  | L | Low Finding
Note on C6: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on L6: Statuses are: Open Closed Info

## WEEK6
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 1
[7 empty] | Current Date: |  | 19.06.2015
2015-06-19
Item No |  | Ref | Section or Page | Priority | What | Action Party |  | By When | Days to Close | Status
1 |  | DMD's Office Repairs |  | H | Repainting of the Private room, window repairs and office clean up | SA to the DMD | the painting has been completed, the window is fixed and the office has been thoroughly cleaned | 18/06/2015 | 2015-06-03 | Closed
2 |  | Nape Exhibition Stand |  | H | To get a new Vendor and quote | SA to the DMD | To get a new quote and follow up with the Vendor | 2015-06-12 | 618/06/2015 | Open
3 |  | Membership Update |  | H | 1 new member joined the club and 2 old ones are now active in their respective houses | SA to the DMD | The new members are active on the BBM Chat rooms | 2015-06-08 | 2015-06-08 | Open
4 |  | Platinum Number |  | H | To Activate a new number for the club | SA to the DMD | Activated and currently being used without hitches | 2015-06-02 | 2015-06-08 | Closed
5 |  | Starter Packs for Divas |  | H | Distribution of 20 starter packs for Lagos Divas | SA to the DMD | Distribution is still ongoing | 2015-12-06 | 2015-06-12 | Open
6 |  | WIGPA Publication and Stationary |  | M | the produced came in but not completed and below expectation | SA to the DMD | Mr. Tope to reproduce the brochures and Mr Sola is producing the Notebooks and pens | 19/06/2015 | 2015-06-15 | Open
7 |  | Staionary for G.O.D |  | H | Mr. Tope to is yet to send in the designs | SA to the DMD | awaiting his mail and further instructions from the DMD | 218/06/2015 |  | Open
[9 empty] | Open: | 3
[9 empty] | Closed: | 2
| Actionees (Key): | [7 empty] | Info: | 0
`H
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding
|  |  |  | L | Low Finding
Note on C6: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on L6: Statuses are: Open Closed Info

## WEEK7
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 1
[7 empty] | Current Date: |  | 19.06.2015
2015-06-19
Item No |  | Ref | Section or Page | Priority | What | Action Party |  | By When | Days to Close | Status
1 |  | Nape Exhibition Stand |  | H | To get a new Vendor and quote | SA to the DMD | To get a new quote and follow up with the Vendor | 2015-06-12 | 2015-03-07 | Open
2 |  | Membership Update |  | H | 4 old members are now active in their respective houses | SA to the DMD | To bring every member in before the next season | 2015-06-08 | 30/6/2015 | Open
3 |  |  |  | H |  | SA to the DMD |  | 2015-06-02 | 2015-06-08 | Closed
4 |  | Starter Packs for Divas |  | H | Distribution of starter packs for all Divas | SA to the DMD | collation of the names and addresses. To be sent out this week | 24/6/2015 | 2015-07-05 | Open
5 |  | WIGPA Publication and Stationary |  | H | MR Tope reproduced the entire work | SA to the DMD | The Stationary was sent in time for the conference | 19/06/2015 | 2015-06-23 | Closed
|  | Relocation to the 3rd Floor |  | H | This is still in progress. | SA to the DMD | Tocensure the internet is up and running.Minimise traffic to the floor and ensure the artistans do as they are told without hitches | 21/06/2015 | 2015-07-07 | Open
[9 empty] | Open: | 3
[9 empty] | Closed: | 2
| Actionees (Key): | [7 empty] | Info: | 0
`H
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding
|  |  |  | L | Low Finding
Note on C6: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on L6: Statuses are: Open Closed Info

## Sheet1
[7 empty] | Current Date: |  | 17.08.2015
2015-07-09
Item No |  | Ref | Section or Page | Priority | What | Action Party |  | By When | Days to Close | Status
1 |  | Identity Cards for CL&O and Solar House |  | H | To get designs and quote | SA to the DMD | To send to the DMD for Approval | 2015-08-12 | 2015-08-20 | Open
2 |  | Membership Update |  | H | 8 new members are now active in their respective members joined | SA to the DMD | To bring every member in as soon as possible | 2015-08-14 | 2015-08-18 | Open
3 |  | New Chatroom House |  | H | A new house was created on BBM and members reshuffled to the new house | SA to the DMD | Reshuffling to be completed this week | 2015-08-14 | 2015-08-18 | Open
[9 empty] | Open: | 3
[9 empty] | Closed: | 2
| Actionees (Key): | [7 empty] | Info: | 0
`H
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding
|  |  |  | L | Low Finding
Note on C3: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on L3: Statuses are: Open Closed Info

## Key Features Hints
Issues | Disciplines
1 HQ | HSE/Quality
2 PA | Project admin
3 DS | Diving System
4 DP | Dynamic Positioning
5 MS | Marine Systems
6 CL | Craneage & Lifting
7
8
9 CS | Cost & schedule
Features of "Action tracker"
Cell J1 contains a "running total" of the number of actions - retrieved from the last "Ref no" entered in column B - so each time a new action is added, give it the next Ref no.
Cell A4 contains a comment which is input manually to reflect the issue headings that the actions relate to - the comment should reflect the issues (and their abbreviations) entered on this sheet
Column A uses "data validation" to present a dropdown list of the "issues" from "Sheet2"
Column C uses conditional formatting to color the cell grren if "L" is entered, amber if "M" is entered and red if "H" is entered - the cell does not change color if nothing is entered so priority color coding is optional.
By entering a date in column H and "Open" in column J, the number of days to close the action is displayed in column I. Entering "Closed" or "Info" in column J sets column I to "-".
Cells at bottom right of table calculate number of "Open", "Closed" and "Info" actions in the list
Cell J1 displays a "running total" of the number of actions - retrieved from the last "Ref no" entered in column B - so each time a new action is added, give it the next Ref no.
Hints....
Enter the names of actionees at the bottom of the sheet and assign them an abbreviation for use in column F.
If you want to change the "Issues"; change them on this sheet (you may need to re-define the named range "Issues" call me if you need assistance); edit the comment box for cell A4 and edit the custom footer via File_Page Setup.
When the action tracker is "up & running", order the actions by: column J - descending (Open actions first), column A - ascending (by "Issue" order), column I - ascending (by due date).
To extend the action tracker to cope with more actions, insert rows - this will ensure that formulae will apply to the new rows eg. for the dropdown list, conditional formatting etc.
You can hide closed actions and empty rows if you want for display and/or printing.
If you have regular weekly meetings and produce monthly reports from the data, note the relevant items under 'Report items', and at month end transfer to your report template.
You can use the "Autofilter" to display only the data you want to see