## 22-11-19
|  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 26
Current Date:
2020-01-10
Item No | Issue | Ref | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Abimbola Akindiilete
1 | SOP |  | H | HR SOFTWARE | AO | LOS STAFF WERE TUTORED ON ITS USAGE AND A WRITTEN TUTORIAL ALSO SENT TO PHC. SOFTWARE NOW IN USE BY ALL STAFF. CONTINUOS UPDATE IN PLACE | 6TH JAN | 8TH JAN | Closed
2 | SOP |  | H | AFFIDAVIT FOR CUG LINES | AO/FA | DONE | 6TH JAN |  | Closed
3 | SOP |  | M | MIKANO AND MANTRAC GENERATOR PRICE LISTS | AO/GMFA | DONE | 6TH JAN |  | Closed
4 | SOP |  | H | PERSONAL TAX IDENTIFICATION AND PAYE | AO | IN PROGRESS | 6TH JAN |  | Open
5 | SOP |  | H | GENERATOR ISSUES | AO/FA | ARTISAN HAS BEEN MOBILISED. JOB WILL BE CONCLUDED NEXTWEEK | 6TH JAN |  | Open
6 | SOP |  | M | DIRTY WATER AND PUMPING MACHINE NOISE IN THE OFFICE | AO | GETTING QUOTES | 6TH JAN |  | Open
7 | SOP |  | H | BIOMETRICS | AO | IN PROGRESS | 7TH JAN |  | Open
8 | SOP |  | H | DOOR BELL FOR DMD | AO | DONE | 7TH JAN |  | Closed
9 | SOP |  | H | SUNKANMI'S HANDOVER NOTE | AO | RECEIVED | 7TH JAN |  | Closed
10 | PA |  | H | OSP FOR PERSONNEL | AO | IN PROGRESS | 7TH JAN |  | Open
11 | SOP |  | M | GREENBAY ISSUES WITH UFUOMA | AO | MAIL SENT TO GREENBAY TO RECTIFY THE ISSUE | 7TH JAN |  | Open
12 | SOP |  | M | STAFF CONFIRMATION | AO | REQUEST SENT | 7TH JAN |  | Closed
13 | SOP |  | H | WELDING AND PAINTING OF FRONT DOOR AT LB | AO | DONE | 7TH JAN |  | Closed
14 | SOP |  | M | NEW SUG LINE REGISTRATION TO COMPANY'S NAME | AO | DONE | 7TH JAN |  | Closed
15 | SOP |  | M | FLIGHT TICKET AND NECCESARY LOGISTICS FOR AZUKA | AO | DONE | 7TH JAN |  | Closed
16 | SOP |  | H | ITEDO ESTATE LANDLORD DUES | AO/FA | SENT TO ACCOUNT FOR ACTION | 8TH JAN |  | Closed
17 | SOP |  | H | QUARTERLY BUDGET LOOKAHEAD | AO | IN PROGRESS | 8TH JAN |  | Open
18 | SOP |  | M | NYSC CLEARANCE FOR CORPERS | AO | DONE | 9TH JAN |  | Closed
19 | PA |  | H | TICKET BOOKING FOR DOTUN,OBIOMA,SALLEY AND TOBI | AO | DONE | 9TH JAN |  | Closed
20 | PA |  | H | LOGISTICS AND TICKET BOOKING FOR AZMAN | AO | DONE | 9TH JAN |  | Closed
21 | SOP |  | H | BATTERY FOR TUNDRA | AO | DONE | 9TH JAN |  | Closed
22 | SOP |  | M | OFFICE PAINTING REQUISTION | AO | SENT TO ACCOUNT FOR ACTION | 9TH JAN |  | Closed
23 | SOP |  | M | REFRESHMENT FOR MANAGEMENT RETREAT | AO | SENT TO ACCOUNT FOR ACTION | 9TH JAN |  | Closed
24 | SOP |  | H | LOCAL TICKET FOR AZMAN AND SHIVA | AO | DONE | 10TH JAN |  | Closed
25 | SOP |  | M | IVAN'S TICKET | AO | IN PROGRESS | 10TH JAN |  | Closed
26 | PA |  | M | FLOWER PLANTING FOR OFFICE BEAUTIFICATION | AO | SENT TO ACCOUNT FOR ACTION | 10TH JAN |  | Closed
[8 empty] | Open: | 7
[8 empty] | Closed: | 19
| Actionees (Key): | [6 empty] | Info:
|  | Priority Key: | H | High Finding
|  |  | M | Medium Finding
|  |  | L | Low Finding
|  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 7 Closed 19 Info