## 22-11-19
|  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 16
Current Date:
2020-01-16
Item No | Issue | Ref | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Abimbola Akindiilete
1 | PA |  | H | OSP FOR PERSONNEL | AO | Concluded. Awaiting go-ahead and information from GMO to start that of other Expats that had altready gone back to their destination before the OSP process started. | 13TH JAN |  | Closed
2 | SOP |  | M | LB GEN HOUSE AND GATE | AO/FA | DONE | 13TH JAN |  | Closed
3 | SOP |  | M | SCREEDING OF MD AND DMD'S OFFICE | AO | DONE | 13th JAN |  | Closed
4 | SOP |  | M | BULBS FOR OFFICE | AO | ALL LIGHTING POINTS COUNTED AND REQUSIITION SENT TO ACCOUNT AND PROCUREMENT TO HANDLE | 13TH JAN |  | Closed
5 | SOP |  | M | CHAIR UPHOLSTERY AND CAPENTRY ISSUES IN THE OFFICE | AO | REQUISITION SENT TO ACCOUNT FOR ACTION | 14TH JAN |  | Closed
6 | SOP |  | H | PAYE | AO | TAX PAYER ID FOR ALL STAFF IN PROGRESS | 14TH JAN |  | Closed
7 | SOP |  | M | AC REPAIR FOR TEA ROOM, MD AND DMD'S | AO | DONE | 14TH JAN |  | Closed
8 | SOP |  | H | PUMPING MACHINE ISSUES | AO | REQUISITION SENT TO ACCOUNT FOR ACTION | 14TH JAN |  | Open
9 | SOP |  | H | BIOMETRICS FOR OFFICE | AO | DONE | 15TH JAN |  | Closed
10 | PA |  | H | TICKET BOOKING FOR IVAN | AO | DONE | 15TH JAN |  | Closed
11 | SOP |  | M | CLEANING ROASTER | AO | ADJUSTEMENT MADE AND DISTRIBUTED ACCORDINGLY | 15TH JAN |  | Closed
12 | SOP |  | M | REMOVAL AND REPLACEMENT OF OUTDATED INFO ON NOTICE BOARD | AO | REMOVAL DONE AND REPLACEMENT HANDEDOVER TO QA/QC | 15TH JAN |  | Closed
13 | SOP |  | H | CUG RENEWAL | AO | DONE | 16TH JAN |  | Closed
14 | SOP |  | M | DPR AND WAEL OFFICE | AO | DONE | 16TH JAN |  | Closed
15 | SOP |  | M | LB CHANDLING AND ISSUES FOR THE WEEK | AO | DONE | 17TH JAN |  | Closed
16 | SOP |  | H | FOLLOW UP EQUIPMENT FREIGHT | AO/LPC | DONE | 17TH JAN |  | Closed
[8 empty] | Open: | 1
[8 empty] | Closed: | 15
| Actionees (Key): | [6 empty] | Info:
|  | Priority Key: | H | High Finding
|  |  | M | Medium Finding
|  |  | L | Low Finding
|  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 1 Closed 15 Info