## 20-01-2020
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 9
Current Date:
2020-01-20
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Eronmonseh Toluwalope
1 | SOP |  |  | H | Record all passwords for every system in Brone | DCAA | Done | 20th Jan |  | Closed
2 | SOP |  |  | H | computer back up hard drive for all systems in Brone | DCAA | in progress | 21st Jan |  | Open
3 | SOP |  |  | M | New generator log book | DCAA | Done | 21st Jan |  | Closed
4 | SOP |  |  | H | Opened new twitter and instagram handle for Brone | DCAA | Done | 22nd Jan |  | Closed
5 | SOP |  |  | H | Opened new journey management administartion book | DCAA | Done | 23rd Jan |  | Closed
6 | SOP |  |  | M | Started a montly cleaning roster | DCAA | Done | 24th Jan |  | Closed
7 | SOP |  |  | M | Opened a weekly generator checklist | DCAA | Done | 24th Jan |  | Closed
8 | SOP |  |  | H | Opened a weekly vehicle checklist | DCAA | Done | 25th Jan |  | Closed
9 | SOP |  |  | H | Documentation of water and fuel | DCAA | Done | 20th Jan | 25th Jan | Closed
[9 empty] | Open: | 1
[9 empty] | Closed: | 8
| Actionees (Key): | [7 empty] | Info:
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding
|  |  |  | L | Low Finding
|  |  |  | Info | Information
Note on B4: 8 SOP- Standard Operating Procedure
Note on K4: Statuses are: Open 1 Closed 8 Info

## 27-01-2020
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 17
[7 empty] | Current Date: |  | 2019-09-13
[7 empty] | 2019-09-13 |  | 2019-09-13
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Abimbola Akindiilete
1 | SOP |  |  | M | FEEDING AND WELFARE OF EXPATRIATES | AO | Done. Expatriates are back to their destinations for now | 9th Sept 2019 | 12th Sept 2019 | Closed
2 | SOP |  |  | H | DATA RECAPTURING FOR OLD STAFF | AO | Data recapturing form has been printed and given to old staff to fill and submit for Pal pension recapturing of data | 9th Sept 2019 |  | Closed
3 | SOP |  |  | H | SATISH'S SALARY AND TELEX COPY | AO | Notice and reminders has been sent to GMA for processing | 9th Sept 2019 |  | Open
4 | SOP |  |  | M | MR. MIKE'S ACCOUNT | AO | BVN has been done and the pin has been sent to the accoiunt officer. Currently working on him getting an ATM. | 13th Sept 2019 |  | Open
5 | SOP |  |  | H | KHAIRAT'S MEDICALS | AO | Done | 9th Sept 2019 |  | Closed
6 | SOP |  |  | H | EXPATRIATE QUARTERS DEMANDS AND ISSUES | AO | Items have been purchased as requested, quotations have been recived from vendor for bathroom renovation and other needed work. | 9th Sept 2019 | 10th Sept 2019 | Open
7 | SOP |  |  | M | ELECTRICAL ISSUES AT SECURITY HOUSE | AO | Done | 11th Sept 2019 |  | Closed
8 | SOP |  |  | M | CHANDLING FOR LEKKI BASE | AO | Done | 9th Sept 2019 |  | Closed
9 | SOP |  |  | M | RESCHEDULING AND ARANGEMENT OF EXPATRIATES' FLIGHTS TO THEIR DESTINATION | AO | Done | 9th Sept 2019 | 12th Sept 2019 | Closed
10 | SOP |  |  | M | MAKING AND SORTING PAYMENTS AND REQUISITIONS | AO | Done for the week | 9th Sept 2019 | 13th Sept 2019 | Closed
11 | SOP |  |  | M | BOOKING OF TICKET FOR PERSONNELS | AO | Done | 11th Sept 2019 |  | Closed
12 | SOP |  |  | M | RUNNING ERANDS ON DMD'S INSTRUCTIONS | AO | Done | 9th Sept 2019 | 13th Sept 2019 | Closed
13 | SOP |  |  | H | MAKING SURE EXPATRIATES ARE CONVEY TO AIRPORT ON TIME FOR THEIR FLIGHTS | AO | Done | 10th Sept 2019 | 13th Sept 2019 | Closed
14 | SOP |  |  | M | PISCES INV 1089 | AO | Done. | 12th Sept 2019 |  | Closed
15 | SOP |  |  | H | DIRECTING JUNIOR STAFF ON KEEPING THE OFFICE CLEAN AND MAKING SURE COMPANY RULES ARE UPHELD | AO | Done | 9th Sept 2019 | 13th Sept 2019 | Open
16 | SOP |  |  | H | SORTING LEKKI BASE NEEDS FOR THE WEEKEND | AO | Done | 13th Sept 2019 |  | Closed
17 | PA |  |  | M | SURVEY DEPARTMENT REQUISITION AND NEEDS FOR IMA AMNI | AO | Done | 11th Sept 2019 | 12th Sept 2019 | Closed
[9 empty] | Open: | 4
[9 empty] | Closed: | 13
| Actionees (Key): | [7 empty] | Info:
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding
|  |  |  | L | Low Finding
|  |  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 10 Closed Info

## 11-10-19
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 21
Current Date:
2019-10-11
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Abimbola Akindiilete
1 | SOP |  |  | H | Zenith account opening for staff | AO | In progress | 7th Oct |  | Open
2 | SOP |  |  | H | HR software training and test running | AO | Training concluded, Test running on going | 7th Oct |  | Open
3 | SOP |  |  | M | Visa's expiry dates for expats | AO | All expat's visas' collated and expiration kept in check | 7th Oct |  | Closed
4 | SOP |  |  | H | NSITF | AO | Payment made, working on certificate | 7th Oct |  | Open
5 | PA |  |  | M | Hotel accomodation for personnel | AO/FO | Done | 7th Oct |  | Closed
6 | SOP |  |  | M | NYSC posting | AO | Done | 7th Oct | 9th Oct | Closed
7 | SOP |  |  | M | Lekki base needs for the week | AO/FO | Done | 7th Oct |  | Closed
8 | SOP |  |  | H | Access control | AO | Done, Biometrics for clocking in and out in progress | 8th Oct |  | Closed
9 | PA |  |  | H | James flight and logistics to PHC | AO | Done | 8th Oct |  | Closed
10 | SOP |  |  | H | Solar house Engineer | AO | Popoola said he got another offer, Collins has no hands on knowledge, will be sending out advert for renewable engineer | 8th Oct |  | Open
11 | PA |  |  | H | Azuka's medicals and certification | AO | Certification and medicals done. TB test to be received tomorrow morning | 9th Oct |  | Closed
12 | SOP |  |  | M | Electricity bill | AO/FO | Bill sent to FO and Part payment made | 9th Oct |  | Closed
13 | SOP |  |  | H | Solar house equipment transfer | AO | In progress | 9th Oct |  | Open
14 | SOP |  |  | H | Twp for Satish | AO | In progress | 9th Oct |  | Open
15 | SOP |  |  | M | Refund for printer | AO | Done | 10th Oct |  | Closed
16 | SOP |  |  | H | New recruitement | AO | In progress | 10th Oct |  | Open
17 | SOP |  |  | H | DMD's office | AO/FO | In progress | 11th Oct |  | Open
18 | SOP |  |  | M | Tundra and Escalade issues | AO/FO | In progress | 11th Oct |  | Open
| SOP |  |  | M | Expat Quarter's issues | AO/FO | In progress | 11th Oct |  | Open
| SOP |  |  | M | Office waste disposal | AO | Done | 11th Oct |  | Closed
| SOP |  |  | M | Flight booking and arrangement for 3 personnel | AO | Done | 11th Oct |  | Closed
[9 empty] | Open: | 10
[9 empty] | Closed: | 11
| Actionees (Key): | [7 empty] | Info:
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding
|  |  |  | L | Low Finding
|  |  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 10 Closed Info