## 9-1-20
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 6
Current Date: 9/1/20
Last updated on: 9/1/2020
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Innocent Edward Isong
1 | HQ |  |  | H | Went to oil mill for Tarpaulin for Jascon 39 | HSE/OM | Pending | 6/1/19 |  | Open
2 | HQ |  |  | H | Sent to marine base for plywood for Jascon 39 | HSE/OS | Pending, 1inch not available | 7/1/19 |  | Open
3 | HQ |  |  | H | Went to Ikoku searching of wood screw | HSE/OS | Done | 7/1/19 |  | Closed
4 | HQ |  |  | H | Picking of 1TB hard drive for Jascon 39 | HSE/GMO | Picking of 1TB hard drive at garrision for Jascon 39 was successful | 8/1/19 |  | Closed
5 | HQ |  |  | H | Sent to Intels camp to collect Portable hard drive | HSE/GMA | Successful | 8/1/19 |  | Closed
6 | HQ |  |  | H | Sent to Fedex for sending of Portable Hard drive | HSE/GMA | sending of Portable Hard drive was successful. | 9/1/19 |  | Closed
[9 empty] | Open: | 2
[9 empty] | Closed: | 4
| Actionees (Key): | [7 empty] | Info: | 0
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding |  | Ebika Ayeba-Enenimiete: Generation Manager Administrative (GMA)
|  |  |  | L | Low Finding |  | Adebisi Adenuga: General Manager Operation (GMO)
|  |  |  | Info | Information |  | Christian Ojetteh: Offshore surveyor (OS)
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open - 2 Closed - 4 Info

## 16-1-20
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 6
Current Date: 16/1/20
Last updated on: 16/1/20
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Innocent Edward Isong
1 | HQ |  |  | H | Equipment brought back from Onne(WAV), Jascon 39 | HSE/GMO | Equipment brought back from Onne (WAV) was successful. | 13/1/20 |  | Closed
2 | HQ |  |  | H | Sent to watergate Technical Services Limited for hiring of equipment (USBL). | HSE/GMO | Successful | 14/1/20 |  | Closed
3 | HQ |  |  | H | Equipment send to Onne (WAV) USBL and MRU | HSE/GMO | Done | 15/1/20 |  | Closed
4 | HQ |  |  | H | Inspection of MV Rubicon at Harbor Master Jetty, Abuloma. | HSE/GMO | Inspection of MV Rubicon at Harbor Master Jetty was successful. | 16/1/20 |  | Closed
5 | HQ |  |  | H | Went to St. John's and garrison for consumables | HSE/GMO | Successful | 16/1/20 |  | Closed
6 | HQ |  |  | H | Sending of Generator and consumables to Bonny | HSE/GMO | Went to Nembe water side for sending of Generator and consumables for Bonny. | 16/1/20 |  | Closed
[9 empty] | Open: | 0
[9 empty] | Closed: | 6
| Actionees (Key): | [7 empty] | Info: | 0
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding
|  |  |  | L | Low Finding |  | Adebisi Adenuga: General Manager Operation (GMO)
|  |  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open - 0 Closed - 6 Info

## 23-1-20
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 6
Current Date: 23/1/20
Last updated on: 23/1/20
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Innocent Edward Isong
1 | HQ |  |  | M | Arranging of equipment brought back from Amni Project. | HSE | Equipment brought back from Amni Project was successful arrange. | 20/1/20 |  | Closed
2 | HQ |  |  | M | Sending the zenith Bank | HSE/GMA | Successful | 21/1/20 |  | Closed
3 | HQ |  |  | M | Cleaning and arranging of the store | HSE | The cleaning and arranging of the store was successful. | 21/1/20 |  | Closed
4 | HQ |  |  | H | Went to St. John's for Bubbles wraps for Jascon 39. | HSE/GMA | Pending. | 22/1/20 | 23/1/20 | Open
5 | HQ |  |  | H | Sent to Ikoku for purchase of Bubble wraps for Jascon 39 | HSE/GMA | Successful | 23/1/20 |  | Closed
6 | HQ |  |  | H | Sent to Onne (WAV) to coodinate equipment and personnel demobilization | HSE/GMO | Personnel demobilization was successful. | 23/1/20 |  | Closed
[9 empty] | Open: | 1
[9 empty] | Closed: | 5
| Actionees (Key): | [7 empty] | Info: | 0
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding |  | Ebika Ayeba-Enenimiete: Generation Manager Administrative (GMA)
|  |  |  | L | Low Finding |  | Adebisi Adenuga: General Manager Operation (GMO)
|  |  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open - 1 Closed - 5 Info