## 22-11-19
|  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 16
Current Date:
2020-01-24
Item No | Issue | Ref | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Abimbola Akindiilete
1 | PA |  | H | Satish TWP extension | AO | Done | 20TH JAN |  | Closed
2 | SOP |  | M | Contract of employment for Trainee Document Controller | AO | DONE | 20TH JAN |  | Closed
3 | SOP |  | M | Observations and necessary adjustment with office generator | AO | DONE | 20TH JAN |  | Closed
4 | SOP |  | M | LB DSTV issues | AO | Done | 20TH JAN |  | Closed
5 | PA |  | M | Hotel reservation for Amni job | AO | Done | 20TH JAN |  | Closed
6 | PA |  | H | Hotel reservation for Exxonmobil Demob | AO | Done | 20TH JAN |  | Closed
7 | SOP |  | M | Range rover and Escalade issues | AO | DONE | 20TH JAN | 24TH JAN | Closed
8 | PA |  | H | AZMAN'S TICKET REFUND LETTER | AO | SENT TO ACCOUNT FOR ACTION | 21ST JAN |  | Closed
9 | SOP |  | H | CUG LINE FOR DOCUMENT CONTROLLER AND RENEWAL FOR NEW CUG LINES | AO | DONE | 21ST JAN |  | Closed
10 | PA |  | H | DATE CHANGE FOR SATISH AND EVANTHIA AND AZMAN | AO | DONE | 21ST JAN | 23RD JAN | Closed
11 | PA |  | M | LOCAL TICKET BOOKING FOP EXPATS, FREELANCE AND PERSONNEL | AO | DONE | 22ND JAN | 23RD JAN | Closed
12 | SOP |  | M | OLD TRANSFORMER FOR ITEDO PAYMENT | AO/FA | DONE | 22ND JAN |  | Closed
13 | SOP |  | H | NEW UNIFORM FOR HAPPINESS LB WORKER | AO | IN progress | 22ND JAN |  | Open
14 | SOP |  | M | TRAINING ON DOCUMENT CONTROL AND ADMIN PROCEDURES FOR TOLU | AO | IN progress | 23RD JAN |  | Open
15 | SOP |  | M | DEMOB PROCESS FOR EXONNMOBIL | AO/LPC | DONE | 23RD JAN |  | Closed
16 | SOP |  | H | PAYE | AO | ON IT. AWAITING GROSS INCOME FROM GMA | 23RD JAN | 24TH JAN | Closed
17 | SOP |  | H | DEVELOPMENT LEVY AND BUSINESS PREMISES FOR PAYE | AO | PAYMENT MADE | 24TH JAN |  | Closed
18 | SOP |  | H | VISIT TO THE TAX OFFICE FOR PAYE ISSUES | AO | DONE | 24TH JAN |  | Closed
19 | SOP |  | M | LB GENERATOR SERVICING | AO | ON IT | 24TH JAN |  | Closed
[8 empty] | Open: | 2
[8 empty] | Closed: | 17
| Actionees (Key): | [6 empty] | Info:
|  | Priority Key: | H | High Finding
|  |  | M | Medium Finding
|  |  | L | Low Finding
|  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 2 Closed 17 Info