## 31-01-2020
|  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 19
Current Date:
2020-01-31
Item No | Issue | Ref | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Abimbola Akindiilete
1 | SOP |  | H | Tax return | AO | Done | 27th Jan |  | Closed
2 | SOP |  | H | Breakfast for the office | AO | Requisition sent to account for action | 27th Jan | 28th Jan | Closed
3 | SOP |  | M | LB generator servicing | AO | Done | 27th Jan |  | Closed
4 | SOP |  | H | Preparation for NPDC audit | AO | Done | 27th Jan | 28th Jan | Closed
5 | SOP |  | H | Requsiition for printer | AO | Sent to account for action | 27th Jan |  | Closed
6 | SOP |  | M | ID card for MD, DMD and Document controller | AO | In Progress | 27th Jan |  | Open
7 | SOP |  | H | Treach pocket size invoice | AO | IN PROGRESS | 27th Jan |  | Open
8 | SOP |  | H | Visitor's tag | AO | In Progress | 27th Jan |  | Open
9 | SOP |  | H | Tundra repair | AO | Requisition sent to account for action | 28th Jan |  | Open
10 | PA |  | H | Steward recruitment for Lekki base | AO | Done | 28th Jan |  | Closed
11 | SOP |  | M | LB staff duty | AO | Done | 29th Jan |  | Closed
12 | SOP |  | M | Solar staff and surveyor recruitment | AO | In Progress | 29th Jan |  | Open
13 | SOP |  | H | OSP for Demola | AO | DONE | 29th Jan | 31st Jan | Closed
14 | SOP |  | M | Solar house uniform | AO | In progress. Awaiting DMD's contact for cheaper price | 29th Jan |  | Open
15 | SOP |  | M | Stationeries and toiletries | AO | Sent to account for action | 29th Jan |  | Closed
16 | SOP |  | H | Range rover AC balance issue | AO/FA | Sorted | 29th Jan |  | Closed
17 | SOP |  | H | Labour relations and Human resource management plans for Brone | AO | Done | 30th Jan |  | Closed
18 | SOP |  | M | CUG lines issues | AO | In progress | 31st Jan |  | Open
19 | PA |  | H | Fire extinguisher servicing | AO | In progress | 31st Jan |  | Open
[8 empty] | Open: | 8
[8 empty] | Closed: | 11
| Actionees (Key): | [6 empty] | Info:
|  | Priority Key: | H | High Finding
|  |  | M | Medium Finding
|  |  | L | Low Finding
|  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 8 Closed 11 Info