## 14-02-2020
|  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 23
|  |  | ACT/BGS/ADM/14022020/06 |  | Current Date:
2020-02-12
Item No | Issue | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Abimbola Akindiilete
1 | SOP | H | HMO RENEWAL | AO | Names complied and sent to GMA and GMFA for approval | 10th Feb |  | Open
2 | SOP | M | Meeting with MD regarding Bersh, recruitment, LB BQ and Printer issues | AO | Done. All instructions are currently being carried out. | 10th Feb |  | Open
3 | SOP | H | PA for MD recruitment | AO | Ongoing. Application forms sent to all applicant | 10th Feb |  | Open
4 | SOP | M | Bricklayer for BQ and Security house issues at LB | AO | Quotation received ans forwarded to account for action | 10th Feb |  | Open
5 | SOP | M | 5 KVA generator | AO | Done | 10th Feb | 11th Feb | Closed
6 | SOP | M | Follow up with Office and LB jobs | AO | Done | 11th Feb |  | Open
7 | SOP | M | Job completion form for LB kitchen tap | AO | Done | 11th Feb |  | Closed
8 | SOP | H | Electricity bill for september | AO | Sent to account for action | 11th Feb |  | Closed
9 | SOP | H | HR software renewal | AO | Sent to account for action | 11th Feb |  | Closed
10 | SOP | M | AC for account/logistics/Bersh | AO/LPC | In progress | 11th Feb |  | Open
11 | SOP | M | Staff file updating | AO | Done | 11th Feb |  | Closed
12 | SOP | M | Quotation for printer | AO | Sent to account for action | 11th Feb |  | Closed
13 | SOP | H | Repair fof LB extensions | AO | Working on another quoatation | 12th Feb |  | Open
14 | SOP | H | CUG renewal budgetting | AO/FA | Sent to account for action | 12th Feb |  | Closed
15 | SOP | M | Get another vendor for extension at LB | AO | In progress | 12th Feb |  | Open
16 | SOP | H | Final induction for Tolu | AO | Done | 13th Feb |  | Closed
17 | SOP | H | 2nd vendor for Solar house Tshirt | AO/AYO | In progress | 13th Feb |  | Open
18 | SOP | M | February birthday request | AO | Sent to account for action | 13th Feb |  | Closed
19 | SOP | H | Digging of Bolanle Oyewole's details for GMA | AO | Done | 13th Feb |  | Closed
20 | SOP | M | Parcel pick up for MD | AO | Done | 13th Feb |  | Closed
21 | SOP | M | Invoice for ID card | AO | Sent to account for action | 13th Feb |  | Closed
22 | SOP | M | Meal for staff for Valentine | AO | Done | 14th Feb |  | Closed
23 | SOP | H | Elevator servicing | AO | Vendor coming for the servicing next week | 14th Feb |  | Open
[7 empty] | Open: | 10
[7 empty] | Closed: | 13
| Actionees (Key): | [5 empty] | Info:
|  | H | High Finding
|  | M | Medium Finding
|  | L | Low Finding
|  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on I4: Statuses are: Open 10 Closed 13 Info