## Sheet1
|  |  |  | TECHNICAL OPERATIONS - ACTION TRACKER |  |  |  |  | Total actions: | 1
[7 empty] | Current Date: 17/02/2020 |  | 14.02.2020
Last updated on: 14/02/2020
Item No | Issue | Ref | Section/Page | Priority | What | Action Party | Update | By When | Days to Close | Status
1 | MS |  | PM | H | MPN Oyot Reporting | GMO/DP | Developed executive summary section, inserted and developed magnetometer and MBES sections in report, QC of text report and charts, MBES output .grd processing up to presentable level | 2020-02-14 | 0 | Closed
2 |  |  | PM | H | MPN Oyot Deliverables | GMO/DP/Survey/QC | Data compilation for survey deliverables | 2020-02-19 |  | Open
3 |  |  | PM | H | MPN Oyot Invoicing | GMO/GMFA | Assisted with operational time interpretation | 2020-02-12 |  | Open
4 | MS |  | OPS | H | Return of rented survey gears | GMO/LPC | Provided guidance to the LPC on shipping invoices and freight processes | 2020-02-14 |  | Closed
5 | MS |  | PM | H | WAV J39 offhire fuel reconciliation | GMO | Reviewed WAV offhire certificate and disputed fuel figures, awaiting feedback. Submitted completed client feedback form for J39 hire | 2020-02-13 |  | Open
6 | MS |  | PM | H | OYOT 2D Data Processing Navigation Issues | GMO | Engaged RDI, MPN and TTS in tripartite meeting to resolve same | 2020-02-14 |  | Open
7 | MS |  | OPS | H | Missing Fem Associates laptop | GMO | Coordinated the boarding of J39 by Innocent at midstream with WAV and search for missing laptop | 2020-02-12 |  | Open
8 | MS |  | OPS | H | TTS invoicing | GMO | Engaged TTS on reason for delay in invoice settlement | 2020-02-11 |  | Open
| Actionees (Key): | [7 empty] | Open | 6
[9 empty] | Closed: | 2
Info:
|  | Priority Key: |  | H | High Finding |  | GMO: Adebisi Adenuga
|  |  |  | M | Medium Finding |  | HR.: Bimbo Akindielete
|  |  |  | L | Low Finding |  | Logistics Cordinator: Dotun Coker
|  |  |  | Info | Information |  | GMFA: Busola Adekanmbi
Note on K4: Statuses are: Open Closed Info