## March
|  | BRONE RENEWABLES-SOLAR HOUSE LIMITED |  |  |  |  | Total actions: | 10
[5 empty] | Current Date: |  | 06.03.2020
Last updated on: 06/03/2020
Item No | Issue | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Action Tracker
1 | Weekly Action Tracker | H | Prepare and submit the weekly action tracker | Ayo | Prepared and sent | 2020-03-06 |  | Closed
2 | Reparing the inverter at Precise lighting Fola Osibo | H | Client seeks to repair his 5KVA inverter installed at his office in Fola Osibo, Lekki | BERSH Team | The faulty 5kva inverter has been repaired, faulty components replaced and undergoing troubleshooting. | 2020-03-06 | 2020-03-09 | Open
3 | Relocating 2v 1000ah batteries from power room to ground floor | H | Batteries are yet to be installed and operational | BERSH Team | Final location (Ground floor kitchen) has been selected by the MD for the installation of inverter batteries. Firstly, there is a need to elevate the area where the batteries are to be positioned because of its poor condition at the moment. Quotation has been retreived from a bricklayer, we are awating another quotation from a carpenter who is to construct a better roof to protect the batteries from rain and sunlight. | 2020-03-02 | 2020-03-15 | Open
4 | Follow up call to Mr. Femi Breeze Energy | H | Solar Pump for rural community | Johnson | Awaiting feedback for meeting from Mr. Femi | 2020-03-03 | 2020-03-15 | Open
5 | MAS Global Express | H | Follow up on the status of the shipment | Ayo | Shipment arrived WHAF, awating transfer of batteries to warehouse. A follow up call will be palced before COB today | 2020-03-04 | 2020-03-15 | Open
6 | Eskay | H | Inverter repair and Imole resolutions | BERSH Team | Eskays 1.25kva has been repaired and deployed to Ekiti. He is awaiting the batteries before the inverter is reinstalled | 2019-03-05 | 15/03/20 | Open
7 | Instagram Post | H | Post on Instagram page | Ayo | Instagram pictures uploaded | 2020-03-06 | 2020-03-06 | Closed
8 | Ms Kenny Gold | H | Marketing brief to Ms. Kenny | BERSH Team | Wants solution installed at her apartment. Energy audit will be carried out and quotation sent to client | 2020-03-04 | 2020-03-04 | Open
9 | Mr. Deji Adesugba | H | Request for solar panel quotation | BERSH team | Client wants to install aditional 12 units of 12v 330W panels. Johnson and I visited to survey and clarify with clients request | 2020-03-06 | 2020-03-06 | Open
10 | Mr. Timothy's Payment | M | Debt retrieval | Ayo | Still unable to get fixed date or amount to pay debt | 2020-03-02 |  | Open
[7 empty] | Open: | 10
[7 empty] | Closed: | 2
| Actionees (Key): | [5 empty] | Info: | -
|  | H | High Finding
|  | M | Medium Finding
|  | L | Low Finding
|  | Info | Information
Note on B4: Priority H - High M - Medium L - Low
Note on I4: Statuses are: Open Closed Info

## Key Features Hints
Issues | Disciplines
1 HQ | HSE/Quality
2 PA | Project admin
3 DS | Diving System
4 DP | Dynamic Positioning
5 MS | Marine Systems
6 CL | Craneage & Lifting
7
8
9 CS | Cost & schedule
Features of "Action tracker"
Cell J1 contains a "running total" of the number of actions - retrieved from the last "Ref no" entered in column B - so each time a new action is added, give it the next Ref no.
Cell A4 contains a comment which is input manually to reflect the issue headings that the actions relate to - the comment should reflect the issues (and their abbreviations) entered on this sheet
Column A uses "data validation" to present a dropdown list of the "issues" from "Sheet2"
Column C uses conditional formatting to color the cell grren if "L" is entered, amber if "M" is entered and red if "H" is entered - the cell does not change color if nothing is entered so priority color coding is optional.
By entering a date in column H and "Open" in column J, the number of days to close the action is displayed in column I. Entering "Closed" or "Info" in column J sets column I to "-".
Cells at bottom right of table calculate number of "Open", "Closed" and "Info" actions in the list
Cell J1 displays a "running total" of the number of actions - retrieved from the last "Ref no" entered in column B - so each time a new action is added, give it the next Ref no.
Hints....
Enter the names of actionees at the bottom of the sheet and assign them an abbreviation for use in column F.
If you want to change the "Issues"; change them on this sheet (you may need to re-define the named range "Issues" call me if you need assistance); edit the comment box for cell A4 and edit the custom footer via File_Page Setup.
When the action tracker is "up & running", order the actions by: column J - descending (Open actions first), column A - ascending (by "Issue" order), column I - ascending (by due date).
To extend the action tracker to cope with more actions, insert rows - this will ensure that formulae will apply to the new rows eg. for the dropdown list, conditional formatting etc.
You can hide closed actions and empty rows if you want for display and/or printing.
If you have regular weekly meetings and produce monthly reports from the data, note the relevant items under 'Report items', and at month end transfer to your report template.
You can use the "Autofilter" to display only the data you want to see