## 9-1-20
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 6
Current Date: 9/1/20
Last updated on: 9/1/2020
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Innocent Edward Isong
1 | HQ |  |  | H | Went to oil mill for Tarpaulin for Jascon 39 | HSE/OM | Pending | 6/1/20 |  | Open
2 | HQ |  |  | H | Sent to marine base for plywood for Jascon 39 | HSE/OS | Pending, 1inch not available | 7/1/20 |  | Open
3 | HQ |  |  | H | Went to Ikoku searching of wood screw | HSE/OS | Done | 7/1/20 |  | Closed
4 | HQ |  |  | H | Picking of 1TB hard drive for Jascon 39 | HSE/GMO | Picking of 1TB hard drive at garrision for Jascon 39 was successful | 8/1/20 |  | Closed
5 | HQ |  |  | H | Sent to Intels camp to collect Portable hard drive | HSE/GMA | Successful | 8/1/20 |  | Closed
6 | HQ |  |  | H | Sent to Fedex for sending of Portable Hard drive | HSE/GMA | sending of Portable Hard drive was successful. | 9/1/20 |  | Closed
[9 empty] | Open: | 2
[9 empty] | Closed: | 4
| Actionees (Key): | [7 empty] | Info: | 0
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding |  | Ebika Ayeba-Enenimiete: Generation Manager Administrative (GMA)
|  |  |  | L | Low Finding |  | Adebisi Adenuga: General Manager Operation (GMO)
|  |  |  | Info | Information |  | Christian Ojetteh: Offshore surveyor (OS)
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open - 2 Closed - 4 Info

## 16-1-20
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 6
Current Date: 16/1/20
Last updated on: 16/1/20
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Innocent Edward Isong
1 | HQ |  |  | H | Equipment brought back from Onne(WAV), Jascon 39 | HSE/GMO | Equipment brought back from Onne (WAV) was successful. | 13/1/20 |  | Closed
2 | HQ |  |  | H | Sent to watergate Technical Services Limited for hiring of equipment (USBL). | HSE/GMO | Successful | 14/1/20 |  | Closed
3 | HQ |  |  | H | Equipment send to Onne (WAV) USBL and MRU | HSE/GMO | Done | 15/1/20 |  | Closed
4 | HQ |  |  | H | Inspection of MV Rubicon at Harbor Master Jetty, Abuloma. | HSE/GMO | Inspection of MV Rubicon at Harbor Master Jetty was successful. | 16/1/20 |  | Closed
5 | HQ |  |  | H | Went to St. John's and garrison for consumables | HSE/GMO | Successful | 16/1/20 |  | Closed
6 | HQ |  |  | H | Sending of Generator and consumables to Bonny | HSE/GMO | Went to Nembe water side for sending of Generator and consumables for Bonny. | 16/1/20 |  | Closed
[9 empty] | Open: | 0
[9 empty] | Closed: | 6
| Actionees (Key): | [7 empty] | Info: | 0
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding
|  |  |  | L | Low Finding |  | Adebisi Adenuga: General Manager Operation (GMO)
|  |  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open - 0 Closed - 6 Info

## 23-1-20
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 6
Current Date: 23/1/20
Last updated on: 23/1/20
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Innocent Edward Isong
1 | HQ |  |  | M | Arranging of equipment brought back from Amni Project. | HSE | Equipment brought back from Amni Project was successful arrange. | 20/1/20 |  | Closed
2 | HQ |  |  | M | Sending the zenith Bank | HSE/GMA | Successful | 21/1/20 |  | Closed
3 | HQ |  |  | M | Cleaning and arranging of the store | HSE | The cleaning and arranging of the store was successful. | 21/1/20 |  | Closed
4 | HQ |  |  | H | Went to St. John's for Bubbles wraps for Jascon 39. | HSE/GMA | Pending. | 22/1/20 | 23/1/20 | Open
5 | HQ |  |  | H | Sent to Ikoku for purchase of Bubble wraps for Jascon 39 | HSE/GMA | Successful | 23/1/20 |  | Closed
6 | HQ |  |  | H | Sent to Onne (WAV) to coodinate equipment and personnel demobilization | HSE/GMO | Personnel demobilization was successful. | 23/1/20 |  | Closed
[9 empty] | Open: | 1
[9 empty] | Closed: | 5
| Actionees (Key): | [7 empty] | Info: | 0
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding |  | Ebika Ayeba-Enenimiete: Generation Manager Administrative (GMA)
|  |  |  | L | Low Finding |  | Adebisi Adenuga: General Manager Operation (GMO)
|  |  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open - 1 Closed - 5 Info

## 30-1-20
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 5
Current Date: 30/1/20
Last updated on: 30/1/2020
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Innocent Edward Isong
1 | HQ |  |  | M | Send to zenith Bank for PAYE print out | HSE/GMA | Pending | 27/1/20 | 28/1/20 | Open
2 | HQ |  |  | M | PAYE Print out from zenith bank | HSE/GMA | PAYE Print out was successsfully collected from zenith bank | 28/1/20 |  | Closed
3 | HQ |  |  | H | Went to Rumuogba Paramount ruler Palace with GMA for Meeting | HSE/GMA | Pending | 29/1/20 |  | Open
4 | HQ |  |  | M | Geomatics Staff and Contractors' HSSE Meeting - January Edition. | HSE | Geomatics Staff and Contractors' HSSE Meeting - January Edition was successful | 29/1/20 |  | Closed
5 | HQ |  |  | M | Scanning of PHC staff PAYE receipt | HSE/GMA | Successful | 30/1/20 |  | Closed
[9 empty] | Open: | 2
[9 empty] | Closed: | 3
| Actionees (Key): | [7 empty] | Info: | 0
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding |  | Ebika Ayeba-Enenimiete: Generation Manager Administrative (GMA)
|  |  |  | L | Low Finding
|  |  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open - 2 Closed - 3 Info

## 06-02-20
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 6
Current Date: 06/02/20
Last updated on: 06/02/2020
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Innocent Edward Isong
1 | HQ |  |  | H | Send to zenith Bank for DPR print out | HSE/GMA | DPR Print out was successsfully collected from zenith bank | 3/2/20 |  | Open
2 | HQ |  |  | H | Sick | HSE/GMA | Sick | 4/2/20 |  | Closed
3 | HQ |  |  | H | Went to onne (WAV Yard) for demobbed of equipment. | HSE/LPC | Equipment was successfully demobbed at Onne (WAV Yard) | 5/2/20 |  | Open
4 | HQ |  |  | H | Supervising Of reloading of equipment to other truck to be send to LOS office. | HSE/LPC | Done | 5/1/20 |  | Closed
5 | HQ |  |  | H | Went to ordinance for Shipping Invoice for the truck. | HSE | Shipping Invoice for the truck was successful | 6/2/20 |  | Closed
6 | HQ |  |  | M | Sent to T & N Press Limited Office for detail and invoice for Printing of Geomatics Calendar for Shell. | HSE/GMA | Successful | 6/2/20 |  | Closed
[9 empty] | Open: | 2
[9 empty] | Closed: | 4
| Actionees (Key): | [7 empty] | Info: | 0
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding |  | Ebika Ayeba-Enenimiete: Generation Manager Administrative (GMA)
|  |  |  | L | Low Finding |  | Oladotun Coker: Logistics and Procurement coodinator (LPC)
|  |  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open - 2 Closed - 4 Info

## 13-02-20
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 4
Current Date: 13/02/20
Last updated on: 13/02/2020
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Innocent Edward Isong
1 | HQ |  |  | M | Went to Oil Mill for tarpaulin for covering of Mikano Generator. | HSE/GMA | Pending | 10/2/20 |  | Open
2 | HQ |  |  | H | Sent to Onne( WAV Yard) for searching of Laptop in Jascon 39 | HSE/GMO/LPC | Pending, because she (Jascon 39) sailed to FOT anchorage. | 11/2/20 | 12/2/20 | Open
3 | HQ |  |  | H | Sent to Onne( FOT Anchorage) for searching of Laptop in Jascon 39. | HSE/GMO/LPC | Searching of Laptop was succssful, but not available | 12/2/20 |  | Closed
4 | HQ |  |  | M | Went to Ogunabali for buying of HDMI and Cross Cable for Fem Associate Nigeria Limited. | HSE/GMO | Done | 13/2/20 |  | Closed
[9 empty] | Open: | 2
[9 empty] | Closed: | 2
| Actionees (Key): | [7 empty] | Info: | 0
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding |  | Ebika Ayeba-Enenimiete: Generation Manager Administrative (GMA)
|  |  |  | L | Low Finding |  | Oladotun Coker: Logistics and Procurement coodinator (LPC)
|  |  |  | Info | Information |  | Adebisi Adenuga: General Manager Operation (GMO)
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open - 2 Closed - 2 Info

## 20-02-20
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 4
Current Date: 20/02/20
Last updated on: 20/02/2020
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Innocent Edward Isong
1 | HQ |  |  | M | Went to Oil Mill for negatioate of tarpauline | HSE/GMA | Pending | 17/2/20 |  | Open
2 | HQ |  |  | H | Searching for Data for Valeport | HSE/OS | Pending | 18/2/20 | 20/2/20 | Open
3 | HQ |  |  | M | Searching for MRU Cable | HSE/SE | Not available in PHC office | 19/2/20 |  | Open
4 | HQ |  |  | M | Data for Valeport was successfully sent to LOS office | HSE/OS | Done | 20/2/20 |  | Closed
[9 empty] | Open: | 3
[9 empty] | Closed: | 1
| Actionees (Key): | [7 empty] | Info: | 0
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding |  | Ebika Ayeba-Enenimiete: Generation Manager Administrative (GMA)
|  |  |  | L | Low Finding |  | Salley Ekeng: Survey Engineer (SE)
|  |  |  | Info | Information |  | Obioma Chikere: Offshore Survey (OS)
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open - 3 Closed - 1 Info

## 05-03-20
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 7
Current Date: 05/03/20
Last updated on: 05/03/2020
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Innocent Edward Isong
1 | HQ |  |  | M | Went to Oil Mill for purchase of Tarpauline for Covering of Mikano Generator. | HSE/GMA | Pending | 02/03/20 |  | Open
2 | HQ |  |  | H | Follow up the AC'S Technician and Supervision of fixing of new AC's for the Office. | HSE/ADMIN/ASSIT. | Fixing of new AC's in the office was successful. | 02/03/20 |  | Closed
3 | HQ |  |  | H | Sent to T & N Press Limited Office for detail and invoice for Reprinting of Geomatics Calendar for Shell. | HSE/OS | Detail and Invoice for reprinting of Geomatics Calaender for Shell. | 03/03/20 |  | Closed
4 | HQ |  |  | M | Went to Oil Mill to pick up the Tarpauline for Covering of Mikano Generator. | HSE/SE | Successful | 03/03/20 |  | Closed
| HQ |  |  | M | Old AC's | HSE | Arranging of Old AC's | 04/03/20 |  | Closed
| HQ |  |  | H | Covering of Mikano Generator with Tarpaulin | HSE/OS | Successful | 04/03/20 |  | Closed
5 | HQ |  |  | M | Fixing of New Binatone fan for PHC Office | HSE/OS | Done | 05/03/20 |  | Closed
[9 empty] | Open: | 1
[9 empty] | Closed: | 6
| Actionees (Key): | [7 empty] | Info: | 0
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding |  | Ebika Ayeba-Enenimiete: Generation Manager Administrative (GMA)
|  |  |  | L | Low Finding |  | Gift Enigha Kozeami. Admin/Assistant.
|  |  |  | Info | Information |  | Christian Ojetteh. Offshore Survey (OS)
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open - 1 Closed - 6 Info