## 06-03-2020
|  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 18
|  |  | ACT/BGS/ADM/06032020/08 |  | Current Date:
2020-03-06
Item No | Issue | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Abimbola Akindiilete
1 | SOP | M | Tundra gear pump | AO | In progress | 2nd March |  | Open
2 | SOP | M | Generator issue | AO | Sorted | 2nd March |  | Closed
3 | SOP | H | Green bay HMO for new staff | AO | Done | 2nd March | 6th March | Closed
4 | SOP | H | Ufuoma's PC issue | AO | Sorted | 2nd March |  | Closed
5 | SOP | H | Johnson Omaba's confirmation of employement | AO | Done | 2nd March |  | Closed
6 | SOP | M | Follow up with artisan | AO | Done | 3rd March |  | Closed
7 | SOP | M | AC installation | AO | Done | 3rd March |  | Closed
8 | SOP | H | Elevator servicing | AO | On it | 3rd March |  | Open
9 | SOP | H | Waste bin payment for LB and Office for the month | AO/FA | Done | 3rd March |  | Closed
10 | SOP | M | Petty cash book follow up | AO | Cash book delivered | 3rd March |  | Closed
11 | SOP | M | Fire extinguisher balance follow up | AO | On it | 3rd March |  | Open
12 | SOP | M | Twp for Satish | AO | Done | 3rd March |  | Closed
13 | SOP | H | Previous employer verification for new staff | AO | On it | 4th March |  | Open
14 | SOP | H | Pumping machine fixing | AO/FA | Done | 4th March |  | Closed
15 | SOP | M | Job completion forms | AO | Done | 4th March |  | Closed
16 | SOP | M | water dispenser and mircowave requisition | AO | Sent to account for action | 5th March |  | Open
17 | SOP | H | Job application form | AO | Sent to applicants | 5th March |  | Open
18 | SOP | M | requisition for EQ | AO | Sent to account for action | 5th March |  | Closed
[7 empty] | Open: | 6
[7 empty] | Closed: | 12
| Actionees (Key): | [5 empty] | Info:
|  | H | High Finding
|  | M | Medium Finding
|  | L | Low Finding
|  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on I4: Statuses are: Open 6 Closed 12 Info