## 10-01-2020
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 12
[7 empty] | Current Date: |  | 10.01.2020
[7 empty] | Last updated on: 10/01/2020 |  | 2020-01-10
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Ebika Ayeba-Enenimiete
1 | PA |  |  | M | SPDC Cad Contract 13th Salary for December 2019 | GMA | Paid | 8th January 2020 |  | Closed
2 | SOP |  |  | H | Requested Documents for Visa for AZMAN YUSOF | GMA | Sent | 1st Jan 2020 |  | Closed
3 | SOP |  |  | H | Request for Quote for Freelance Service | GMA | Document Sent to DMD for Approval and final document sent out to Vendors for Quotes | 3rd and 4th Jan 2020 |  | Closed
4 | PA |  |  | H | Positioning and Seabed Survey at Ima / Langley Contract | GMA/Legal | Executed and Final Copy Received From Amni, Signed and sent back to Amni | 7th Jan 2020 |  | Closed
5 | SOP |  |  | H | Bathymetric Survey for 4 X 150 MW Idowu Ramos Power Plant, Ramos Electric Coal (Lignite) Fired Power Plant Project at Ugbodu, Delta State for RAMOS ELECTRIC POWER LTD | GMA/Tendering Team | Ongoing |  |  | Open
6 | PA |  |  | H | Letters for Letter Head | GMA |  |  |  | Closed
7 | SOP |  |  | H | Follow up with the request for Quotes Received from different vendors and final selection process and counter offers | GMA/GMO | Done/Successful Vendors Selected |  |  | Closed
8 | SOP |  |  | H | Freelance Contract Agreements sent out to the chosen Vendors/Freelance personnel | GMA | Done | 10th Jan 2020 |  | Closed
9 | SOP |  |  | H | WHT Schedules Used and Unused for Tax Issues | GMA | Pending |  |  | Open
10 | SOP |  |  | M | Approval given to the Admin Assist. for Petty Cash Disbursement for this week | GMA | Done |  |  | Closed
11 | SOP |  |  | H | Tiling work for the Survey Pool and Office Entrance/Painting | GMA/AAO | Completed | 9th Jan 2020 |  | Closed
12 | PA |  |  | H | Email Responses to various Clients | GMA | Done |  |  | Closed
[9 empty] | Open: | 2
[9 empty] | Closed: | 10
| Actionees (Key): | [5 empty] | Ebika Ayeba-Enenimiete: GM, Contracts & Administration (GMA) |  | Info: | 0
Mr. Bunmi Akomolede: Managing Director (MD)
|  | Priority Key: |  | H | High Finding |  | Mrs. Tiwalade Akomolede: Deputy Managing Director (DMD)
|  |  |  | M | Medium Finding |  | Mr. Sunkanmi Dairo: Management Trainee (MT)
|  |  |  | L | Low Finding |  | Tender Team: Adebisi A., OloladeOlanipekun
|  |  |  | Info | Information |  | Accounts: Ufuoma Odogu
Adebisi Adenuga (GMO)
Bimbo Akindiilete (AO)
Mike Mattinson (DDO)
Satish Mudaliar (Team Lead, Survey Engrg.)
Busola Adekanmbi (GM, Finance & Admin, LOS
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 2 Closed 10 Info

## 17-01-2020
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 20
[7 empty] | Current Date: |  | 17.01.2020
[7 empty] | Last updated on: 17/01/2020 |  | 2020-01-17
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Ebika Ayeba-Enenimiete
1 | PA |  |  | M | Attestation Letters for Mobil Oyot Project | GMA | Sent to GMO | 14th Jan 2020 |  | Closed
2 | SOP |  |  | H | Follow up on Shell Invoices, November 2019 Due Invoice escalated to Shell Representative | GMA | Done | 14th Jan 2020 |  | Closed
3 | SOP |  |  | H | Request for Quote for Freelance Quinsy Surveyor/Equipment Hire | GMA/Procurements | Done | 13th Jan 2020 |  | Closed
4 | PA |  |  | H | Request for Survey Vessel | GMA/Procurements | Done | 13th Jan 2020 |  | Closed
5 | SOP |  |  | H | Bathymetric Survey for 4 X 150 MW Idowu Ramos Power Plant, Ramos Electric Coal (Lignite) Fired Power Plant Project at Ugbodu, Delta State for RAMOS ELECTRIC POWER LTD | GMA/Tendering Team | Submitted | 15th Jan 2020 & 16th Jan 2020 |  | Closed
6 | PA |  |  | H | Letters for Letter Head | GMA | Done | 15th Jan 2020 |  | Closed
7 | SOP |  |  | H | Commercial Proposal for Bathymetry Survey Amni Petroleum | GMA/Tendering Team | Submitted | 14th Jan 2020 |  | Closed
8 | SOP |  |  | H | Freelance Service Agreements for Quinsy Surveyor under Irentify | GMA | Done | 17th Jan 2020 |  | Closed
9 | PA |  |  | H | Kick Off Meeting at Jascon 39 Onne, Port Harcourt for Analogue Survey Mobil Oyot Project | GMA | Attended | 13th Jan 2020 |  | Closed
10 | PA |  |  | H | Updated Project Charge Sheet for Oyot Mobil Project | GMA | Sent to DMD | 15th Jan 2020 |  | Closed
11 | SOP |  |  | M | Payment Advices for VAT filing requested and received from Shell | GMA | Received | 15th Jan 2020 |  | Closed
12 | SOP |  |  | H | Confirmation Letters for Salley, Ademola, Ozegbe and Obioma | GMA | Done | 16th Jan 2020 |  | Closed
13 | SOP |  |  | H | Letter for Hydrogarphic Survey Permit for Amni Bathymetry Work | GMA | Sent to Dotun | 16th Jan 2020 |  | Closed
14 | PA |  |  | H | Service Order Amendment 8 for Bathymety Survey Project | GMA | Signed and Executed | 16th Jan 2020 |  | Closed
15 | SOP |  |  | H | Contract Templates for Surveyor and Document control | GMA | Sent to Bimbo | 17th Jan 2020 |  | Closed
16 | SOP |  |  | M | Budget PHC Jan Week 4 | GMA/Enigha | Sent to Accounts | 17th Jan 2020 |  | Closed
17 | SOP |  |  | H | WHT Schedules Used and Unused for Tax Issues | GMA | Pending |  |  | Open
18 | SOP |  |  | H | Information for PAYE Annual Returns for Lagos Staff | GMA | Sent to Bimbo | 17th Jan 2020 |  | Closed
19 | SOP |  |  | M | Approval given to the Admin Assist. for Petty Cash Disbursement for this week | GMA | Done |  |  | Closed
20 | PA |  |  | H | Email Responses to various Clients | GMA | Done | 13th-17th Jan 2020 |  | Closed
[9 empty] | Open: | 1
[9 empty] | Closed: | 19
| Actionees (Key): | [5 empty] | Ebika Ayeba-Enenimiete: GM, Contracts & Administration (GMA) |  | Info: | 0
Mr. Bunmi Akomolede: Managing Director (MD)
|  | Priority Key: |  | H | High Finding |  | Mrs. Tiwalade Akomolede: Deputy Managing Director (DMD)
|  |  |  | M | Medium Finding |  | Mr. Sunkanmi Dairo: Management Trainee (MT)
|  |  |  | L | Low Finding |  | Tender Team: Adebisi A., OloladeOlanipekun
|  |  |  | Info | Information |  | Accounts: Ufuoma Odogu
Adebisi Adenuga (GMO)
Bimbo Akindiilete (AO)
Mike Mattinson (DDO)
Satish Mudaliar (Team Lead, Survey Engrg.)
Busola Adekanmbi (GM, Finance & Admin, LOS
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 1 Closed 19 Info

## 24-01-2020
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 16
[7 empty] | Current Date: |  | 24.01.2020
[7 empty] | Last updated on: 24/01/2020 |  | 2020-01-24
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Ebika Ayeba-Enenimiete
1 | PA |  |  | M | Freelance Service Agreement for Dogiye Saigbolo Irentify Consultant | GMA | Sent and Excecuted | 20th Jan 2020 |  | Closed
2 | SOP |  |  | H | Project Charge Sheet for Amni Bathymetry Survey | GMA | Done | 20th Jan 2020 |  | Closed
3 | PA |  |  | H | Email Account for New staff Tolu Eronmonseh | GMA | Done | 20th Jan 2020 |  | Closed
4 | SOP |  |  | H | Extension of CPA for Jascon 39 | GMA | Email sent and Addendum Executed and sent to Mobil | 20th Jan 2020 |  | Closed
5 | PA |  |  | H | Letters for Letter Head | GMA | Done | 20th and 23rd Jan 2020 |  | Closed
6 | SOP |  |  | H | Documents for invoicing requested for GMFA on expats Visas and TWPs | GMA | Forwarded to GMFA | 20th Jan 2020 |  | Closed
7 | SOP |  |  | H | Invoice for AGOL Service Credit Payment for SPDC Cad Contract | GMA | Done and Submitted | 21st Jan 2020 |  | Closed
8 | PA |  |  | H | Bullet point on actions and resolutions in a document format for Exxon Mobil Meeting | GMA | Sent to DMD | 22nd Jan 2020 |  | Closed
9 | PA |  |  | H | Commercial Proposal for Realtime Bathymetry Survey Services for Amni | GMA/Tendering Team | Submitted | 22nd Jan 2020 |  | Closed
10 | SOP |  |  | M | Commercial Proposal for Advisian Worley Group- Geophysical and Geotechnical works | GMA/Tendering Team | Submitted | 23rd Jan 2020 |  | Closed
11 | SOP |  |  | H | More information for Annual Filing of Paye Lagos Staff | GMA | Sent To Bimbo | 23rd Jan 2020 |  | Closed
12 | SOP |  |  | M | Budget PHC Jan Week 5 | GMA/Enigha | Sent to Accounts | 24th Jan 2020 |  | Closed
13 | SOP |  |  | H | WHT Schedules Used and Unused for Tax Issues | GMA | Pending |  |  | Open
14 | SOP |  |  | H | Annual Filing FOR Phc staff and Personal Income Tax for DMD | GMA/Enigha | Pending |  |  | Open
15 | SOP |  |  | M | Approval given to the Admin Assist. for Petty Cash Disbursement for this week | GMA | Done |  |  | Closed
16 | PA |  |  | H | Email Responses to various Clients | GMA | Done | 20th-24th Jan 2020 |  | Closed
[9 empty] | Open: | 2
[9 empty] | Closed: | 14
| Actionees (Key): | [5 empty] | Ebika Ayeba-Enenimiete: GM, Contracts & Administration (GMA) |  | Info: | 0
Mr. Bunmi Akomolede: Managing Director (MD)
|  | Priority Key: |  | H | High Finding |  | Mrs. Tiwalade Akomolede: Deputy Managing Director (DMD)
|  |  |  | M | Medium Finding |  | Mr. Sunkanmi Dairo: Management Trainee (MT)
|  |  |  | L | Low Finding |  | Tender Team: Adebisi A., OloladeOlanipekun
|  |  |  | Info | Information |  | Accounts: Ufuoma Odogu
Adebisi Adenuga (GMO)
Bimbo Akindiilete (AO)
Mike Mattinson (DDO)
Satish Mudaliar (Team Lead, Survey Engrg.)
Busola Adekanmbi (GM, Finance & Admin, LOS
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 2 Closed 14 Info

## 31-01-2020
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 16
[7 empty] | Current Date: |  | 31.01.2020
[7 empty] | Last updated on: 31/01/2020 |  | 2020-01-31
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Ebika Ayeba-Enenimiete
1 | PA |  |  | H | Technical and Commercial Tender for Obodo - Escravos Route Survey for Conoil/CONOG | GMA/Tendering Team | Submitted | 27th Jan 2020 |  | Closed
2 | SOP |  |  | H | Supply of 2 Nos of Feeder Barges in 2 options (Hire & Outright Purchase) for Sterling Petroleum | GMA/Tendering Team | Ongoing |  |  | Open
3 | PA |  |  | H | Documents for NPDC Technical Bids Assessments | GMA/Tendering Team | Done | 31st Jan 2020 |  | Closed
4 | SOP |  |  | H | DTO REGISTRATION FORMS AND REQUIREMENTS - IKIKE SURF PROJECT PRE-QUALIFICAITON | GMA/Tendering Team | Filled and Signed Forms/ Required Documents Submitted | 31st Jan 2020 |  | Closed
5 | PA |  |  | H | Industrial Relations and Human Resource Management Plans - Reviewed | GMA | Done | 30th Jan 2020 |  | Closed
6 | SOP |  |  | H | Salary Breakdown for BEG and expatriates January 2020 | GMA/GMFA/Bimbo | Final Reviewed computed Salaries sent to DMD | 28th Jan 2020 |  | Closed
7 | SOP |  |  | H | MOA with Terralog for Geomechanics Projects | GMA | Sent, awaiting signed Copy | 30th Jan 2020 |  | Open
8 | PA |  |  | H | Requested Remittance Schedule for SPDC Cad Contract Staff for Pension Alliance | GMA | Sent to Pension Alliance | 30th Jan 2020 |  | Closed
9 | PA |  |  | H | Revised Conoil/CONOG Commercial Tender | GMA/Tendering Team | Submitted | 31st Jan 2020 |  | Closed
10 | SOP |  |  | M | ONGC EOI for for providing metocean, geophysical, geotechnical survey services on hiring basis with Petroviz consultants | GMA/Tendering Team | Ongoing |  |  | Open
11 | SOP |  |  | H | MOA with Argyle Petroleum for Geomechanics Project with NPDC | GMA | Signed and Exceuted | 31st Jan 2020 |  | Closed
12 |  |  |  | H | DPR Permit for Technical Consultancy | GMA | Ongoing |  |  | Open
13 | SOP |  |  | M | Budget PHC Feb Week 1 | GMA/Enigha | Sent to Accounts | 31st Jan 2020 |  | Closed
14 | SOP |  |  | H | WHT Schedules Used and Unused for Tax Issues | GMA | Pending |  |  | Open
15 | SOP |  |  | H | Annual Filing FOR Phc staff and Personal Income Tax for DMD | GMA/Enigha | Pending |  |  | Open
16 | SOP |  |  | M | Approval given to the Admin Assist. for Petty Cash Disbursement for this week | GMA | Done |  |  | Closed
17 | PA |  |  | H | Email Responses to various Clients | GMA | Done | 27th-31st Jan 2020 |  | Closed
[9 empty] | Open: | 6
[9 empty] | Closed: | 11
| Actionees (Key): | [5 empty] | Ebika Ayeba-Enenimiete: GM, Contracts & Administration (GMA) |  | Info: | 0
Mr. Bunmi Akomolede: Managing Director (MD)
|  | Priority Key: |  | H | High Finding |  | Mrs. Tiwalade Akomolede: Deputy Managing Director (DMD)
|  |  |  | M | Medium Finding |  | Mr. Sunkanmi Dairo: Management Trainee (MT)
|  |  |  | L | Low Finding |  | Tender Team: Adebisi A., OloladeOlanipekun
|  |  |  | Info | Information |  | Accounts: Ufuoma Odogu
Adebisi Adenuga (GMO)
Bimbo Akindiilete (AO)
Mike Mattinson (DDO)
Satish Mudaliar (Team Lead, Survey Engrg.)
Busola Adekanmbi (GM, Finance & Admin, LOS
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 6 Closed 11 Info

## 07-02-2020
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 16
[7 empty] | Current Date: |  | 07.02.2020
[7 empty] | Last updated on: 07/02/2020 |  | 2020-02-07
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Ebika Ayeba-Enenimiete
1 | PA |  |  | H | Remittance Schedules and payment for Pensions January 2020, PAYE Payment Jan 2020 | GMA/Enigha | Done | 4th Feb 2020 |  | Closed
2 | SOP |  |  | H | Supply of 2 Nos of Feeder Barges in 2 options (Hire & Outright Purchase) for Sterling Petroleum | GMA/Tendering Team | Declined |  |  | Closed
3 | PA |  |  | H | Reference Letter for Lolade Olanipekun | GMA | Done | 7th Feb 2020 |  | Closed
7 | SOP |  |  | H | MOA with Terralog for Geomechanics Projects | GMA | Terralog Declined at this time | 4th Feb 2020 |  | Closed
10 | SOP |  |  | M | ONGC EOI for for providing metocean, geophysical, geotechnical survey services on hiring basis with Petroviz consultants | GMA/Tendering Team | Ongoing |  |  | Open
12 |  |  |  | H | DPR Permit for Technical Consultancy | GMA | Ongoing |  |  | Open
[5 empty] | HMO Renewal List for Brone Personnel | GMA | Done for Phc, Instructed Bimbo to complile the LOS List for final Approval |  |  | Closed
13 | SOP |  |  | M | Budget PHC Feb Week 2 | GMA/Enigha | Sent to Accounts | 7th Feb 2020 |  | Closed
14 | SOP |  |  | H | WHT Schedules Used and Unused for Tax Issues | GMA | Pending |  |  | Open
15 | SOP |  |  | H | Annual Filing FOR Phc staff and Personal Income Tax for DMD | GMA/Enigha | Pending |  |  | Open
16 | SOP |  |  | M | Approval given to the Admin Assist. for Petty Cash Disbursement for this week | GMA | Done |  |  | Closed
17 | PA |  |  | H | Email Responses to various Clients | GMA | Done | 3rd-7th Feb 2020 |  | Closed
[9 empty] | Open: | 6
[9 empty] | Closed: | 11
| Actionees (Key): | [5 empty] | Ebika Ayeba-Enenimiete: GM, Contracts & Administration (GMA) |  | Info: | 0
Mr. Bunmi Akomolede: Managing Director (MD)
|  | Priority Key: |  | H | High Finding |  | Mrs. Tiwalade Akomolede: Deputy Managing Director (DMD)
|  |  |  | M | Medium Finding |  | Mr. Sunkanmi Dairo: Management Trainee (MT)
|  |  |  | L | Low Finding |  | Tender Team: Adebisi A., OloladeOlanipekun
|  |  |  | Info | Information |  | Accounts: Ufuoma Odogu
Adebisi Adenuga (GMO)
Bimbo Akindiilete (AO)
Mike Mattinson (DDO)
Satish Mudaliar (Team Lead, Survey Engrg.)
Busola Adekanmbi (GM, Finance & Admin, LOS
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 6 Closed 11 Info

## 14-02-2020
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 16
[7 empty] | Current Date: |  | 14.02.2020
[7 empty] | Last updated on: 14/02/2020 |  | 2020-02-14
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Ebika Ayeba-Enenimiete
1 | PA |  |  | H | Invoices for January 2020/SEs GIM Services and Geomatics Calender | GMA | Done and Submitted | 12th Feb 2020 |  | Closed
2 | SOP |  |  | H | Commercial offer request and Technical bid - Tender JESA-QI930101-20 Bathymetric | GMA/Tendering Team | Submitted on Jesa Ariba Portal | 14th Feb 2020 |  | Closed
3 | PA |  |  | H | Previous Employer Reference form for Bolanle Oyewole | GMA | I am waiting for information on her last salary before her exiting from Peju, so I put in the right information. I don’t have any 2013 Salary Schedule for LOS staff |  |  | Open
4 | SOP |  |  | H | Salary Schedules for NSITF Audit | GMA | Done | 14th Feb 2020 |  | Closed
5 | SOP |  |  | M | ONGC EOI for for providing metocean, geophysical, geotechnical survey services on hiring basis with Petroviz consultants | GMA/Tendering Team | Ongoing |  |  | Open
6 | SOP |  |  | H | DPR Permit for Technical Consultancy | GMA | Ongoing |  |  | Open
7 | SOP |  |  | H | Letter Head for letters | GMA | Issued | 10th and 14th Feb 2020 |  | Closed
8 | SOP |  |  | M | Budget PHC Feb Week 3 | GMA/Enigha | Sent to Accounts | 14th Feb 2020 |  | Closed
9 | SOP |  |  | H | WHT Schedules Used and Unused for Tax Issues | GMA | Pending |  |  | Open
10 | SOP |  |  | H | Annual Filing FOR Phc staff and Personal Income Tax for DMD | GMA/Enigha | Pending |  |  | Open
11 | SOP |  |  | M | Approval given to the Admin Assist. for Petty Cash Disbursement for this week | GMA | Done |  |  | Closed
12 | PA |  |  | H | Email Responses to various Clients | GMA | Done | 10th-14th Feb 2020 |  | Closed
[9 empty] | Open: | 6
[9 empty] | Closed: | 11
| Actionees (Key): | [5 empty] | Ebika Ayeba-Enenimiete: GM, Contracts & Administration (GMA) |  | Info: | 0
Mr. Bunmi Akomolede: Managing Director (MD)
|  | Priority Key: |  | H | High Finding |  | Mrs. Tiwalade Akomolede: Deputy Managing Director (DMD)
|  |  |  | M | Medium Finding |  | Mr. Sunkanmi Dairo: Management Trainee (MT)
|  |  |  | L | Low Finding |  | Tender Team: Adebisi A., Felix Oyeleke
|  |  |  | Info | Information |  | Accounts: Ufuoma Odogu
Adebisi Adenuga (GMO)
Bimbo Akindiilete (AO)
Mike Mattinson (DDO)
Satish Mudaliar (Team Lead, Survey Engrg.)
Busola Adekanmbi (GM, Finance & Admin, LOS
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 6 Closed 11 Info

## 21-02-2020
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 16
[7 empty] | Current Date: |  | 21.02.2020
[7 empty] | Last updated on: 21/02/2020 |  | 2020-02-21
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Ebika Ayeba-Enenimiete
1 | PA |  |  | H | Invoices for February 2020 SEs for GIM Services | GMA | Done and Submitted | 18th Feb 2020 |  | Closed
2 | SOP |  |  | H | Cover Letter for Exxon Mobil Oyot Project Invoices | GMA | Done | 18th Feb 2020 |  | Closed
3 | PA |  |  | H | Previous Employer Reference form for Bolanle Oyewole | GMA | Done and Submitted | 17th Feb 2020 |  | Closed
4 | SOP |  |  | H | Authorisation Letter to Retrieve CUG Lines | GMA | Done | 18th Feb 2020 |  | Closed
5 | SOP |  |  | H | Updated CV for DMD | GMA | Done | 19th Feb 2020 |  | Closed
6 | SOP |  |  | H | Employment Letter for New Steward Innocent Lekki Base on Brone Letter Head | GMA | Done | 19th Feb 2020 |  | Closed
7 | SOP |  |  | H | Request for Payment advices from SPDC and Due Dates for New Invoices Submitted | GMA | Requested Payment Advices Received from Shell Vendor Services | 19th Feb 2020 |  | Closed
8 | SOP |  |  | H | Vat filing for Payments received in January 2020 | GMA/Enigha | Done | 19th Feb 2020 |  | Closed
9 | SOP |  |  | M | ONGC EOI for for providing metocean, geophysical, geotechnical survey services on hiring basis with Petroviz consultants | GMA/Tendering Team | Done |  |  | Closed
10 | SOP |  |  | H | DPR Permit for Technical Consultancy | GMA | Ongoing |  |  | Open
11 | SOP |  |  | H | Letter Head for letters | GMA | Issued | 10th and 14th Feb 2020 |  | Closed
12 | SOP |  |  | M | Budget PHC Feb Week 4 | GMA/Enigha | Sent to Accounts | 14th Feb 2020 |  | Closed
13 | SOP |  |  | H | WHT Schedules Used and Unused for Tax Issues | GMA | Pending |  |  | Open
14 | SOP |  |  | H | Annual Filing FOR Phc staff and Personal Income Tax for DMD | GMA/Enigha | Ongoing |  |  | Open
15 | SOP |  |  | M | Approval given to the Admin Assist. for Petty Cash Disbursement for this week | GMA | Done |  |  | Closed
16 | PA |  |  | H | Email Responses to various Clients | GMA | Done | 17th-20th Feb 2020 |  | Closed
[9 empty] | Open: | 3
[9 empty] | Closed: | 13
| Actionees (Key): | [5 empty] | Ebika Ayeba-Enenimiete: GM, Contracts & Administration (GMA) |  | Info: | 0
Mr. Bunmi Akomolede: Managing Director (MD)
|  | Priority Key: |  | H | High Finding |  | Mrs. Tiwalade Akomolede: Deputy Managing Director (DMD)
|  |  |  | M | Medium Finding |  | Mr. Sunkanmi Dairo: Management Trainee (MT)
|  |  |  | L | Low Finding |  | Tender Team: Adebisi A., Felix Oyeleke
|  |  |  | Info | Information |  | Accounts: Ufuoma Odogu
Adebisi Adenuga (GMO)
Bimbo Akindiilete (AO)
Mike Mattinson (DDO)
Satish Mudaliar (Team Lead, Survey Engrg.)
Busola Adekanmbi (GM, Finance & Admin, LOS
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 3 Closed 13 Info

## 28-02-2020
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 16
[7 empty] | Current Date: |  | 28.02.2020
[7 empty] | Last updated on: 28/02/2020 |  | 2020-02-28
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Ebika Ayeba-Enenimiete
1 | PA |  |  | H | SPDC TENDER FOR PROVISION OF GEOSCIENCE SUPERVISION SERVICES - IN PARTNERSHIP WITH TRUE BLUE ENERGY | GMA/Tendering Team | Requested Documents Submitted |  |  | Open
2 | SOP |  |  | H | Revised Commercial for Topographic Services for Survey of Oil Pipeline Route OML13 NPDC Block | GMA/Tendering Team | Submitted | 25th Feb 2020 |  | Closed
3 | PA |  |  | H | TWP Documents and Request Letter for Satish Mudaliar | GMA | Sent | 25th Feb 2020 |  | Closed
4 | SOP |  |  | H | Salaries for February 2020 | GMA | Done | 26th Feb 2020 |  | Closed
5 | SOP |  |  | H | Indemnity Letter to Zenith Bank as Instructed by DMD | GMA | Done | 19th Feb 2020 |  | Closed
6 | SOP |  |  | H | Amni Commercial Proposal for Tidal Observation at Tubu | GMA/Tendering Team | Submitted | 26th Feb 2020 |  | Closed
7 | SOP |  |  | H | Expatriates Salary Breakdown for Feb 2020 | GMA | Done | 27th feb 2020 |  | Closed
8 | SOP |  |  | H | MOA with True Blue Energy for SPDC Geoscience Supervision tender | GMA | Done | 25th Feb 2020 |  | Closed
9 | SOP |  |  | M | Instructions & Discussion with Temi Adegbite for Legal input on GMO's email response on the letters received from ACME Lawyer for Brone Email Response | GMA/Legal | Done | 25th & 27th Feb 2020 |  | Open
10 | SOP |  |  | H | DPR Permit for Technical Consultancy | GMA | Ongoing |  |  | Open
11 | SOP |  |  | M | Paye Phc and Pensions for Feb 2020 | GMA | Remittance schedules and payments made for Pension and Paye payment made | 28th Feb 2020 |  | Closed
12 | SOP |  |  | M | Budget PHC Mar Week 1 | GMA/Enigha | Sent to Accounts | 14th Feb 2020 |  | Closed
13 | SOP |  |  | H | WHT Schedules Used and Unused for Tax Issues | GMA | Pending |  |  | Open
14 | SOP |  |  | H | Annual Filing FOR Phc staff and Personal Income Tax for DMD | GMA/Enigha | Ongoing |  |  | Open
15 | SOP |  |  | M | Approval given to the Admin Assist. for Petty Cash Disbursement for this week | GMA | Done |  |  | Closed
16 | PA |  |  | H | Email Responses to various Clients | GMA | Done | 24th-28th Feb 2020 |  | Closed
[9 empty] | Open: | 5
[9 empty] | Closed: | 11
| Actionees (Key): | [5 empty] | Ebika Ayeba-Enenimiete: GM, Contracts & Administration (GMA) |  | Info: | 0
Mr. Bunmi Akomolede: Managing Director (MD)
|  | Priority Key: |  | H | High Finding |  | Mrs. Tiwalade Akomolede: Deputy Managing Director (DMD)
|  |  |  | M | Medium Finding |  | Mr. Sunkanmi Dairo: Management Trainee (MT)
|  |  |  | L | Low Finding |  | Tender Team: Adebisi A., Felix Oyeleke
|  |  |  | Info | Information |  | Accounts: Ufuoma Odogu
Adebisi Adenuga (GMO)
Bimbo Akindiilete (AO)
Mike Mattinson (DDO)
Satish Mudaliar (Team Lead, Survey Engrg.)
Busola Adekanmbi (GM, Finance & Admin, LOS
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 5 Closed 11 Info

## 06-03-2020
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 16
[7 empty] | Current Date: |  | 06.03.2020
[7 empty] | Last updated on: 06/03/2020 |  | 2020-03-06
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Ebika Ayeba-Enenimiete
1 | PA |  |  | H | SPDC TENDER FOR PROVISION OF GEOSCIENCE SUPERVISION SERVICES - IN PARTNERSHIP WITH TRUE BLUE ENERGY | GMA/Tendering Team | Requested Documents Submitted | 2nd March 2020 |  | Closed
2 | SOP |  |  | H | Reviewed and Updated Previous Employer Reference Form for Brone | GMA | Submitted | 2nd March 2020 |  | Closed
3 | PA |  |  | H | REQUEST FOR QUOTE FOR SUPPLY OF SURVEY MATERIALS FOR ANOH-SPDC PROJECT | GMA/Tendering Team | Brone does not have the requested equipment | 3rd March 2020 |  | Closed
4 | SOP |  |  | H | Commercial Proposal Amni for Tubu SeaBed Survey & Close Grid Bathymetry | GMA/Tendering Team | Submitted | 3rd March 2020 |  | Closed
5 | SOP |  |  | H | Commercial Proposal Amni Real-Time Bathymetry Survey | GMA/Tendering Team | Submitted | 3rd March 2020 |  | Closed
6 | SOP |  |  | H | Re-Submitted Amni Commercial Proposal for Tidal Observation at Tubu | GMA/Tendering Team | Submitted | 3rd March 2020 |  | Closed
7 | SOP |  |  | H | AMNI Contractor Registration online | GMA | Done and Requested Documents Uploaded | 4th March 2020 |  | Closed
8 | SOP |  |  | H | SHARJAH KYC- form for bureau | GMA | Filled | 6th March 2020 |  | Closed
9 | SOP |  |  | M | Whatsapp Meeting with Temi and GMO on plans and Brone stand for the re-scheduled meeting for 6th March 2020 with ACME and Lawyer | GMA/Legal/GMO | Done | 5th March 2020 |  | Closed
10 | SOP |  |  | H | DPR Permit for Technical Consultancy | GMA | Under Processing on the OGISP/DPR Portal |  |  | Open
11 | SOP |  |  | M | Query Letter for Dotun | GMA | Sent to Busola | 6th March 2020 |  | Closed
12 | SOP |  |  | M | Budget PHC Mar Week 2 | GMA/Enigha | Sent to Accounts | 6th March 2020 |  | Closed
13 | SOP |  |  | H | WHT Schedules Used and Unused for Tax Issues | GMA | Ongoing, Used ones are being filed |  |  | Open
14 | SOP |  |  | H | Annual Filing FOR Phc staff and Personal Income Tax for DMD | GMA/Enigha | Ongoing |  |  | Open
15 | SOP |  |  | M | Approval given to the Admin Assist. for Petty Cash Disbursement for this week | GMA | Done |  |  | Closed
16 | PA |  |  | H | Email Responses to various Clients | GMA | Done | 2nd-6th Mar 2020 |  | Closed
[9 empty] | Open: | 3
[9 empty] | Closed: | 13
| Actionees (Key): | [5 empty] | Ebika Ayeba-Enenimiete: GM, Contracts & Administration (GMA) |  | Info: | 0
Mr. Bunmi Akomolede: Managing Director (MD)
|  | Priority Key: |  | H | High Finding |  | Mrs. Tiwalade Akomolede: Deputy Managing Director (DMD)
|  |  |  | M | Medium Finding |  | Mr. Sunkanmi Dairo: Management Trainee (MT)
|  |  |  | L | Low Finding |  | Tender Team: Adebisi A., Felix Oyeleke
|  |  |  | Info | Information |  | Accounts: Ufuoma Odogu
Adebisi Adenuga (GMO)
Bimbo Akindiilete (AO)
Mike Mattinson (DDO)
Satish Mudaliar (Team Lead, Survey Engrg.)
Busola Adekanmbi (GM, Finance & Admin, LOS
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 3 Closed 13 Info

## 13-03-2020
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 21
[7 empty] | Current Date: |  | 13.03.2020
[7 empty] | Last updated on: 13/03/2020 |  | 2020-03-13
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Ebika Ayeba-Enenimiete
1 | PA |  |  | H | Reviewed Employment Letter sent by Bimbo and sent letter headed acceptance letter for Felix Oyeleke | GMA | Sent back to Bimbo after reviewing and formatting | 9th March 2020 |  | Closed
2 | SOP |  |  | H | Confirmation Letter for Johnson Omaba | GMA | Sent | 11th March 2020 |  | Closed
3 | PA |  |  | H | Siwes Letter of Engagement and Acceptance Letter on Letter head for High Praise | GMA | Sent back to Bimbo | 9th March 2020 |  | Closed
4 | SOP |  |  | H | Follow up on Brone Nipex Status and Reactivation | GMA | Sent Updated documents and payments | 10th -13th March 2020 |  | Closed
5 | SOP |  |  | H | SPDC Staff Salaries Feb 2020, Pension Oct 2019 and Paye Feb 2020 | GMA | Paid and remittance Schedules sent to PFAs | 10th March 2020 |  | Closed
6 | SOP |  |  | H | INVITATION TO TENDER: DEBRIS SURVEY AND SEWOP POSITIONING SERVICES FOR AMNI PETROLEUM | GMA/Tendering Team | Ongoing |  | 18th March 2020 | Open
7 | SOP |  |  | H | Filled and Signed Acknowledgement Form for Amni Debris Survey and Sewop Positioning | GMA | Submitted | 13th March 2020 |  | Closed
8 | SOP |  |  | H | Registration on JESA Portal | GMA | Ongoing |  |  | Open
9 | SOP |  |  | H | VAT Instalment payment for 2014/2015 Audit Liability Raised | GMA/Enigha | Paid and Filed at VAT Office | 12th March 2020 |  | Closed
10 | SOP |  |  | H | Re-Submitted requested document for insurance for the re-opened AMNI Contractor Registration online | GMA | Done and Requested Document Uploaded | 13th March 2020 |  | Closed
11 | SOP |  |  | H | Re-Drafted Query Letter for Dotun | GMA | Sent To GMFA - Issued | 11th March 2020 |  | Closed
12 | SOP |  |  | M | Discounted Commercial Proposal for Tidal Observation at Tubu | GMA/Tendering Team | Submitted | 11th March 2020 |  | Closed
13 | SOP |  |  | H | DPR Permit for Technical Consultancy | GMA | Under Processing on the OGISP/DPR Portal |  |  | Open
14 | SOP |  |  | M | Letter Head for USD Withdrawals and letter of authority | GMA | Sent to Busola/Ufuoma | 9th & 12th March 2020 |  | Closed
15 | SOP |  |  | H | Confirmation of Remittance of Accrued Pension Contribution for IBTC pensions | GMA | Letter sent | 12th March 2020 |  | Closed
16 | SOP |  |  | M | Total E & P Nipex Geophysical and Geotechnical Tender | GMA & Tendering Team | Ongoing |  | 6th April 2020 | Open
17 | SOP |  |  | M | Budget PHC Mar Week 3 | GMA/Enigha | Sent to Accounts | 6th March 2020 |  | Closed
18 | SOP |  |  | H | WHT Schedules Used and Unused for Tax Issues | GMA | Ongoing, Used ones are being filed |  |  | Open
19 | SOP |  |  | H | Annual Filing FOR Phc staff and Personal Income Tax for DMD | GMA/Enigha | Done |  |  | Closed
20 | SOP |  |  | M | Approval given to the Admin Assist. for Petty Cash Disbursement for this week | GMA | Done |  |  | Closed
21 | PA |  |  | H | Email Responses to various Clients | GMA | Done | 9th-13th Mar 2020 |  | Closed
[9 empty] | Open: | 5
[9 empty] | Closed: | 16
| Actionees (Key): | [5 empty] | Ebika Ayeba-Enenimiete: GM, Contracts & Administration (GMA) |  | Info: | 0
Mr. Bunmi Akomolede: Managing Director (MD)
|  | Priority Key: |  | H | High Finding |  | Mrs. Tiwalade Akomolede: Deputy Managing Director (DMD)
|  |  |  | M | Medium Finding |  | Mr. Sunkanmi Dairo: Management Trainee (MT)
|  |  |  | L | Low Finding |  | Tender Team: Adebisi A., Felix Oyeleke
|  |  |  | Info | Information |  | Accounts: Ufuoma Odogu
Adebisi Adenuga (GMO)
Bimbo Akindiilete (AO)
Mike Mattinson (DDO)
Satish Mudaliar (Team Lead, Survey Engrg.)
Busola Adekanmbi (GM, Finance & Admin, LOS
Tolu Eronmonseh
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 5 Closed 16 Info