## 09- 1302020
|  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 10
[5 empty] | Current Date: |  | 13.03.20
[5 empty] | Last updated on: 13/03/2020 |  | 2020-03-13
Item No | Issue | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Action Tracker
1 |  | info | Preparation and study for side scan sonar seminar | Ademola |  | 2020-10-02 |  | open
2 |  | H | Rearrangement of the lab | Ademola, chukwujindu, salley |  | 2020-11-02 |  | open
3 |  | H | testing and diagnostics check on some equipments | Ademola, chukwujindu, salley |  | 2020-12-02 |  | open
4 |  | H | inventory update | Ademola, chukwujindu, salley |  | 13/02/2020 |  | open
5 |  | H | Equipment test | Ademola, chukwujindu,salley |  | 13/02/2020 |  | Closed
6 |  | H | Preparation and study for side scan sonar seminar | Ademola |  | 14/02/2020 |  | open
7 |  | info | Subbuttom profiler seminar | all technical crew |  |  |  | Closed
8 |  | info | Exxon mobil project debriefing | all technical crew |  |  |  | Closed
9 |  | info | Sidescan sonar seminar | all technical crew |  |  |  | Closed
10 |  | H | Equipment test | ademola, chukwujindu, salley |  |  |  | open
[7 empty] | Open | 6
[7 empty] | Closed | 4
| Actionees (Key): | [5 empty] | Info | 4
|  | H | High Finding
|  | M | Medium Finding
|  | L | Low Finding
|  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on I4: Statuses are: Open Closed Info

## Key Features Hints
Issues | Disciplines
1 HQ | HSE/Quality
2 PA | Project admin
3 DS | Diving System
4 DP | Dynamic Positioning
5 MS | Marine Systems
6 CL | Craneage & Lifting
7
8
9 CS | Cost & schedule
Features of "Action tracker"
Cell J1 contains a "running total" of the number of actions - retrieved from the last "Ref no" entered in column B - so each time a new action is added, give it the next Ref no.
Cell A4 contains a comment which is input manually to reflect the issue headings that the actions relate to - the comment should reflect the issues (and their abbreviations) entered on this sheet
Column A uses "data validation" to present a dropdown list of the "issues" from "Sheet2"
Column C uses conditional formatting to color the cell grren if "L" is entered, amber if "M" is entered and red if "H" is entered - the cell does not change color if nothing is entered so priority color coding is optional.
By entering a date in column H and "Open" in column J, the number of days to close the action is displayed in column I. Entering "Closed" or "Info" in column J sets column I to "-".
Cells at bottom right of table calculate number of "Open", "Closed" and "Info" actions in the list
Cell J1 displays a "running total" of the number of actions - retrieved from the last "Ref no" entered in column B - so each time a new action is added, give it the next Ref no.
Hints....
Enter the names of actionees at the bottom of the sheet and assign them an abbreviation for use in column F.
If you want to change the "Issues"; change them on this sheet (you may need to re-define the named range "Issues" call me if you need assistance); edit the comment box for cell A4 and edit the custom footer via File_Page Setup.
When the action tracker is "up & running", order the actions by: column J - descending (Open actions first), column A - ascending (by "Issue" order), column I - ascending (by due date).
To extend the action tracker to cope with more actions, insert rows - this will ensure that formulae will apply to the new rows eg. for the dropdown list, conditional formatting etc.
You can hide closed actions and empty rows if you want for display and/or printing.
If you have regular weekly meetings and produce monthly reports from the data, note the relevant items under 'Report items', and at month end transfer to your report template.
You can use the "Autofilter" to display only the data you want to see