## 13-09-19
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 17
[7 empty] | Current Date: |  | 2019-09-13
[7 empty] | 2019-09-13 |  | 2019-09-13
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Abimbola Akindiilete
1 | SOP |  |  | M | FEEDING AND WELFARE OF EXPATRIATES | AO | Done. Expatriates are back to their destinations for now | 9th Sept 2019 | 12th Sept 2019 | Closed
2 | SOP |  |  | H | DATA RECAPTURING FOR OLD STAFF | AO | Data recapturing form has been printed and given to old staff to fill and submit for Pal pension recapturing of data | 9th Sept 2019 |  | Closed
3 | SOP |  |  | H | SATISH'S SALARY AND TELEX COPY | AO | Notice and reminders has been sent to GMA for processing | 9th Sept 2019 |  | Open
4 | SOP |  |  | M | MR. MIKE'S ACCOUNT | AO | BVN has been done and the pin has been sent to the accoiunt officer. Currently working on him getting an ATM. | 13th Sept 2019 |  | Open
5 | SOP |  |  | H | KHAIRAT'S MEDICALS | AO | Done | 9th Sept 2019 |  | Closed
6 | SOP |  |  | H | EXPATRIATE QUARTERS DEMANDS AND ISSUES | AO | Items have been purchased as requested, quotations have been recived from vendor for bathroom renovation and other needed work. | 9th Sept 2019 | 10th Sept 2019 | Open
7 | SOP |  |  | M | ELECTRICAL ISSUES AT SECURITY HOUSE | AO | Done | 11th Sept 2019 |  | Closed
8 | SOP |  |  | M | CHANDLING FOR LEKKI BASE | AO | Done | 9th Sept 2019 |  | Closed
9 | SOP |  |  | M | RESCHEDULING AND ARANGEMENT OF EXPATRIATES' FLIGHTS TO THEIR DESTINATION | AO | Done | 9th Sept 2019 | 12th Sept 2019 | Closed
10 | SOP |  |  | M | MAKING AND SORTING PAYMENTS AND REQUISITIONS | AO | Done for the week | 9th Sept 2019 | 13th Sept 2019 | Closed
11 | SOP |  |  | M | BOOKING OF TICKET FOR PERSONNELS | AO | Done | 11th Sept 2019 |  | Closed
12 | SOP |  |  | M | RUNNING ERANDS ON DMD'S INSTRUCTIONS | AO | Done | 9th Sept 2019 | 13th Sept 2019 | Closed
13 | SOP |  |  | H | MAKING SURE EXPATRIATES ARE CONVEY TO AIRPORT ON TIME FOR THEIR FLIGHTS | AO | Done | 10th Sept 2019 | 13th Sept 2019 | Closed
14 | SOP |  |  | M | PISCES INV 1089 | AO | Done. | 12th Sept 2019 |  | Closed
15 | SOP |  |  | H | DIRECTING JUNIOR STAFF ON KEEPING THE OFFICE CLEAN AND MAKING SURE COMPANY RULES ARE UPHELD | AO | Done | 9th Sept 2019 | 13th Sept 2019 | Open
16 | SOP |  |  | H | SORTING LEKKI BASE NEEDS FOR THE WEEKEND | AO | Done | 13th Sept 2019 |  | Closed
17 | PA |  |  | M | SURVEY DEPARTMENT REQUISITION AND NEEDS FOR IMA AMNI | AO | Done | 11th Sept 2019 | 12th Sept 2019 | Closed
[9 empty] | Open: | 4
[9 empty] | Closed: | 13
| Actionees (Key): | [7 empty] | Info:
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding
|  |  |  | L | Low Finding
|  |  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 10 Closed Info

## 11-10-19
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 21
Current Date:
2019-10-11
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Abimbola Akindiilete
1 | SOP |  |  | H | Zenith account opening for staff | AO | In progress | 7th Oct |  | Open
2 | SOP |  |  | H | HR software training and test running | AO | Training concluded, Test running on going | 7th Oct |  | Open
3 | SOP |  |  | M | Visa's expiry dates for expats | AO | All expat's visas' collated and expiration kept in check | 7th Oct |  | Closed
4 | SOP |  |  | H | NSITF | AO | Payment made, working on certificate | 7th Oct |  | Open
5 | PA |  |  | M | Hotel accomodation for personnel | AO/FO | Done | 7th Oct |  | Closed
6 | SOP |  |  | M | NYSC posting | AO | Done | 7th Oct | 9th Oct | Closed
7 | SOP |  |  | M | Lekki base needs for the week | AO/FO | Done | 7th Oct |  | Closed
8 | SOP |  |  | H | Access control | AO | Done, Biometrics for clocking in and out in progress | 8th Oct |  | Closed
9 | PA |  |  | H | James flight and logistics to PHC | AO | Done | 8th Oct |  | Closed
10 | SOP |  |  | H | Solar house Engineer | AO | Popoola said he got another offer, Collins has no hands on knowledge, will be sending out advert for renewable engineer | 8th Oct |  | Open
11 | PA |  |  | H | Azuka's medicals and certification | AO | Certification and medicals done. TB test to be received tomorrow morning | 9th Oct |  | Closed
12 | SOP |  |  | M | Electricity bill | AO/FO | Bill sent to FO and Part payment made | 9th Oct |  | Closed
13 | SOP |  |  | H | Solar house equipment transfer | AO | In progress | 9th Oct |  | Open
14 | SOP |  |  | H | Twp for Satish | AO | In progress | 9th Oct |  | Open
15 | SOP |  |  | M | Refund for printer | AO | Done | 10th Oct |  | Closed
16 | SOP |  |  | H | New recruitement | AO | In progress | 10th Oct |  | Open
17 | SOP |  |  | H | DMD's office | AO/FO | In progress | 11th Oct |  | Open
18 | SOP |  |  | M | Tundra and Escalade issues | AO/FO | In progress | 11th Oct |  | Open
| SOP |  |  | M | Expat Quarter's issues | AO/FO | In progress | 11th Oct |  | Open
| SOP |  |  | M | Office waste disposal | AO | Done | 11th Oct |  | Closed
| SOP |  |  | M | Flight booking and arrangement for 3 personnel | AO | Done | 11th Oct |  | Closed
[9 empty] | Open: | 10
[9 empty] | Closed: | 11
| Actionees (Key): | [7 empty] | Info:
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding
|  |  |  | L | Low Finding
|  |  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 10 Closed Info

## 18-10-19
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 18
Current Date:
2019-10-18
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Abimbola Akindiilete
1 | SOP |  |  | M | flight for GMO | AO | Done | 14th Oct |  | Closed
2 | PA |  |  | H | Issues with Azuka's training certification | AO | Done | 14th Oct |  | Closed
3 | SOP |  |  | H | Safety Boot for Azuka | AO | Done | 14th Oct |  | Closed
4 | SOP |  |  | H | Solar engineer recruitment | AO | In progress | 14th Oct |  | Open
5 | SOP |  |  | H | Procurement officer recruitment | AO | In progress | 14th Oct |  | Open
6 | SOP |  |  | M | HSE officer interview | AO | Done | 14th Oct | 16th Oct | Closed
7 | PA |  |  | M | James demobilisation and travelling processes | AO/FO | Done | 14th Oct | 18th Oct | Closed
8 | PA |  |  | H | Twp for Satish | AO | Done | 14th Oct |  | Closed
9 | PA |  |  | H | Expatriates's retrun tickets reminder and opening | AO | Done | 15th Oct |  | Closed
10 | SOP |  |  | M | DMD's office | AO | In progress. Requisition sent | 15th Oct |  | Closed
11 | PA |  |  | H | TWP for MATARA | AO | Done | 15th Oct |  | Closed
12 | SOP |  |  | M | Zenith account opening for new staff | AO | Done. Awaiting acount numbers of PHC staff | 16th Oct |  | Closed
13 | SOP |  |  | H | Solar house equipement transfer | AO | Done | 16th Oct | 19th Oct | Closed
14 | PA |  |  | H | Prashant's demobilisation and travelling arrangement | AO | Done | 17th Oct |  | Closed
15 | SOP |  |  | M | Accountant's new office space | AO | Done | 17th Oct | 18th Oct | Closed
16 | PA |  |  | H | Matara's business visa and traveeling arrangement | AO | Done | 17th Oct |  | Closed
17 | PA |  |  | H | Matara's medicals and logistics to the vessel | AO | Done | 18th |  | Closed
18 | SOP |  |  | M | Brone policy handbook | AO | In progress | 18th Oct |  | Open
[9 empty] | Open: | 3
[9 empty] | Closed: | 15
| Actionees (Key): | [7 empty] | Info:
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding
|  |  |  | L | Low Finding
|  |  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 10 Closed Info

## 25-10-19
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 18
Current Date:
2019-10-25
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Abimbola Akindiilete
1 | SOP |  |  | H | Solar engineer recruitment | AO | In progress. Waiting for Bersh team to arrange for Practicals for 2 qualified applicants | 21st Oct | 24th Oct | Open
2 | SOP |  |  | H | Sorting mail server error | AO | Done | 21st Oct | 24th Oct | Closed
3 | SOP |  |  | H | CUG renewal | AO | Done | 21st Oct |  | Closed
4 | SOP |  |  | H | Setting the ball rolling for new GMFA | AO | Done | 21st Oct | 24th Oct | Closed
5 | PA |  |  | H | Visa renewal for Prakash | AO | In progress | 22nd Oct | 23rd Oct | Open
6 | SOP |  |  | M | Urgent office needs | AO | Done | 22nd Oct |  | Closed
7 | SOP |  |  | M | Clerical staffs introduction to GMFA | AO | Done | 22nd Oct |  | Closed
8 | SOP |  |  | H | GMO's unused ticket issue | AO | Solved | 22nd Oct |  | Closed
9 | SOP |  |  | M | Fumigation of the office | AO | Requisition and quostations sent to FO for action | 22nd Oct |  | Open
10 | SOP |  |  | H | June till date expatriate tickets | AO | In progress | 23rd Oct |  | Open
11 | OP |  |  | H | ISO Audit | AO | Date fixed. | 23rd Oct |  | Closed
12 | SOP |  |  | M | Admin Assitant recruitment for CLO client | AO | Sample form sent to GMFA for approval | 23rd Oct |  | Open
13 | SOP |  |  | H | Salary details | AO | Done | 24th Oct |  | Closed
14 | SOP |  |  | H | Request letter for NSITF compliance certificate | AO | Done | 24th Oct |  | Closed
15 | SOP |  |  | H | Enquiries for work visa for Matara | AO | Done | 24th Oct |  | Closed
16 | SOP |  |  | H | Sudiyonno's return ticket opening | AO | In progress | 25th Oct |  | Open
17 | SOP |  |  | H | Office stationeries and toilteries for November | AO | Done | 25th Oct |  | Closed
18 | SOP |  |  | M | General cleaning preparation and training of support staff | AO | Done | 25th Oct |  | Closed
[9 empty] | Open: | 6
[9 empty] | Closed: | 12
| Actionees (Key): | [7 empty] | Info:
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding
|  |  |  | L | Low Finding
|  |  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 10 Closed Info

## 01-11-19
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 21
Current Date:
2019-11-01
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Abimbola Akindiilete
1 | SOP |  |  | H | ID card for GMFA | AO | Done | 28th Oct |  | Closed
2 | SOP |  |  | M | Obioma's travelling logistics | AO | Done | 28th Oct |  | Closed
3 | SOP |  |  | M | Updating salary details | AO | Done | 28th Oct |  | Closed
4 | SOP |  |  | M | Security check memo for all staff | AO | Done | 28th Oct |  | Closed
5 | PA |  |  | M | CUG matters (affidavit,authorisation letter etc) | AO | Done | 28th Oct |  | Open
6 | SOP |  |  | M | GMFA'S PC | AO | The needed funds for repair is too much. New one will be purchased. | 28th Oct |  | Closed
7 | SOP |  |  | M | Solar engineer recruitment | AO | Done | 28th Oct | 1st Nov | Closed
8 | SOP |  |  | H | ticket and visas from june till date | AO | The available documents has been compiled and sent to GMFA | 28th Oct | 1st Nov | Closed
9 | SOP |  |  | H | Recruitment for asset and inventory offiver cum gesophysicist | AO | Advert sent. Waiting for applicants. | 28th Oct | 1st Nov | Open
10 | SOP |  |  | M | Logistics arrangement to pick new printer and install it | AO | Done | 29th Oct |  | Closed
11 | OP |  |  | H | Website issues | AO | Waiting for account to balance the designer for solar house website and management to provide needed adjustment to the coastal line and ocean website | 29th Oct |  | Open
12 | SOP |  |  | M | Tundra issues | AO | In progress. Waiting for account's action | 29th Oct |  | Open
13 | SOP |  |  | M | Follow up with artisans for awarded jobs | AO | Done | 29th Oct |  | Closed
14 | SOP |  |  | H | Sudiyonno's return ticket issues | AO | Done. | 29th Oct |  | Closed
15 | SOP |  |  | M | Newspaper requisition for the month | AO | Done | 31st Oct |  | Closed
16 | SOP |  |  | M | Microwave and dispenser servicing | AO | Quotation and requisition sent to account | 31st Oct |  | Closed
17 | SOP |  |  | M | Logistics for solar marketing | AO | Done | 31st Oct |  | Closed
18 | SOP |  |  | M | Connect Togra dessigns with GMFA | AO | Done | 1st Nov |  | Closed
19 | SOP |  |  | M | Next week's expense budget for LB and Office | AO | Done | 1st Nov |  | Closed
20 | SOP |  |  | M | Transport arrangement for GMFA to abuleegaba | AO | Done | 1st Nov |  | Closed
21 | PA |  |  | H | Hotel arrangement at Bonny for personnels | AO | Done | 1st Nov |  | Closed
[9 empty] | Open: | 4
[9 empty] | Closed: | 17
| Actionees (Key): | [7 empty] | Info:
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding
|  |  |  | L | Low Finding
|  |  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 10 Closed Info

## 08-11-19
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 22
Current Date:
2019-11-08
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Abimbola Akindiilete
1 | SOP |  |  | H | Ticket renewal/opening for Matara | AO | DONE | 8th NOV |  | Closed
2 | SOP |  |  | M | VISA RENEWAL FOR MATARA | AO | IN PROGRESS | 8th NOV |  | Open
3 | SOP |  |  | M | Toll gate issue with Range rover and Tundra | AO | Done | 8th NOV |  | Closed
4 | SOP |  |  | M | Tundra issues | AO | Repair in progress | 8th NOV |  | Open
5 | SOP |  |  | M | 80KVA generator servicing | AO | Invoice and requisition sent. Waiting for account's action | 2019-11-05 |  | Open
6 | SOP |  |  | M | Christmas and end of year budgets | AO | Done and sent to GMFA | 2019-11-05 | 2019-11-07 | Closed
7 | SOP |  |  | M | Data recapturing for old staff | AO | Done. Staff whose documents are not complete has been enjoined to do that. | 2019-11-05 | 2019-11-07 | Closed
8 | SOP |  |  | H | Introduction, general induction and orientation of new staff | AO | Done | 2019-11-06 | 2019-11-07 | Closed
9 | SOP |  |  | H | Parcel for MD from PH monitoring and follow up | AO | Done and percel received | 2019-11-06 |  | Closed
10 | SOP |  |  | M | Clearance letter for Emmanuel | AO | Done | 2019-11-06 |  | Closed
11 | SOP |  |  | H | Issues with office@coastallineocean.com | AO | Case reported to GMA and GMFA | 2019-11-06 |  | Open
12 | SOP |  |  | M | Job advert for Surveyor | AO | Done. Waiting for applications. | 2019-11-07 | 8th Nov | Closed
13 | SOP |  |  | L | LB Lawma bill processing to account | AO | Done | 2019-11-07 |  | Closed
14 | SOP |  |  | M | Zenith account opening for new staff | AO | Done. Forms sent to account officer | 2019-11-07 |  | Closed
15 | SOP |  |  | M | Zenith account opening for 6 PHC staff | AO | Done. Account details received. | 2019-11-07 |  | Closed
16 | SOP |  |  | M | Spines for office files | AO | Done | 2019-11-07 |  | Closed
17 | SOP |  |  | M | Electricity bill for the month | AO | Sent to account for action | 2019-11-07 |  | Closed
18 | SOP |  |  | M | ID card processing for new staff and renewal of expired ones for old staff | AO | In progress. | 2019-11-07 | 2019-11-08 | Open
19 | SOP |  |  | H | Staff appraisals | AO | Date fixed. Notice will be sent next week | 2019-11-08 |  | Closed
20 | SOP |  |  | M | Test and Interview schedule for applicants | AO | Done | 2019-11-08 |  | Closed
21 | SOP |  |  | H | Passport and visa follow up for Satish | AO | Done | 2019-11-08 |  | Closed
22 | SOP |  |  | H | Ticket booking for Satish | AO | In progress. 3cords has been contacted | 2019-11-08 |  | Open
[9 empty] | Open: | 6
[9 empty] | Closed: | 16
| Actionees (Key): | [7 empty] | Info:
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding
|  |  |  | L | Low Finding
|  |  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 6 Closed 16 Info

## 15-11-19
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 17
Current Date:
2019-11-15
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Abimbola Akindiilete
1 | SOP |  |  | H | Visa renewal for Matara | AO | In progress | 12th NOV |  | Open
2 | SOP |  |  | H | Recruitments & DMD's instructions | AO | In progress | 12th NOV |  | Open
3 | SOP |  |  | H | CLO website | AO | In progress. | 12th NOV |  | Open
4 | SOP |  |  | H | Satish's ticket | AO | Done | 12th NOV |  | Closed
5 | SOP |  |  | M | ID card processing for new staff and renewal of expired ones for old staff | AO | Done | 2019-11-12 | 15th Nov | Closed
6 | SOP |  |  | M | Weekly office expense and budget | AO | Done | 12th Nov |  | Closed
7 | SOP |  |  | M | Staff filing | AO | In progress | 12th NOV | 15th Nov | Open
8 | SOP |  |  | H | Interview for geophycist | AO | Done | 13th Nov |  | Closed
9 | SOP |  |  | H | Logistics for Satish's arrival | AO | Done | 13th Nov |  | Closed
10 | SOP |  |  | M | Finalise price with Ejiro on CPU repair | AO | Done | 13th Nov |  | Closed
11 | SOP |  |  | H | Tundra tyre issue | AO | Tyre purchased and delivered | 13th Nov | 15th Nov | Closed
12 | SOP |  |  | M | Expat's arrival and departure dates computation | AO | Done | 13th Nov |  | Closed
13 | SOP |  |  | H | HR Software | AO | On it | 14th Nov |  | Open
14 | SOP |  |  | M | CUG renewal | AO | Budget sent to account against next week | 14th Nov |  | Open
15 | SOP |  |  | M | LB needs and preparation for visitors | AO | Sorted | 14th Nov | 15th Nov | Closed
16 | SOP |  |  | M | HMO issue with Ufuoma | AO | On it | 15th Nov |  | Open
17 | SOP |  |  | H | Visa renewal for 4 expats | AO | In progress | 15th Nov |  | Open
[9 empty] | Open: | 8
[9 empty] | Closed: | 9
| Actionees (Key): | [7 empty] | Info:
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding
|  |  |  | L | Low Finding
|  |  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 8 Closed 9 Info

## 22-11-19
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 26
Current Date:
2019-11-22
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Abimbola Akindiilete
1 | SOP |  |  | H | MD's instruction on Bakare Olubunmi | AO | First stage of interview concluded. Second stage will be a zoom interview with GMO, before the last stage with MD and DMD | 18th Nov |  | Open
2 | SOP |  |  | H | Follow up with plumbing issues | AO | Done | 18th Nov |  | Closed
3 | SOP |  |  | H | Follow up with visa renewal for matara | AO | Done. Passport sent back to PHC | 18th Nov |  | Closed
4 | SOP |  |  | H | Test and interviews | AO | Done for the week | 18th Nov | 22nd Nov | Closed
5 | SOP |  |  | M | Bersh warehouse lighting and fixing of door | AO | Lighting done, quoatation for door repair sent to account for action | 18th Nov | 19th Nov | Closed
6 | SOP |  |  | M | Follow up HMO issue with Ufuoma | AO | Done. Her name finally registered with Imperial Hospital. Working on her refund | 18th Nov | 20th Nov | Closed
7 | SOP |  |  | M | Sending out application form to all applicants | AO | Done | 19th Nov |  | Closed
8 | SOP |  |  | H | Staff appraisal | AO | Sent to all staff | 19th Nov |  | Closed
9 | SOP |  |  | H | Sunkanmi's leave processing and approval | AO | Done | 19th Nov |  | Closed
10 | SOP |  |  | M | MD's office leakage | AO | Done | 19th Nov | 20th Nov | Closed
11 | SOP |  |  | H | Affidavit for NSITF | AO | In progress. | 19th Nov | 22nd Nov | Open
12 | SOP |  |  | M | Job completion forms for the week | AO | Done | 19th Nov |  | Closed
13 | SOP |  |  | H | CUG renewal | AO | Done | 19th Nov |  | Closed
14 | SOP |  |  | M | Mail error issue | AO | In progress | 20th Nov |  | Open
15 | SOP |  |  | M | Security rest room issue | AO | Done | 20th Nov |  | Closed
16 | SOP |  |  | M | Travelling arrangement for Bersh | AO | On it | 20th Nov |  | Open
17 | SOP |  |  | H | Khairat HMO card | AO | Done | 20th Nov |  | Closed
18 | SOP |  |  | M | Salary advance for staff | AO | Done | 20th Nov |  | Closed
19 | SOP |  |  | M | Staff's Palpension certificate of registration | AO | Done | 21st Nov |  | Closed
20 | SOP |  |  | M | Issue with CLO website | AO | Errors sent to Dairo Ibukunoluwa for correction | 21st Nov |  | Closed
21 | SOP |  |  | H | Collection and sending Matara's passport to PHC | AO | Done | 21st Nov |  | Closed
22 | SOP |  |  | M | Picanto issues | AO | Spare tyre fixed, request for engine oil sent to account for action | 21st Nov |  | Closed
23 | SOP |  |  | M | DMD's instructions on Diva's bags | AO | Bags sorted and distributed to groups ready for pick ups | 21st Nov | 22nd Nov | Closed
24 | SOP |  |  | M | Local flight bookinf for Satish, Dante and Demola | AO | Done | 21st Nov |  | Closed
25 | SOP |  |  | M | Requisitions for pending issues | AO | Sent to account for action | 22nd Nov |  | Closed
26 | PA |  |  | M | Neccesary Admin preparations for Amni Okoro project | AO | In progress | 22nd Nov |  | Closed
[9 empty] | Open: | 4
[9 empty] | Closed: | 22
| Actionees (Key): | [7 empty] | Info:
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding
|  |  |  | L | Low Finding
|  |  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 4 Closed 22 Info

## 29-11-19
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 23
Current Date:
2019-11-29
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Abimbola Akindiilete
1 | SOP |  |  | H | Sudiyonno's ticket rescheduling | AO | Done | 25th Nov |  | Closed
2 | SOP |  |  | H | Dustbin issue | AO | Resolved | 25th Nov | 26th Nov | Closed
3 | SOP |  |  | H | Affidavit for NSITF and CUG | AO | In progress | 25th Nov |  | Open
4 | SOP |  |  | H | Staff filing | AO | Done | 25th Nov | 28th Nov | Closed
5 | SOP |  |  | M | December's stationeries and toiletries | AO | Sent to account for action | 25th Nov |  | Closed
6 | SOP |  |  | M | Application form to applicants for HSE and Legal Compliance officer | AO | Done | 25th Nov |  | Closed
7 | SOP |  |  | M | Surveyor trainee zoom interview | AO | Done | 25th Nov | 26th Nov | Closed
8 | SOP |  |  | H | Gutter issue | AO | Sorted | 25th Nov | 28th Nov | Closed
9 | SOP |  |  | H | Job completion form for fumiagtion | AO | Done | 25th Nov |  | Closed
10 | SOP |  |  | M | Generator issues | AO | On it | 25th Nov | 29th Nov | Closed
11 | SOP |  |  | H | DMD's assignment for the Divas | AO | Done | 26th Nov | 28th Nov | Closed
12 | SOP |  |  | M | Corrections and getting approval for affidavits | AO | Done | 26th Nov |  | Closed
13 | PA |  |  | H | TWP follow up | AO | On it | 27th Nov | 29th Nov | Open
14 | SOP |  |  | M | HSE interview | AO | In progress | 27th Nov |  | Open
15 | SOP |  |  | M | Carpenter for 2nd floor rest room | AO | Quotation sent to account for action | 27th Nov |  | Closed
16 | SOP |  |  | M | Schedule zoom final interview | AO | Done. Interview reschedule for Monday | 27th Nov | 28th Nov | Closed
17 | SOP |  |  | H | Interview for Toluwalope | AO | Done | 28th Nov |  | Closed
18 | SOP |  |  | M | Process business card for GMFA and I | AO | On it | 28th Nov |  | Open
19 | SOP |  |  | M | Attendance tracker | AO | Done | 28th Nov |  | Closed
20 | SOP |  |  | M | Paul LB health issue | AO | Solved | 28th Nov |  | Closed
21 | SOP |  |  | H | HMO refund for Ufuoma | AO | On it | 28th Nov |  | Open
22 | SOP |  |  | M | Mopol LB issue with attendance | AO | On it | 29th Nov |  | Open
23 | SOP |  |  | M | Hotel booking for return of personnel on Amni Okro | AO | Done | 29th Nov |  | Closed
[9 empty] | Open: | 6
[9 empty] | Closed: | 17
| Actionees (Key): | [7 empty] | Info:
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding
|  |  |  | L | Low Finding
|  |  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 6 Closed 17 Info

## 06-12-19
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 23
Current Date:
2019-12-06
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Abimbola Akindiilete
1 | SOP |  |  | H | Generator issues | AO | In progress | 2nd Dec |  | Open
2 | SOP |  |  | H | Follow up with TWP and visa renewal | AO | In progress | 2nd Dec | 6th Dec | Open
3 | SOP |  |  | H | Tfare reimbursement for personel | AO | Done | 2nd Dec |  | Closed
4 | SOP |  |  | H | CLO website necessary adjustments follow up | AO | Done | 2nd Dec |  | Closed
5 | SOP |  |  | M | Zoom interview rescheduling for final recruitment stage | AO | Done | 2nd Dec |  | Closed
6 | SOP |  |  | M | Offer and contract letter drafting for new employees | AO | Done | 3rd Dec | 6th Dec | Closed
7 | SOP |  |  | M | HMO refund for Ufuoma | AO | Done | 3rd Dec |  | Closed
8 | SOP |  |  | H | CUG issues | AO | In progress | 3rd Dec |  | Open
9 | SOP |  |  | H | Attendance tracker | AO | Done | 3rd Dec |  | Closed
10 | SOP |  |  | M | Prakash and Matara's PHC to LOS flight | AO | Done | 4th Dec |  | Closed
11 | SOP |  |  | H | Prakash ticket rescheduling | AO | Done | 4th Dec |  | Closed
12 | SOP |  |  | M | Logistics and welfare for Prakash and Matara's travelling | AO | Done | 4th Dec |  | Closed
13 | PA |  |  | H | Personnel's feeding allowance and ticket refund | AO | Done | 4th Dec |  | Closed
14 | SOP |  |  | M | New staff introduction | AO | Done | 4th Dec |  | Closed
15 | SOP |  |  | M | Mike's TWP extension | AO | In progress | 4th Dec |  | Open
16 | SOP |  |  | M | NYSC clearance for corpers | AO | Done | 4th Dec |  | Closed
17 | SOP |  |  | H | 3 passports for visa extension transfer back to PHC | AO | Done | 5th Dec |  | Closed
18 | SOP |  |  | M | LB needs | AO | Done | 6th Dec |  | Closed
19 | SOP |  |  | M | PC for new geophysicists | AO | On it | 6th Dec |  | Open
20 | SOP |  |  | M | Slab for fornt office | AO | On it | 6th Dec |  | Open
21 | SOP |  |  | H | System for biometrics | AO | Done | 6th Dec |  | Closed
22 | SOP |  |  | M | Sudioyonno's flight | AO | Done | 6th Dec |  | Closed
23 | SOP |  |  | M | Business card contarct to Togra | AO | Done | 6th Dec |  | Closed
[9 empty] | Open: | 6
[9 empty] | Closed: | 17
| Actionees (Key): | [7 empty] | Info:
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding
|  |  |  | L | Low Finding
|  |  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 6 Closed 17 Info

## 13-12-19
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 16
Current Date:
2019-12-13
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Abimbola Akindiilete
1 | SOP |  |  | H | Induction for new staff | AO | Done | 9th Dec |  | Closed
2 | SOP |  |  | H | LB and Office dustbin bill | AO | Paid | 9th Dec |  | Closed
3 | SOP |  |  | H | Interview schedule for legal complaince officer | AO | Done | 9th Dec |  | Closed
4 | SOP |  |  | H | New staff introduction | AO | Done | 9th Dec |  | Closed
5 | SOP |  |  | M | Recruiments (coper, Toluwalope, Legal&training school, HSE) | AO | awaiting go-ahead | 10th Dec |  | Open
6 | SOP |  |  | M | Parmesh ticket booking | AO | awaiting go-ahead from GMO | 10th Dec |  | Open
7 | SOP |  |  | M | Query letter and issuing to Felix | AO | Done | 10th Dec |  | Closed
8 | SOP |  |  | H | Interview | AO | Done | 11th Dec |  | Closed
9 | SOP |  |  | H | Exhaust pipe for 80 KVA | AO | On it | 11th Dec |  | Open
10 | SOP |  |  | M | LOS security rest room issues | AO | On it | 11th Dec |  | Open
11 | SOP |  |  | H | Travelling issues with Hassan and Paul | AO | On it | 12th Dec |  | Open
12 | SOP |  |  | M | Ticket booking and logistics for Obioma and Ozegbe | AO | Done | 12th Dec |  | Closed
13 | SOP |  |  | H | Get MIKANO Engineer to check the 2 generators | AO | Done | 12th Dec |  | Closed
14 | SOP |  |  | M | Tundra repair | AO | Requisition sent to account for action | 12th Dec |  | Closed
15 | SOP |  |  | M | Logistics to send security boot from PHC | AO | In place | 12th Dec |  | Closed
16 | SOP |  |  | M | ID card for new staff | AO | Done | 13th Dec |  | Closed
[9 empty] | Open: | 5
[9 empty] | Closed: | 11
| Actionees (Key): | [7 empty] | Info:
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding
|  |  |  | L | Low Finding
|  |  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 5 Closed 11 Info

## 20-12-19
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 22
Current Date:
2019-12-20
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Abimbola Akindiilete
1 | SOP |  |  | H | Affidavit for NSITF and CUG | AO | On it | 16th Dec |  | Open
2 | SOP |  |  | H | LB Battery | AO | Purchased | 16th Dec |  | Closed
3 | SOP |  |  | H | Business card delivery | AO | Done | 16th Dec |  | Closed
4 | SOP |  |  | H | MD's office leakage | AO | Done | 16th Dec |  | Closed
5 | SOP |  |  | M | GMA's birthday notification | AO | Done | 16th Dec |  | Closed
6 | PA |  |  | H | Flight booking for Evanthia | AO | Done | 17th Dec | 20th Dec | Closed
7 | SOP |  |  | M | New invoice sheet for account | AO | Quoatation sent to account for action | 17th Dec |  | Closed
8 | SOP |  |  | H | Logistics for staff presence at the Oyediran's burial ceremoney | AO | Done | 18th Dec | 20th Dec | Closed
9 | SOP |  |  | H | Salary details for December | AO | Done | 18th Dec |  | Closed
10 | SOP |  |  | M | Toiletries and stationeries for January 2020 | AO | Sent to account | 18th Dec |  | Closed
11 | SOP |  |  | H | CUG renewal | AO | Done | 18th Dec |  | Closed
12 | SOP |  |  | M | Servicing of ford | AO | Done | 18th Dec |  | Closed
13 | PA |  |  | H | Logistics for POP cement purchase | AO | Done | 18th Dec |  | Closed
14 | SOP |  |  | M | Christmas takeaway for staff | AO | Purchased and shared | 19th Dec | 20th Dec | Closed
15 | SOP |  |  | M | Arrange Christmas treats for staff and office decoration | GMFA/AO | Done | 19th Dec | 20th Dec | Closed
16 | SOP |  |  | M | Airtel office | AO | Done | 19th Dec |  | Closed
17 | SOP |  |  | H | Appraisal collation and submission | AO | Done | 19th Dec | 20th Dec | Closed
18 | SOP |  |  | M | Attendee HRM | AO | Continous action | 19th Dec |  | Closed
19 | SOP |  |  | M | End of the year report notification | AO | Sent | 19th Dec |  | Closed
20 | SOP |  |  | M | Christian's birthday notification | AO | Sent | 20th Dec |  | Closed
21 | SOP |  |  | H | LOS to PHC flight and logistics for Evanthia | AO | Done | 20th Dec |  | Closed
22 | SOP |  |  | H | Tax identification number for staff | AO | On it | 20th Dec |  | Open
[9 empty] | Open: | 2
[9 empty] | Closed: | 20
| Actionees (Key): | [7 empty] | Info:
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding
|  |  |  | L | Low Finding
|  |  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 2 Closed 20 Info

## 24-12-19
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 11
Current Date:
2019-12-24
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Abimbola Akindiilete
1 | SOP |  |  | H | Christmas gifts for clients | AO | Done | 23rd Dec |  | Closed
2 | SOP |  |  | H | Work on the completion of all jobs given to clients | AO | Done | 23rd Dec |  | Closed
3 | SOP |  |  | H | Lunch meal purchased for all staff for Christmas treat | AO | Done | 23rd Dec |  | Closed
4 | SOP |  |  | M | Logistics for movies for all staff | AO | Done | 23rd Dec |  | Closed
5 | SOP |  |  | M | Refund movie payment | AO | Done | 23rd Dec |  | Closed
6 | SOP |  |  | H | LB needs for the rest of the year | AO | Done | 23rd Dec |  | Closed
7 | SOP |  |  | M | Airtel head office for CUG issue | AO | Done | 24th Dec |  | Closed
8 | SOP |  |  | H | DMD's POP supervision and conclusion | AO | Done | 24th Dec |  | Closed
9 | SOP |  |  | H | LB security window follow up | AO | Done | 24th Dec |  | Closed
10 | SOP |  |  | H | Pumping machine issue | AO | Solved | 24th Dec |  | Closed
11 | SOP |  |  | H | LB generator issue | AO | Solved | 24th Dec |  | Closed
[9 empty] | Open: | 0
[9 empty] | Closed: | 11
| Actionees (Key): | [7 empty] | Info:
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding
|  |  |  | L | Low Finding
|  |  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 0 Closed 11 Info