## 20-03-2020
|  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 10
|  |  | ACT/BGS/MGT/20032020/WK3 |  | Current Date: |  | 20-03-2020
Item No | Issue | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Abimbola Akindiilete
1 |  | H | Submission of Proforma invoice for Operational cost | GMFA | Submitted on the 10th Of March | 10th March |  | Closed
2 |  | H | Mob/Demob proforma Invoice | GMFA | Submitted on the 16th of March. Invoice is undergoing payment approvals. | 26th March |  | Open
3 |  | H | Idmenity for Disputed Operational cost and reimbursables | GMFA | Mrs. Egunjobi said we should try and pay TTS and PAM so that the 100% amount will be on the ideminity | 26th March |  | Open
4 |  | H | Pay slip for the Month of February for Staff | GMFA | it has been prepared and given to all staff | 2nd March |  | Closed
5 |  | H | Audited Accounts | GMFA | We have prepared the accounts and sent to the DMD | 26th March |  | Open
6 |  | H | Budget | GMFA | Working on the propsed budget for next week | 26th March |  | Open
7 |  | H | Admin Training | GMFA | I presented the slides last week, Ufuoma will present her slide next month | 26th March |  | Open
8 |  | H | Tinted glass for MD's Car | GMFA | The permit has not been aaproved yet. Once it is approved, we will go and pick it up | 26th March |  | Open
9 |  | H | Monthly progess Report(WAV) | GMFA | I have sent the singed copy to Mobil | 19th March |  | Closed
10 |  | H | Purchase/ delivery of Tide Guages | GMFA | Payment was made last week Friday but we do not have an update on the delivery yet | 23rd March |  | Open
[7 empty] | Open: | 7
[7 empty] | Closed: | 3
| Actionees (Key): | [5 empty] | Info:
|  | H | High Finding
|  | M | Medium Finding
|  | L | Low Finding
|  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on I4: Statuses are: Open 10 Closed 13 Info