## Sheet1
|  |  |  | TECHNICAL OPERATIONS - ACTION TRACKER |  |  |  |  | Total actions: | 1
[7 empty] | Current Date: 20/03/2020 |  | 20.03.2020
Last updated on: 20/03/2020
Item No | Issue | Ref | Section/Page | Priority | What | Action Party | Update | By When | Days to Close | Status
1 | MS |  | PM | H | MPN Oyot Reporting | GMO/DP | Submitted draft seabed clearance report. Coordinating seismic data processing and interpretation with RDI and GEMS | 2020-03-27 | 5 | Open
2 |  |  | PM | H | MPN Oyot Deliverables | GMO/DP/QC | Data compilation for survey deliverables in progressing. Generated deliverables checklist | 2020-03-27 | 5 | Open
3 |  |  | PM | H | Amni Ima Tender | GMO/QC Geo | Prepared technical and commercial submissions | 2020-03-18 |  | Closed
4 | MS |  | OPS | H | Repair of MBES, Sector scan sonar, USBL and Seaspy magnetometer | GMO/LPC | Following up with LPC for timely action | 2020-04-03 |  | Open
5 | MS |  | PM | H | WAV J39 offhire fuel reconciliation and vessel downtime | GMO | Prepared claims report along with evidences for Admni Unit to action | 2020-03-16 |  | Closed
6 | MS |  | PM | H | Project planning for Amni tidal measurement | GMO/QC Geo | Equipment, vessel and freelance personnel sourcing, interfacing with client | 2020-03-27 |  | Open
7 | MS |  | OPS | M | Oyot survey project debrief | GMO/QC Geo | Coordinated debrief of Oyot project and involved expatriate part chief in online meeting | 2020-03-12 |  | Closed
|  |  | PM | H | Technical response to MPN on submitted Oyot seabed clearance report | GMO/DP | Providing requested clarifications on report content and charts | 2020-03-20 |  | Closed
|  |  | PM | H | Oyot survey project close out meeting | GMO | Prepared slide presentation and presented same at the meeting | 2020-03-20 |  | Closed
|  |  | OPS | M | Drydocking of Brone Explorer | GMO | Sourcing for shipyard and engaging with INSB Class | 2020-04-03 |  | Open
|  |  | OPS | M | Commercial quotes reconciliation with Amni Procurement | GMO | Provide necessary defence for submitted quotes for tidal measurement and survey works | 2020-03-16 |  | Closed
8 | MS |  | OPS | H | TTS invoicing | GMO | Engaged TTS on reason for delay in invoice settlement | 2020-02-11 |  | Open
| Actionees (Key): | [7 empty] | Open | 6
[9 empty] | Closed: | 6
Info:
|  | Priority Key: |  | H | High Finding |  | GMO: Adebisi Adenuga
|  |  |  | M | Medium Finding |  | HR.: Bimbo Akindielete
|  |  |  | L | Low Finding |  | Logistics Cordinator: Dotun Coker
|  |  |  | Info | Information |  | GMFA: Busola Adekanmbi
Note on K4: Statuses are: Open Closed Info