## Sheet1
|  |  |  | BRONE POSITIONING+SURVEY LTD - DAILY LOG |  |  |  |  | Total actions: | 5
Current Date:
2020-03-23
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update | By When | Days to Close | Status
NAME
1 | PA |  |  | M | GENERATE PROJECT COST ESTIMATE FOR AMNI TIDAL MEASUREMENT JOB | GMFA |  | 23RD MAR |  | Closed
2 | PA |  |  | H | WORK ON TOTAL TENDER | GMO |  | 2ND APR |  | Open
3 | MS |  |  | H | WORK WITH TOBI ON THE REMAINING MOBIL DELIVERABLES | DCAA |  | 27TH MAR |  | Open
[9 empty] | Open: | 4
[9 empty] | Closed: | 1
| Actionees (Key): | [7 empty] | Info:
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding
|  |  |  | L | Low Finding
|  |  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 3 Closed 7 nfo