## 09-01-2020
2018-02-22 |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 9
[5 empty] | Current Date: |  | 2020-01-09
Last updated on: 29-11-19
Item No | Issue | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Action Tracker
1 | SOP | H | Budget for the new week | ACCOUNTS | Budget and cash flow for the new week was sent for approval | 2020-01-10 |  | Closed
2 | SOP | M | Ticket refund from Arik and Aero | Accounts/OA | In progress; awaiting refund | 2020-01-09 |  | Open
3 | SOP | M | BRONE and BESRH : TCC | Accounts/GMA | pending when audited account Is ready | 2020-01-09 |  | Open
4 | SOP | H | Invoice Follow up; | Accounts | Folowing up on Amni invoices. Still waiting for feedback from Ftsolutions | 2020-01-09 |  | Open
5 | SOP | H | BERSH AUDITED accounts 2019 | Accounts/BERSH | In progress; documents are been prepared | 2020-01-09 |  | Open
6 | SOP | M | Exxo mobile requisitions | Accounts/ GMO/GMA | contractors invoices update and reconcilation and other requisitions | 2020-01-09 |  | Open
7 | SOP | M | Refund claim on faulty USBL; Subsea STR | Accounts | credit note has been received | 2020-01-09 |  | Closed
8 | SOP | M | AMNI- VAT and WHT | Accounts | Feedback to get all evidence on FIRS platform online | 2020-01-09 |  | Closed
9 | SOP | H | Invoice Issuing; | Accounts/PCO/GMA | SEWOP- Logs have been received, awaiting contract for details. Positioning and Seabed Survey at Ima / Langley - Contract has been received. Awaiting signed logs | 2020-01-09 |  | Open
[7 empty] | Open: | 6
[7 empty] | Closed: | 3
| Actionees (Key): | [5 empty] | Info: | 0
|  | H | High Finding
|  | M | Medium Finding
|  | L | Low Finding
|  | Info | Information
900
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on I4: Statuses are: Open Closed Info

## 16-01-2020
2018-02-22 |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 8
[5 empty] | Current Date: |  | 2020-01-16
Last updated on: 09-01-2020
Item No | Issue | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Action Tracker
1 | SOP | H | Budget for the new week | ACCOUNTS | Budget and cash flow for the new week was sent for approval | 2020-01-17 |  | Closed
2 | SOP | M | Ticket refund from Arik and Aero | Accounts/OA | In progress; awaiting refundfrom Arik; Aero has made refund | 2020-01-13 |  | Open
3 | SOP | M | BRONE and BESRH : TCC | Accounts/GMA | pending when audited account Is ready | 2020-01-13 |  | Open
4 | SOP | H | Invoice Follow up; | Accounts | Folowing up on Amni invoices. Still waiting for feedback from Ftsolutions | 2020-01-13 |  | Open
5 | SOP | H | BERSH AUDITED accounts 2019 | Accounts/BERSH | In progress; documents are been prepared | 2020-01-13 |  | Open
6 | SOP | M | Exxo mobile requisitions | Accounts/ GMO/GMA | contractors invoices update and reconcilation and other requisitions | 2020-01-13 |  | Open
7 | SOP | M | VAT For BERSH | Accounts | Payment as been made and filling is in progress | 2020-01-16 |  | Open
8 | SOP | H | Invoice Issuing; | Accounts/PCO/GMA | Tubu Bathymetry - Awaiting approval to issue Positioning and Seabed Survey at Ima / Langley - Awaiting reviewed Contract to revise invoice. | 2020-01-13 |  | Open
[7 empty] | Open: | 7
[7 empty] | Closed: | 1
| Actionees (Key): | [5 empty] | Info: | 0
|  | H | High Finding
|  | M | Medium Finding
|  | L | Low Finding
|  | Info | Information
900
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on I4: Statuses are: Open Closed Info

## 23-01-2020
2018-02-22 |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 8
[5 empty] | Current Date: |  | 2020-01-23
Last updated on: 16-01-2020
Item No | Issue | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Action Tracker
1 | SOP | H | Budget for the new week | ACCOUNTS | Budget and cash flow for the new week was sent for approval | 2020-01-24 |  | Closed
2 | SOP | M | Ticket refund from Arik | Accounts/OA | In progress; awaiting refundfrom Arik; | 2020-01-20 |  | Open
3 | SOP | M | BRONE and BESRH : TCC | Accounts/GMA | pending when audited account Is ready | 2020-01-20 |  | Open
4 | SOP | H | Invoice Follow up; | Accounts | Folowing up on Amni invoices. Still waiting for feedback from Ftsolutions | 2020-01-20 |  | Open
5 | SOP | H | BERSH AUDITED accounts 2019 | Accounts/BERSH | In progress; documents are been prepared | 2020-01-20 |  | Open
6 | SOP | M | Exxo mobile requisitions | Accounts/ GMO/GMA | contractors invoices update and reconcilation and other requisitions | 2020-01-20 |  | Open
7 | SOP | M | VAT For BERSH | Accounts | filling has been done | 2020-01-20 |  | Closed
8 | SOP | H | Invoice Issuing; | Accounts/PCO/GMA | Tubu Bathymetry - Awaiting approval to issue | 2020-01-20 |  | Open
[7 empty] | Open: | 6
[7 empty] | Closed: | 2
| Actionees (Key): | [5 empty] | Info: | 0
|  | H | High Finding
|  | M | Medium Finding
|  | L | Low Finding
|  | Info | Information
900
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on I4: Statuses are: Open Closed Info

## 30-01-2020
2018-02-22 |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 7
[5 empty] | Current Date: |  | 2020-01-31
Last updated on: 23-01-2020
Item No | Issue | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Action Tracker
1 | SOP | H | Budget for the new week | ACCOUNTS | Budget and cash flow for the new week was sent for approval | 2020-01-31 |  | Closed
2 | SOP | M | Ticket refund from Arik | Accounts/OA | In progress; awaiting refundfrom Arik on 1st week feb 2020 | 2020-01-28 |  | Open
3 | SOP | M | BRONE and BESRH : TCC | Accounts/GMA | pending when audited account Is ready | 2020-01-27 |  | Open
4 | SOP | H | Invoice Follow up; | Accounts | Folowing up on Amni invoices. Still waiting for feedback from Ftsolutions | 2020-01-27 |  | Open
5 | SOP | H | BERSH AUDITED accounts 2019 | Accounts/BERSH | In progress; documents are been prepared | 2020-01-27 |  | Open
6 | SOP | M | Exxo mobile requisitions | Accounts/ GMO/GMA | project completed | 2020-01-27 |  | Closed
7 | SOP | H | Invoice Issuing; | Accounts/PCO/GMA | Tubu Bathymetry - Awaiting approval to issue | 2020-01-27 |  | Open
[7 empty] | Open: | 5
[7 empty] | Closed: | 2
| Actionees (Key): | [5 empty] | Info: | 0
|  | H | High Finding
|  | M | Medium Finding
|  | L | Low Finding
|  | Info | Information
900
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on I4: Statuses are: Open Closed Info

## 07-02-2020
2018-02-22 |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 6
[5 empty] | Current Date: |  | 2020-02-07
Last updated on: 31-01-2020
Item No | Issue | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Action Tracker
1 | SOP | H | Budget for the new week | ACCOUNTS | Budget and cash flow for the new week was sent for approval | 2020-02-07 |  | Closed
2 | SOP | M | Ticket refund from Arik | Accounts/OA | In progress; awaiting refundfrom Arik on 1st week feb 2020 | 2020-02-03 |  | Open
3 | SOP | M | BRONE and BESRH : TCC | Accounts/GMA | pending when audited account Is ready | 2020-02-03 |  | Open
4 | SOP | H | Invoice Follow up; | Accounts | Folowing up on Amni invoices. Still waiting for feedback from Ftsolutions | 2020-02-03 |  | Open
5 | SOP | H | BERSH AUDITED accounts 2019 | Accounts/BERSH | In progress; documents are been prepared | 2020-02-03 |  | Open
6 | SOP | H | Invoice Issuing; | Accounts/PCO/GMA | Tubu Bathymetry - approved and issued | 2020-02-06 |  | Closed
[7 empty] | Open: | 4
[7 empty] | Closed: | 2
| Actionees (Key): | [5 empty] | Info: | 0
|  | H | High Finding
|  | M | Medium Finding
|  | L | Low Finding
|  | Info | Information
900
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on I4: Statuses are: Open Closed Info

## 14-02-2020
2018-02-22 |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 5
[5 empty] | Current Date: |  | 2020-02-14
Last updated on: 07-02-2020
Item No | Issue | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Action Tracker
1 | SOP | H | Budget for the new week | ACCOUNTS | Budget and cash flow for the new week was sent for approval | 2020-02-14 |  | Closed
2 | SOP | M | Ticket refund from Arik | Accounts/OA | In progress; awaiting refund for Azman flight, obioma refund has been made; | 2020-02-10 |  | Open
3 | SOP | M | BRONE and BESRH : TCC | Accounts/GMA | pending when audited account Is ready | 2020-02-10 |  | Open
4 | SOP | H | Invoice Follow up; | Accounts | Folowing up on Amni invoices. Still waiting for feedback from Ftsolutions | 2020-02-10 |  | Open
5 | SOP | H | BERSH AUDITED accounts 2019 | Accounts/BERSH | In progress; documents are been prepared | 2020-02-10 |  | Open
7 | SOP | M | VAT For BERSH | Accounts | payment has been done, remaining filling | 2020-02-10 |  | Open
[7 empty] | Open: | 6
[7 empty] | Closed: | 2
| Actionees (Key): | [5 empty] | Info: | 0
|  | H | High Finding
|  | M | Medium Finding
|  | L | Low Finding
|  | Info | Information
900
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on I4: Statuses are: Open Closed Info

## 21-02-2020
2018-02-22 |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 6
[5 empty] | Current Date: |  | 2020-02-21
Last updated on: 14-02-2020
Item No | Issue | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Action Tracker
1 | SOP | H | Budget for the new week | ACCOUNTS | Budget and cash flow for the new week was sent for approval | 21/02/2020 |  | Closed
2 | SOP | M | Ticket refund from Arik | Accounts/OA | In progress; awaiting refund for Azman flight | 17/02/2020 |  | Open
3 | SOP | M | BRONE and BESRH : TCC | Accounts/GMA | pending when audited account Is ready | 17/02/2020 |  | Open
4 | SOP | H | Invoice Follow up; | Accounts | Folowing up on Amni invoices. Still waiting for feedback from Ftsolutions | 17/02/2020 |  | Open
5 | SOP | H | BERSH AUDITED accounts 2019 | Accounts/BERSH | In progress; documents have been prepared and sent for review | 21/02/2020 |  | Open
7 | SOP | M | VAT For BERSH | Accounts | filling has been done | 17/02/2020 |  | Closed
[7 empty] | Open: | 4
[7 empty] | Closed: | 2
| Actionees (Key): | [5 empty] | Info: | 0
|  | H | High Finding
|  | M | Medium Finding
|  | L | Low Finding
|  | Info | Information
900
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on I4: Statuses are: Open Closed Info

## 06-03-2020
2018-02-22 |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 1
[5 empty] | Current Date: |  | 2020-06-03
Last updated on: 21-02-2020
Item No | Issue | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Action Tracker
1 | SOP | H | Budget for the new week | ACCOUNTS | Budget and cash flow for the new week was sent for approval | 2020-03-06 |  | Closed
2 | SOP | M | Ticket refund from Arik | Accounts/OA | In progress; awaiting refund for Azman flight | 2020-03-06 |  | Open
3 | SOP | M | BRONE and BESRH : TCC | Accounts/GMA | pending when audited account Is ready | 2020-03-06 |  | Open
4 | SOP | H | Invoice Follow up; | Accounts | Folowing up on Amni invoices. Still waiting for feedback from Ftsolutions | 2020-03-06 |  | Open
5 | SOP | H | BERSH AUDITED accounts 2019 | Accounts/BERSH | In progress; documents have been prepared and sent for review | 2020-03-06 |  | Open
[7 empty] | Open: | 4
[7 empty] | Closed: | 1
| Actionees (Key): | [5 empty] | Info: | 0
|  | H | High Finding
|  | M | Medium Finding
|  | L | Low Finding
|  | Info | Information
900
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on I4: Statuses are: Open Closed Info

## 13-03-2020
2018-02-22 |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 1
[5 empty] | Current Date: |  | 13/3/2020
Last updated on: 06-03-2020
Item No | Issue | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Action Tracker
1 | SOP | H | Budget for the new week | ACCOUNTS | Budget and cash flow for the new week was sent for approval | 2020-03-13 |  | Closed
2 | SOP | M | Ticket refund from Arik | Accounts/OA | In progress; awaiting refund for Azman flight | 2020-03-13 |  | Open
3 | SOP | M | BRONE and BESRH : TCC | Accounts/GMA | pending when audited account Is ready | 2020-03-13 |  | Open
4 | SOP | H | Invoice Follow up; | Accounts | Folowing up on Amni invoices. Still waiting for feedback from Ftsolutions | 2020-03-13 |  | Open
5 | SOP | H | BERSH AUDITED accounts 2019 | Accounts/BERSH | In progress; documents have been prepared and sent for review | 2020-03-13 |  | Open
[7 empty] | Open: | 4
[7 empty] | Closed: | 1
| Actionees (Key): | [5 empty] | Info: | 0
|  | H | High Finding
|  | M | Medium Finding
|  | L | Low Finding
|  | Info | Information
900
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on I4: Statuses are: Open Closed Info

## 20-03-2020
2018-02-22 |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 6
[5 empty] | Current Date: |  | 20/3/2020
Last updated on: 13-03-2020
Item No | Issue | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Action Tracker
1 | SOP | H | Budget for the new week | ACCOUNTS | Budget and cash flow for the new week was sent for approval | 2020-03-20 |  | Closed
2 | SOP | M | Ticket refund from Arik | Accounts/OA | In progress; awaiting refund for Azman flight | 2020-03-20 |  | Open
3 | SOP | M | BRONE and BESRH : TCC | Accounts/GMA | pending when audited account Is ready | 2020-03-20 |  | Open
4 | SOP | H | Invoice Follow up; | Accounts | Folowing up on Amni invoices. Still waiting for feedback from Ftsolutions | 2020-03-20 |  | Open
5 | SOP | M | VAT For BERSH | Accounts | payment and filling has been done | 2020-03-20 |  | Closed
6 | SOP | H | BERSH AUDITED accounts 2019 | Accounts/BERSH | In progress; documents have been prepared and sent for review | 2020-03-20 |  | Open
[7 empty] | Open: | 4
[7 empty] | Closed: | 2
| Actionees (Key): | [5 empty] | Info: | 0
|  | H | High Finding
|  | M | Medium Finding
|  | L | Low Finding
|  | Info | Information
900
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on I4: Statuses are: Open Closed Info

## 27-03-2020
2018-02-22 |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 6
[5 empty] | Current Date: |  | 20/3/2020
Last updated on: 13-03-2020
Item No | Issue | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Action Tracker
1 | SOP | H | Budget for the new week | ACCOUNTS | Budget and cash flow for the new week was sent for approval | 2020-03-20 |  | Closed
2 | SOP | M | Ticket refund from Arik | Accounts/OA | In progress; awaiting refund for Azman flight | 2020-03-20 |  | Open
3 | SOP | M | BRONE and BESRH : TCC | Accounts/GMA | pending when audited account Is ready | 2020-03-20 |  | Open
4 | SOP | H | Invoice Follow up; | Accounts | Folowing up on Amni invoices. Still waiting for feedback from Ftsolutions | 2020-03-20 |  | Open
5 | SOP | M | VAT For BERSH | Accounts | payment and filling has been done | 2020-03-20 |  | Closed
6 | SOP | H | BERSH AUDITED accounts 2019 | Accounts/BERSH | In progress; documents have been prepared and sent for review | 2020-03-20 |  | Open
[7 empty] | Open: | 4
[7 empty] | Closed: | 2
| Actionees (Key): | [5 empty] | Info: | 0
|  | H | High Finding
|  | M | Medium Finding
|  | L | Low Finding
|  | Info | Information
900
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on I4: Statuses are: Open Closed Info

## info
Issues | Disciplines
1 HQ | HSE/Quality
2 PA | Project admin
3 DS | Diving System
4 DP | Dynamic Positioning
5 MS | Marine Systems
6 CL | Craneage & Lifting
7
8
9 CS | Cost & schedule
Features of "Action tracker"
Cell J1 contains a "running total" of the number of actions - retrieved from the last "Ref no" entered in column B - so each time a new action is added, give it the next Ref no.
Cell A4 contains a comment which is input manually to reflect the issue headings that the actions relate to - the comment should reflect the issues (and their abbreviations) entered on this sheet
Column A uses "data validation" to present a dropdown list of the "issues" from "Sheet2"
Column C uses conditional formatting to color the cell grren if "L" is entered, amber if "M" is entered and red if "H" is entered - the cell does not change color if nothing is entered so priority color coding is optional.
By entering a date in column H and "Open" in column J, the number of days to close the action is displayed in column I. Entering "Closed" or "Info" in column J sets column I to "-".
Cells at bottom right of table calculate number of "Open", "Closed" and "Info" actions in the list
Cell J1 displays a "running total" of the number of actions - retrieved from the last "Ref no" entered in column B - so each time a new action is added, give it the next Ref no.
Hints....
Enter the names of actionees at the bottom of the sheet and assign them an abbreviation for use in column F.
If you want to change the "Issues"; change them on this sheet (you may need to re-define the named range "Issues" call me if you need assistance); edit the comment box for cell A4 and edit the custom footer via File_Page Setup.
When the action tracker is "up & running", order the actions by: column J - descending (Open actions first), column A - ascending (by "Issue" order), column I - ascending (by due date).
To extend the action tracker to cope with more actions, insert rows - this will ensure that formulae will apply to the new rows eg. for the dropdown list, conditional formatting etc.
You can hide closed actions and empty rows if you want for display and/or printing.
If you have regular weekly meetings and produce monthly reports from the data, note the relevant items under 'Report items', and at month end transfer to your report template.
You can use the "Autofilter" to display only the data you want to see