## Sheet1
|  |  |  | BRONE RENEWABLES SOALR HOUSE LTD - DAILY LOG |  |  |  |  | Total actions: | 2
Current Date:
2020-03-25
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update | By When | Days to Close | Status
NAME
1 |  |  |  | M | Revisiting of Sango Ota issue | Johnson/Ayo | I received information that Tundra is unavailable. | 25th March |  | open
2 |  |  |  | L | Reconsidering recommisioning of inverter at precise Lighting today | Johnson |  | 25th March |  | Open
3 |  |  |  | L | Design and sizing of 2 Bedroom Solar solution | Johson | The sising was instantly accomplished | 25th March | 25th March | closed
[9 empty] | Open: | 2
[9 empty] | Closed: | 0
| Actionees (Key): | [7 empty] | Info:
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding
|  |  |  | L | Low Finding
|  |  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 2 Closed 0 nfo