## 25-03-2020
|  | BRONE POSITIONING+SURVEY LTD - DAILY LOG |  |  |  |  | Total actions: | 9
|  |  | Daily Log |  | Current Date:
2020-03-25
Item No | Issue | Priority | What | Action Party | Update | By When | Days to Close | Status
Weekly Report - Abimbola Akindiilete
1 | SOP | M | Operations meeting | AO | Done | 25th March |  | Closed
2 | PA | M | Ticket booking for Salley | AO | Done | 25th March |  | Closed
3 | SOP | M | Arrange with drivers to and Salley to transfer equipment from LOS office to the airport | AO | Done | 25th March |  | Closed
4 | SOP | M | Follow up with artisans working in the office | AO | Done | 25th March |  | Closed
5 | SOP | M | Follow up with GMO on necessary admin duties towards the incoming Amni job | AO | Done | 25th March |  | Closed
6 | SOP | H | Continuation of pending recruitment | AO | On it | 25th March |  | Open
7 | SOP | M | ID card for new staff | AO | On it | 25th March |  | Open
8 | SOP | M | Sort out, rename and arrange all Admin Scanned files | AO | Done | 25th March |  | Closed
9 | SOP | M | Whatsapp account for Brone Admin Desk | AO | Done | 25th March |  | Closed
10 | SOP | H | Safety kits for Salley's travelling for Amini Project | AO | Purchased and delivery arrangement done | 25th March |  | Closed
[7 empty] | Open: | 2
[7 empty] | Closed: | 7
| Actionees (Key): | [5 empty] | Info:
|  | H | High Finding
|  | M | Medium Finding
|  | L | Low Finding
|  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on I4: Statuses are: Open 6 Closed Info