## Sheet1
|  |  |  | BRONE RENEWABLES SOALR HOUSE LTD - WEEKLY LOG |  |  |  |  | Total actions: | 2
Current Date:
2020-04-02
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update | By When | Days to Close | Status
NAME
1 |  |  |  | M | 48V/4KW Inverter to be recommision at Hudson Pacific | Johnson | Pending recommission due to Convik-19 Lockdown | 16/03/2020 |  | open
2 |  |  |  | L | Reconsidering recommisioning of inverter at precise Lighting | Johnson | Pending due to Convik-19 Lockdown | 20/03/2020 |  | Open
3 |  |  |  | L | Solar system maintenance at Sango Ota | Johson | Awaiting Battery replacement and Covik-19 lockdown effect | 13/03/2020 |  | open
4 |  |  |  | L | No Power supply to one of the Air conditions and some points in the Training Room | Johnson | The fault was troubleshooted and fixed instantly | 17/03/2020 | 17/03/2020 | closed
5 |  |  |  |  | Design and sizing of 2 Bedroom Solar solution | Johnson | The sizing was instantly accomplished | 25/03/2020 | 25/03/2020 | closed
6 |  |  |  |  | Energy audit at Lekki phase 1 | Johnson | Awaiting raw data from the client | 2020-02-04 |  | open
[9 empty] | Open: | 4
[9 empty] | Closed: | 2
| Actionees (Key): | [7 empty] | Info:
|  | Priority Key: |  | H | High Finding
|  |  |  | M | Medium Finding
|  |  |  | L | Low Finding
|  |  |  | Info | Information
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 4 Closed 2 nfo