## 10-01-2020
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 12
[7 empty] | Current Date: |  | 10.01.2020
[7 empty] | Last updated on: 10/01/2020 |  | 2020-01-10
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Ebika Ayeba-Enenimiete
1 | PA |  |  | M | SPDC Cad Contract 13th Salary for December 2019 | GMA | Paid | 8th January 2020 |  | Closed
2 | SOP |  |  | H | Requested Documents for Visa for AZMAN YUSOF | GMA | Sent | 1st Jan 2020 |  | Closed
3 | SOP |  |  | H | Request for Quote for Freelance Service | GMA | Document Sent to DMD for Approval and final document sent out to Vendors for Quotes | 3rd and 4th Jan 2020 |  | Closed
4 | PA |  |  | H | Positioning and Seabed Survey at Ima / Langley Contract | GMA/Legal | Executed and Final Copy Received From Amni, Signed and sent back to Amni | 7th Jan 2020 |  | Closed
5 | SOP |  |  | H | Bathymetric Survey for 4 X 150 MW Idowu Ramos Power Plant, Ramos Electric Coal (Lignite) Fired Power Plant Project at Ugbodu, Delta State for RAMOS ELECTRIC POWER LTD | GMA/Tendering Team | Ongoing |  |  | Open
6 | PA |  |  | H | Letters for Letter Head | GMA |  |  |  | Closed
7 | SOP |  |  | H | Follow up with the request for Quotes Received from different vendors and final selection process and counter offers | GMA/GMO | Done/Successful Vendors Selected |  |  | Closed
8 | SOP |  |  | H | Freelance Contract Agreements sent out to the chosen Vendors/Freelance personnel | GMA | Done | 10th Jan 2020 |  | Closed
9 | SOP |  |  | H | WHT Schedules Used and Unused for Tax Issues | GMA | Pending |  |  | Open
10 | SOP |  |  | M | Approval given to the Admin Assist. for Petty Cash Disbursement for this week | GMA | Done |  |  | Closed
11 | SOP |  |  | H | Tiling work for the Survey Pool and Office Entrance/Painting | GMA/AAO | Completed | 9th Jan 2020 |  | Closed
12 | PA |  |  | H | Email Responses to various Clients | GMA | Done |  |  | Closed
[9 empty] | Open: | 2
[9 empty] | Closed: | 10
| Actionees (Key): | [5 empty] | Ebika Ayeba-Enenimiete: GM, Contracts & Administration (GMA) |  | Info: | 0
Mr. Bunmi Akomolede: Managing Director (MD)
|  | Priority Key: |  | H | High Finding |  | Mrs. Tiwalade Akomolede: Deputy Managing Director (DMD)
|  |  |  | M | Medium Finding |  | Mr. Sunkanmi Dairo: Management Trainee (MT)
|  |  |  | L | Low Finding |  | Tender Team: Adebisi A., OloladeOlanipekun
|  |  |  | Info | Information |  | Accounts: Ufuoma Odogu
Adebisi Adenuga (GMO)
Bimbo Akindiilete (AO)
Mike Mattinson (DDO)
Satish Mudaliar (Team Lead, Survey Engrg.)
Busola Adekanmbi (GM, Finance & Admin, LOS
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 2 Closed 10 Info

## 17-01-2020
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 20
[7 empty] | Current Date: |  | 17.01.2020
[7 empty] | Last updated on: 17/01/2020 |  | 2020-01-17
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Ebika Ayeba-Enenimiete
1 | PA |  |  | M | Attestation Letters for Mobil Oyot Project | GMA | Sent to GMO | 14th Jan 2020 |  | Closed
2 | SOP |  |  | H | Follow up on Shell Invoices, November 2019 Due Invoice escalated to Shell Representative | GMA | Done | 14th Jan 2020 |  | Closed
3 | SOP |  |  | H | Request for Quote for Freelance Quinsy Surveyor/Equipment Hire | GMA/Procurements | Done | 13th Jan 2020 |  | Closed
4 | PA |  |  | H | Request for Survey Vessel | GMA/Procurements | Done | 13th Jan 2020 |  | Closed
5 | SOP |  |  | H | Bathymetric Survey for 4 X 150 MW Idowu Ramos Power Plant, Ramos Electric Coal (Lignite) Fired Power Plant Project at Ugbodu, Delta State for RAMOS ELECTRIC POWER LTD | GMA/Tendering Team | Submitted | 15th Jan 2020 & 16th Jan 2020 |  | Closed
6 | PA |  |  | H | Letters for Letter Head | GMA | Done | 15th Jan 2020 |  | Closed
7 | SOP |  |  | H | Commercial Proposal for Bathymetry Survey Amni Petroleum | GMA/Tendering Team | Submitted | 14th Jan 2020 |  | Closed
8 | SOP |  |  | H | Freelance Service Agreements for Quinsy Surveyor under Irentify | GMA | Done | 17th Jan 2020 |  | Closed
9 | PA |  |  | H | Kick Off Meeting at Jascon 39 Onne, Port Harcourt for Analogue Survey Mobil Oyot Project | GMA | Attended | 13th Jan 2020 |  | Closed
10 | PA |  |  | H | Updated Project Charge Sheet for Oyot Mobil Project | GMA | Sent to DMD | 15th Jan 2020 |  | Closed
11 | SOP |  |  | M | Payment Advices for VAT filing requested and received from Shell | GMA | Received | 15th Jan 2020 |  | Closed
12 | SOP |  |  | H | Confirmation Letters for Salley, Ademola, Ozegbe and Obioma | GMA | Done | 16th Jan 2020 |  | Closed
13 | SOP |  |  | H | Letter for Hydrogarphic Survey Permit for Amni Bathymetry Work | GMA | Sent to Dotun | 16th Jan 2020 |  | Closed
14 | PA |  |  | H | Service Order Amendment 8 for Bathymety Survey Project | GMA | Signed and Executed | 16th Jan 2020 |  | Closed
15 | SOP |  |  | H | Contract Templates for Surveyor and Document control | GMA | Sent to Bimbo | 17th Jan 2020 |  | Closed
16 | SOP |  |  | M | Budget PHC Jan Week 4 | GMA/Enigha | Sent to Accounts | 17th Jan 2020 |  | Closed
17 | SOP |  |  | H | WHT Schedules Used and Unused for Tax Issues | GMA | Pending |  |  | Open
18 | SOP |  |  | H | Information for PAYE Annual Returns for Lagos Staff | GMA | Sent to Bimbo | 17th Jan 2020 |  | Closed
19 | SOP |  |  | M | Approval given to the Admin Assist. for Petty Cash Disbursement for this week | GMA | Done |  |  | Closed
20 | PA |  |  | H | Email Responses to various Clients | GMA | Done | 13th-17th Jan 2020 |  | Closed
[9 empty] | Open: | 1
[9 empty] | Closed: | 19
| Actionees (Key): | [5 empty] | Ebika Ayeba-Enenimiete: GM, Contracts & Administration (GMA) |  | Info: | 0
Mr. Bunmi Akomolede: Managing Director (MD)
|  | Priority Key: |  | H | High Finding |  | Mrs. Tiwalade Akomolede: Deputy Managing Director (DMD)
|  |  |  | M | Medium Finding |  | Mr. Sunkanmi Dairo: Management Trainee (MT)
|  |  |  | L | Low Finding |  | Tender Team: Adebisi A., OloladeOlanipekun
|  |  |  | Info | Information |  | Accounts: Ufuoma Odogu
Adebisi Adenuga (GMO)
Bimbo Akindiilete (AO)
Mike Mattinson (DDO)
Satish Mudaliar (Team Lead, Survey Engrg.)
Busola Adekanmbi (GM, Finance & Admin, LOS
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 1 Closed 19 Info

## 24-01-2020
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 16
[7 empty] | Current Date: |  | 24.01.2020
[7 empty] | Last updated on: 24/01/2020 |  | 2020-01-24
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Ebika Ayeba-Enenimiete
1 | PA |  |  | M | Freelance Service Agreement for Dogiye Saigbolo Irentify Consultant | GMA | Sent and Excecuted | 20th Jan 2020 |  | Closed
2 | SOP |  |  | H | Project Charge Sheet for Amni Bathymetry Survey | GMA | Done | 20th Jan 2020 |  | Closed
3 | PA |  |  | H | Email Account for New staff Tolu Eronmonseh | GMA | Done | 20th Jan 2020 |  | Closed
4 | SOP |  |  | H | Extension of CPA for Jascon 39 | GMA | Email sent and Addendum Executed and sent to Mobil | 20th Jan 2020 |  | Closed
5 | PA |  |  | H | Letters for Letter Head | GMA | Done | 20th and 23rd Jan 2020 |  | Closed
6 | SOP |  |  | H | Documents for invoicing requested for GMFA on expats Visas and TWPs | GMA | Forwarded to GMFA | 20th Jan 2020 |  | Closed
7 | SOP |  |  | H | Invoice for AGOL Service Credit Payment for SPDC Cad Contract | GMA | Done and Submitted | 21st Jan 2020 |  | Closed
8 | PA |  |  | H | Bullet point on actions and resolutions in a document format for Exxon Mobil Meeting | GMA | Sent to DMD | 22nd Jan 2020 |  | Closed
9 | PA |  |  | H | Commercial Proposal for Realtime Bathymetry Survey Services for Amni | GMA/Tendering Team | Submitted | 22nd Jan 2020 |  | Closed
10 | SOP |  |  | M | Commercial Proposal for Advisian Worley Group- Geophysical and Geotechnical works | GMA/Tendering Team | Submitted | 23rd Jan 2020 |  | Closed
11 | SOP |  |  | H | More information for Annual Filing of Paye Lagos Staff | GMA | Sent To Bimbo | 23rd Jan 2020 |  | Closed
12 | SOP |  |  | M | Budget PHC Jan Week 5 | GMA/Enigha | Sent to Accounts | 24th Jan 2020 |  | Closed
13 | SOP |  |  | H | WHT Schedules Used and Unused for Tax Issues | GMA | Pending |  |  | Open
14 | SOP |  |  | H | Annual Filing FOR Phc staff and Personal Income Tax for DMD | GMA/Enigha | Pending |  |  | Open
15 | SOP |  |  | M | Approval given to the Admin Assist. for Petty Cash Disbursement for this week | GMA | Done |  |  | Closed
16 | PA |  |  | H | Email Responses to various Clients | GMA | Done | 20th-24th Jan 2020 |  | Closed
[9 empty] | Open: | 2
[9 empty] | Closed: | 14
| Actionees (Key): | [5 empty] | Ebika Ayeba-Enenimiete: GM, Contracts & Administration (GMA) |  | Info: | 0
Mr. Bunmi Akomolede: Managing Director (MD)
|  | Priority Key: |  | H | High Finding |  | Mrs. Tiwalade Akomolede: Deputy Managing Director (DMD)
|  |  |  | M | Medium Finding |  | Mr. Sunkanmi Dairo: Management Trainee (MT)
|  |  |  | L | Low Finding |  | Tender Team: Adebisi A., OloladeOlanipekun
|  |  |  | Info | Information |  | Accounts: Ufuoma Odogu
Adebisi Adenuga (GMO)
Bimbo Akindiilete (AO)
Mike Mattinson (DDO)
Satish Mudaliar (Team Lead, Survey Engrg.)
Busola Adekanmbi (GM, Finance & Admin, LOS
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 2 Closed 14 Info

## 31-01-2020
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 16
[7 empty] | Current Date: |  | 31.01.2020
[7 empty] | Last updated on: 31/01/2020 |  | 2020-01-31
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Ebika Ayeba-Enenimiete
1 | PA |  |  | H | Technical and Commercial Tender for Obodo - Escravos Route Survey for Conoil/CONOG | GMA/Tendering Team | Submitted | 27th Jan 2020 |  | Closed
2 | SOP |  |  | H | Supply of 2 Nos of Feeder Barges in 2 options (Hire & Outright Purchase) for Sterling Petroleum | GMA/Tendering Team | Ongoing |  |  | Open
3 | PA |  |  | H | Documents for NPDC Technical Bids Assessments | GMA/Tendering Team | Done | 31st Jan 2020 |  | Closed
4 | SOP |  |  | H | DTO REGISTRATION FORMS AND REQUIREMENTS - IKIKE SURF PROJECT PRE-QUALIFICAITON | GMA/Tendering Team | Filled and Signed Forms/ Required Documents Submitted | 31st Jan 2020 |  | Closed
5 | PA |  |  | H | Industrial Relations and Human Resource Management Plans - Reviewed | GMA | Done | 30th Jan 2020 |  | Closed
6 | SOP |  |  | H | Salary Breakdown for BEG and expatriates January 2020 | GMA/GMFA/Bimbo | Final Reviewed computed Salaries sent to DMD | 28th Jan 2020 |  | Closed
7 | SOP |  |  | H | MOA with Terralog for Geomechanics Projects | GMA | Sent, awaiting signed Copy | 30th Jan 2020 |  | Open
8 | PA |  |  | H | Requested Remittance Schedule for SPDC Cad Contract Staff for Pension Alliance | GMA | Sent to Pension Alliance | 30th Jan 2020 |  | Closed
9 | PA |  |  | H | Revised Conoil/CONOG Commercial Tender | GMA/Tendering Team | Submitted | 31st Jan 2020 |  | Closed
10 | SOP |  |  | M | ONGC EOI for for providing metocean, geophysical, geotechnical survey services on hiring basis with Petroviz consultants | GMA/Tendering Team | Ongoing |  |  | Open
11 | SOP |  |  | H | MOA with Argyle Petroleum for Geomechanics Project with NPDC | GMA | Signed and Exceuted | 31st Jan 2020 |  | Closed
12 |  |  |  | H | DPR Permit for Technical Consultancy | GMA | Ongoing |  |  | Open
13 | SOP |  |  | M | Budget PHC Feb Week 1 | GMA/Enigha | Sent to Accounts | 31st Jan 2020 |  | Closed
14 | SOP |  |  | H | WHT Schedules Used and Unused for Tax Issues | GMA | Pending |  |  | Open
15 | SOP |  |  | H | Annual Filing FOR Phc staff and Personal Income Tax for DMD | GMA/Enigha | Pending |  |  | Open
16 | SOP |  |  | M | Approval given to the Admin Assist. for Petty Cash Disbursement for this week | GMA | Done |  |  | Closed
17 | PA |  |  | H | Email Responses to various Clients | GMA | Done | 27th-31st Jan 2020 |  | Closed
[9 empty] | Open: | 6
[9 empty] | Closed: | 11
| Actionees (Key): | [5 empty] | Ebika Ayeba-Enenimiete: GM, Contracts & Administration (GMA) |  | Info: | 0
Mr. Bunmi Akomolede: Managing Director (MD)
|  | Priority Key: |  | H | High Finding |  | Mrs. Tiwalade Akomolede: Deputy Managing Director (DMD)
|  |  |  | M | Medium Finding |  | Mr. Sunkanmi Dairo: Management Trainee (MT)
|  |  |  | L | Low Finding |  | Tender Team: Adebisi A., OloladeOlanipekun
|  |  |  | Info | Information |  | Accounts: Ufuoma Odogu
Adebisi Adenuga (GMO)
Bimbo Akindiilete (AO)
Mike Mattinson (DDO)
Satish Mudaliar (Team Lead, Survey Engrg.)
Busola Adekanmbi (GM, Finance & Admin, LOS
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 6 Closed 11 Info

## 07-02-2020
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 16
[7 empty] | Current Date: |  | 07.02.2020
[7 empty] | Last updated on: 07/02/2020 |  | 2020-02-07
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Ebika Ayeba-Enenimiete
1 | PA |  |  | H | Remittance Schedules and payment for Pensions January 2020, PAYE Payment Jan 2020 | GMA/Enigha | Done | 4th Feb 2020 |  | Closed
2 | SOP |  |  | H | Supply of 2 Nos of Feeder Barges in 2 options (Hire & Outright Purchase) for Sterling Petroleum | GMA/Tendering Team | Declined |  |  | Closed
3 | PA |  |  | H | Reference Letter for Lolade Olanipekun | GMA | Done | 7th Feb 2020 |  | Closed
7 | SOP |  |  | H | MOA with Terralog for Geomechanics Projects | GMA | Terralog Declined at this time | 4th Feb 2020 |  | Closed
10 | SOP |  |  | M | ONGC EOI for for providing metocean, geophysical, geotechnical survey services on hiring basis with Petroviz consultants | GMA/Tendering Team | Ongoing |  |  | Open
12 |  |  |  | H | DPR Permit for Technical Consultancy | GMA | Ongoing |  |  | Open
[5 empty] | HMO Renewal List for Brone Personnel | GMA | Done for Phc, Instructed Bimbo to complile the LOS List for final Approval |  |  | Closed
13 | SOP |  |  | M | Budget PHC Feb Week 2 | GMA/Enigha | Sent to Accounts | 7th Feb 2020 |  | Closed
14 | SOP |  |  | H | WHT Schedules Used and Unused for Tax Issues | GMA | Pending |  |  | Open
15 | SOP |  |  | H | Annual Filing FOR Phc staff and Personal Income Tax for DMD | GMA/Enigha | Pending |  |  | Open
16 | SOP |  |  | M | Approval given to the Admin Assist. for Petty Cash Disbursement for this week | GMA | Done |  |  | Closed
17 | PA |  |  | H | Email Responses to various Clients | GMA | Done | 3rd-7th Feb 2020 |  | Closed
[9 empty] | Open: | 6
[9 empty] | Closed: | 11
| Actionees (Key): | [5 empty] | Ebika Ayeba-Enenimiete: GM, Contracts & Administration (GMA) |  | Info: | 0
Mr. Bunmi Akomolede: Managing Director (MD)
|  | Priority Key: |  | H | High Finding |  | Mrs. Tiwalade Akomolede: Deputy Managing Director (DMD)
|  |  |  | M | Medium Finding |  | Mr. Sunkanmi Dairo: Management Trainee (MT)
|  |  |  | L | Low Finding |  | Tender Team: Adebisi A., OloladeOlanipekun
|  |  |  | Info | Information |  | Accounts: Ufuoma Odogu
Adebisi Adenuga (GMO)
Bimbo Akindiilete (AO)
Mike Mattinson (DDO)
Satish Mudaliar (Team Lead, Survey Engrg.)
Busola Adekanmbi (GM, Finance & Admin, LOS
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 6 Closed 11 Info

## 14-02-2020
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 16
[7 empty] | Current Date: |  | 14.02.2020
[7 empty] | Last updated on: 14/02/2020 |  | 2020-02-14
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Ebika Ayeba-Enenimiete
1 | PA |  |  | H | Invoices for January 2020/SEs GIM Services and Geomatics Calender | GMA | Done and Submitted | 12th Feb 2020 |  | Closed
2 | SOP |  |  | H | Commercial offer request and Technical bid - Tender JESA-QI930101-20 Bathymetric | GMA/Tendering Team | Submitted on Jesa Ariba Portal | 14th Feb 2020 |  | Closed
3 | PA |  |  | H | Previous Employer Reference form for Bolanle Oyewole | GMA | I am waiting for information on her last salary before her exiting from Peju, so I put in the right information. I don’t have any 2013 Salary Schedule for LOS staff |  |  | Open
4 | SOP |  |  | H | Salary Schedules for NSITF Audit | GMA | Done | 14th Feb 2020 |  | Closed
5 | SOP |  |  | M | ONGC EOI for for providing metocean, geophysical, geotechnical survey services on hiring basis with Petroviz consultants | GMA/Tendering Team | Ongoing |  |  | Open
6 | SOP |  |  | H | DPR Permit for Technical Consultancy | GMA | Ongoing |  |  | Open
7 | SOP |  |  | H | Letter Head for letters | GMA | Issued | 10th and 14th Feb 2020 |  | Closed
8 | SOP |  |  | M | Budget PHC Feb Week 3 | GMA/Enigha | Sent to Accounts | 14th Feb 2020 |  | Closed
9 | SOP |  |  | H | WHT Schedules Used and Unused for Tax Issues | GMA | Pending |  |  | Open
10 | SOP |  |  | H | Annual Filing FOR Phc staff and Personal Income Tax for DMD | GMA/Enigha | Pending |  |  | Open
11 | SOP |  |  | M | Approval given to the Admin Assist. for Petty Cash Disbursement for this week | GMA | Done |  |  | Closed
12 | PA |  |  | H | Email Responses to various Clients | GMA | Done | 10th-14th Feb 2020 |  | Closed
[9 empty] | Open: | 6
[9 empty] | Closed: | 11
| Actionees (Key): | [5 empty] | Ebika Ayeba-Enenimiete: GM, Contracts & Administration (GMA) |  | Info: | 0
Mr. Bunmi Akomolede: Managing Director (MD)
|  | Priority Key: |  | H | High Finding |  | Mrs. Tiwalade Akomolede: Deputy Managing Director (DMD)
|  |  |  | M | Medium Finding |  | Mr. Sunkanmi Dairo: Management Trainee (MT)
|  |  |  | L | Low Finding |  | Tender Team: Adebisi A., Felix Oyeleke
|  |  |  | Info | Information |  | Accounts: Ufuoma Odogu
Adebisi Adenuga (GMO)
Bimbo Akindiilete (AO)
Mike Mattinson (DDO)
Satish Mudaliar (Team Lead, Survey Engrg.)
Busola Adekanmbi (GM, Finance & Admin, LOS
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 6 Closed 11 Info

## 21-02-2020
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 16
[7 empty] | Current Date: |  | 21.02.2020
[7 empty] | Last updated on: 21/02/2020 |  | 2020-02-21
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Ebika Ayeba-Enenimiete
1 | PA |  |  | H | Invoices for February 2020 SEs for GIM Services | GMA | Done and Submitted | 18th Feb 2020 |  | Closed
2 | SOP |  |  | H | Cover Letter for Exxon Mobil Oyot Project Invoices | GMA | Done | 18th Feb 2020 |  | Closed
3 | PA |  |  | H | Previous Employer Reference form for Bolanle Oyewole | GMA | Done and Submitted | 17th Feb 2020 |  | Closed
4 | SOP |  |  | H | Authorisation Letter to Retrieve CUG Lines | GMA | Done | 18th Feb 2020 |  | Closed
5 | SOP |  |  | H | Updated CV for DMD | GMA | Done | 19th Feb 2020 |  | Closed
6 | SOP |  |  | H | Employment Letter for New Steward Innocent Lekki Base on Brone Letter Head | GMA | Done | 19th Feb 2020 |  | Closed
7 | SOP |  |  | H | Request for Payment advices from SPDC and Due Dates for New Invoices Submitted | GMA | Requested Payment Advices Received from Shell Vendor Services | 19th Feb 2020 |  | Closed
8 | SOP |  |  | H | Vat filing for Payments received in January 2020 | GMA/Enigha | Done | 19th Feb 2020 |  | Closed
9 | SOP |  |  | M | ONGC EOI for for providing metocean, geophysical, geotechnical survey services on hiring basis with Petroviz consultants | GMA/Tendering Team | Done |  |  | Closed
10 | SOP |  |  | H | DPR Permit for Technical Consultancy | GMA | Ongoing |  |  | Open
11 | SOP |  |  | H | Letter Head for letters | GMA | Issued | 10th and 14th Feb 2020 |  | Closed
12 | SOP |  |  | M | Budget PHC Feb Week 4 | GMA/Enigha | Sent to Accounts | 14th Feb 2020 |  | Closed
13 | SOP |  |  | H | WHT Schedules Used and Unused for Tax Issues | GMA | Pending |  |  | Open
14 | SOP |  |  | H | Annual Filing FOR Phc staff and Personal Income Tax for DMD | GMA/Enigha | Ongoing |  |  | Open
15 | SOP |  |  | M | Approval given to the Admin Assist. for Petty Cash Disbursement for this week | GMA | Done |  |  | Closed
16 | PA |  |  | H | Email Responses to various Clients | GMA | Done | 17th-20th Feb 2020 |  | Closed
[9 empty] | Open: | 3
[9 empty] | Closed: | 13
| Actionees (Key): | [5 empty] | Ebika Ayeba-Enenimiete: GM, Contracts & Administration (GMA) |  | Info: | 0
Mr. Bunmi Akomolede: Managing Director (MD)
|  | Priority Key: |  | H | High Finding |  | Mrs. Tiwalade Akomolede: Deputy Managing Director (DMD)
|  |  |  | M | Medium Finding |  | Mr. Sunkanmi Dairo: Management Trainee (MT)
|  |  |  | L | Low Finding |  | Tender Team: Adebisi A., Felix Oyeleke
|  |  |  | Info | Information |  | Accounts: Ufuoma Odogu
Adebisi Adenuga (GMO)
Bimbo Akindiilete (AO)
Mike Mattinson (DDO)
Satish Mudaliar (Team Lead, Survey Engrg.)
Busola Adekanmbi (GM, Finance & Admin, LOS
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 3 Closed 13 Info

## 28-02-2020
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 16
[7 empty] | Current Date: |  | 28.02.2020
[7 empty] | Last updated on: 28/02/2020 |  | 2020-02-28
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Ebika Ayeba-Enenimiete
1 | PA |  |  | H | SPDC TENDER FOR PROVISION OF GEOSCIENCE SUPERVISION SERVICES - IN PARTNERSHIP WITH TRUE BLUE ENERGY | GMA/Tendering Team | Requested Documents Submitted |  |  | Open
2 | SOP |  |  | H | Revised Commercial for Topographic Services for Survey of Oil Pipeline Route OML13 NPDC Block | GMA/Tendering Team | Submitted | 25th Feb 2020 |  | Closed
3 | PA |  |  | H | TWP Documents and Request Letter for Satish Mudaliar | GMA | Sent | 25th Feb 2020 |  | Closed
4 | SOP |  |  | H | Salaries for February 2020 | GMA | Done | 26th Feb 2020 |  | Closed
5 | SOP |  |  | H | Indemnity Letter to Zenith Bank as Instructed by DMD | GMA | Done | 19th Feb 2020 |  | Closed
6 | SOP |  |  | H | Amni Commercial Proposal for Tidal Observation at Tubu | GMA/Tendering Team | Submitted | 26th Feb 2020 |  | Closed
7 | SOP |  |  | H | Expatriates Salary Breakdown for Feb 2020 | GMA | Done | 27th feb 2020 |  | Closed
8 | SOP |  |  | H | MOA with True Blue Energy for SPDC Geoscience Supervision tender | GMA | Done | 25th Feb 2020 |  | Closed
9 | SOP |  |  | M | Instructions & Discussion with Temi Adegbite for Legal input on GMO's email response on the letters received from ACME Lawyer for Brone Email Response | GMA/Legal | Done | 25th & 27th Feb 2020 |  | Open
10 | SOP |  |  | H | DPR Permit for Technical Consultancy | GMA | Ongoing |  |  | Open
11 | SOP |  |  | M | Paye Phc and Pensions for Feb 2020 | GMA | Remittance schedules and payments made for Pension and Paye payment made | 28th Feb 2020 |  | Closed
12 | SOP |  |  | M | Budget PHC Mar Week 1 | GMA/Enigha | Sent to Accounts | 14th Feb 2020 |  | Closed
13 | SOP |  |  | H | WHT Schedules Used and Unused for Tax Issues | GMA | Pending |  |  | Open
14 | SOP |  |  | H | Annual Filing FOR Phc staff and Personal Income Tax for DMD | GMA/Enigha | Ongoing |  |  | Open
15 | SOP |  |  | M | Approval given to the Admin Assist. for Petty Cash Disbursement for this week | GMA | Done |  |  | Closed
16 | PA |  |  | H | Email Responses to various Clients | GMA | Done | 24th-28th Feb 2020 |  | Closed
[9 empty] | Open: | 5
[9 empty] | Closed: | 11
| Actionees (Key): | [5 empty] | Ebika Ayeba-Enenimiete: GM, Contracts & Administration (GMA) |  | Info: | 0
Mr. Bunmi Akomolede: Managing Director (MD)
|  | Priority Key: |  | H | High Finding |  | Mrs. Tiwalade Akomolede: Deputy Managing Director (DMD)
|  |  |  | M | Medium Finding |  | Mr. Sunkanmi Dairo: Management Trainee (MT)
|  |  |  | L | Low Finding |  | Tender Team: Adebisi A., Felix Oyeleke
|  |  |  | Info | Information |  | Accounts: Ufuoma Odogu
Adebisi Adenuga (GMO)
Bimbo Akindiilete (AO)
Mike Mattinson (DDO)
Satish Mudaliar (Team Lead, Survey Engrg.)
Busola Adekanmbi (GM, Finance & Admin, LOS
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 5 Closed 11 Info

## 06-03-2020
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 16
[7 empty] | Current Date: |  | 06.03.2020
[7 empty] | Last updated on: 06/03/2020 |  | 2020-03-06
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Ebika Ayeba-Enenimiete
1 | PA |  |  | H | SPDC TENDER FOR PROVISION OF GEOSCIENCE SUPERVISION SERVICES - IN PARTNERSHIP WITH TRUE BLUE ENERGY | GMA/Tendering Team | Requested Documents Submitted | 2nd March 2020 |  | Closed
2 | SOP |  |  | H | Reviewed and Updated Previous Employer Reference Form for Brone | GMA | Submitted | 2nd March 2020 |  | Closed
3 | PA |  |  | H | REQUEST FOR QUOTE FOR SUPPLY OF SURVEY MATERIALS FOR ANOH-SPDC PROJECT | GMA/Tendering Team | Brone does not have the requested equipment | 3rd March 2020 |  | Closed
4 | SOP |  |  | H | Commercial Proposal Amni for Tubu SeaBed Survey & Close Grid Bathymetry | GMA/Tendering Team | Submitted | 3rd March 2020 |  | Closed
5 | SOP |  |  | H | Commercial Proposal Amni Real-Time Bathymetry Survey | GMA/Tendering Team | Submitted | 3rd March 2020 |  | Closed
6 | SOP |  |  | H | Re-Submitted Amni Commercial Proposal for Tidal Observation at Tubu | GMA/Tendering Team | Submitted | 3rd March 2020 |  | Closed
7 | SOP |  |  | H | AMNI Contractor Registration online | GMA | Done and Requested Documents Uploaded | 4th March 2020 |  | Closed
8 | SOP |  |  | H | SHARJAH KYC- form for bureau | GMA | Filled | 6th March 2020 |  | Closed
9 | SOP |  |  | M | Whatsapp Meeting with Temi and GMO on plans and Brone stand for the re-scheduled meeting for 6th March 2020 with ACME and Lawyer | GMA/Legal/GMO | Done | 5th March 2020 |  | Closed
10 | SOP |  |  | H | DPR Permit for Technical Consultancy | GMA | Under Processing on the OGISP/DPR Portal |  |  | Open
11 | SOP |  |  | M | Query Letter for Dotun | GMA | Sent to Busola | 6th March 2020 |  | Closed
12 | SOP |  |  | M | Budget PHC Mar Week 2 | GMA/Enigha | Sent to Accounts | 6th March 2020 |  | Closed
13 | SOP |  |  | H | WHT Schedules Used and Unused for Tax Issues | GMA | Ongoing, Used ones are being filed |  |  | Open
14 | SOP |  |  | H | Annual Filing FOR Phc staff and Personal Income Tax for DMD | GMA/Enigha | Ongoing |  |  | Open
15 | SOP |  |  | M | Approval given to the Admin Assist. for Petty Cash Disbursement for this week | GMA | Done |  |  | Closed
16 | PA |  |  | H | Email Responses to various Clients | GMA | Done | 2nd-6th Mar 2020 |  | Closed
[9 empty] | Open: | 3
[9 empty] | Closed: | 13
| Actionees (Key): | [5 empty] | Ebika Ayeba-Enenimiete: GM, Contracts & Administration (GMA) |  | Info: | 0
Mr. Bunmi Akomolede: Managing Director (MD)
|  | Priority Key: |  | H | High Finding |  | Mrs. Tiwalade Akomolede: Deputy Managing Director (DMD)
|  |  |  | M | Medium Finding |  | Mr. Sunkanmi Dairo: Management Trainee (MT)
|  |  |  | L | Low Finding |  | Tender Team: Adebisi A., Felix Oyeleke
|  |  |  | Info | Information |  | Accounts: Ufuoma Odogu
Adebisi Adenuga (GMO)
Bimbo Akindiilete (AO)
Mike Mattinson (DDO)
Satish Mudaliar (Team Lead, Survey Engrg.)
Busola Adekanmbi (GM, Finance & Admin, LOS
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 3 Closed 13 Info

## 13-03-2020
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 21
[7 empty] | Current Date: |  | 13.03.2020
[7 empty] | Last updated on: 13/03/2020 |  | 2020-03-13
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Ebika Ayeba-Enenimiete
1 | PA |  |  | H | Reviewed Employment Letter sent by Bimbo and sent letter headed acceptance letter for Felix Oyeleke | GMA | Sent back to Bimbo after reviewing and formatting | 9th March 2020 |  | Closed
2 | SOP |  |  | H | Confirmation Letter for Johnson Omaba | GMA | Sent | 11th March 2020 |  | Closed
3 | PA |  |  | H | Siwes Letter of Engagement and Acceptance Letter on Letter head for High Praise | GMA | Sent back to Bimbo | 9th March 2020 |  | Closed
4 | SOP |  |  | H | Follow up on Brone Nipex Status and Reactivation | GMA | Sent Updated documents and payments | 10th -13th March 2020 |  | Closed
5 | SOP |  |  | H | SPDC Staff Salaries Feb 2020, Pension Oct 2019 and Paye Feb 2020 | GMA | Paid and remittance Schedules sent to PFAs | 10th March 2020 |  | Closed
6 | SOP |  |  | H | INVITATION TO TENDER: DEBRIS SURVEY AND SEWOP POSITIONING SERVICES FOR AMNI PETROLEUM | GMA/Tendering Team | Ongoing |  | 18th March 2020 | Open
7 | SOP |  |  | H | Filled and Signed Acknowledgement Form for Amni Debris Survey and Sewop Positioning | GMA | Submitted | 13th March 2020 |  | Closed
8 | SOP |  |  | H | Registration on JESA Portal | GMA | Ongoing |  |  | Open
9 | SOP |  |  | H | VAT Instalment payment for 2014/2015 Audit Liability Raised | GMA/Enigha | Paid and Filed at VAT Office | 12th March 2020 |  | Closed
10 | SOP |  |  | H | Re-Submitted requested document for insurance for the re-opened AMNI Contractor Registration online | GMA | Done and Requested Document Uploaded | 13th March 2020 |  | Closed
11 | SOP |  |  | H | Re-Drafted Query Letter for Dotun | GMA | Sent To GMFA - Issued | 11th March 2020 |  | Closed
12 | SOP |  |  | M | Discounted Commercial Proposal for Tidal Observation at Tubu | GMA/Tendering Team | Submitted | 11th March 2020 |  | Closed
13 | SOP |  |  | H | DPR Permit for Technical Consultancy | GMA | Under Processing on the OGISP/DPR Portal |  |  | Open
14 | SOP |  |  | M | Letter Head for USD Withdrawals and letter of authority | GMA | Sent to Busola/Ufuoma | 9th & 12th March 2020 |  | Closed
15 | SOP |  |  | H | Confirmation of Remittance of Accrued Pension Contribution for IBTC pensions | GMA | Letter sent | 12th March 2020 |  | Closed
16 | SOP |  |  | M | Total E & P Nipex Geophysical and Geotechnical Tender | GMA & Tendering Team | Ongoing |  | 6th April 2020 | Open
17 | SOP |  |  | M | Budget PHC Mar Week 3 | GMA/Enigha | Sent to Accounts | 6th March 2020 |  | Closed
18 | SOP |  |  | H | WHT Schedules Used and Unused for Tax Issues | GMA | Ongoing, Used ones are being filed |  |  | Open
19 | SOP |  |  | H | Annual Filing FOR Phc staff and Personal Income Tax for DMD | GMA/Enigha | Done |  |  | Closed
20 | SOP |  |  | M | Approval given to the Admin Assist. for Petty Cash Disbursement for this week | GMA | Done |  |  | Closed
21 | PA |  |  | H | Email Responses to various Clients | GMA | Done | 9th-13th Mar 2020 |  | Closed
[9 empty] | Open: | 5
[9 empty] | Closed: | 16
| Actionees (Key): | [5 empty] | Ebika Ayeba-Enenimiete: GM, Contracts & Administration (GMA) |  | Info: | 0
Mr. Bunmi Akomolede: Managing Director (MD)
|  | Priority Key: |  | H | High Finding |  | Mrs. Tiwalade Akomolede: Deputy Managing Director (DMD)
|  |  |  | M | Medium Finding |  | Mr. Sunkanmi Dairo: Management Trainee (MT)
|  |  |  | L | Low Finding |  | Tender Team: Adebisi A., Felix Oyeleke
|  |  |  | Info | Information |  | Accounts: Ufuoma Odogu
Adebisi Adenuga (GMO)
Bimbo Akindiilete (AO)
Mike Mattinson (DDO)
Satish Mudaliar (Team Lead, Survey Engrg.)
Busola Adekanmbi (GM, Finance & Admin, LOS
Tolu Eronmonseh
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 5 Closed 16 Info

## 20-03-2020
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 18
[7 empty] | Current Date: |  | 20.03.2020
[7 empty] | Last updated on: 20/03/2020 |  | 2020-03-20
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Ebika Ayeba-Enenimiete
1 | PA |  |  | H | Signed Amendment 9-Tidal Measurement Amni International | GMA | Sent to Amni for execution | 16th March 2020 |  | Closed
2 | SOP |  |  | H | Memo on Corona Virus Alert and Security Alert to all Staff | GMA | Sent | 16th and 17th March 2020 |  | Closed
3 | PA |  |  | H | March 2020 Invoices and SEs for SPDC CAD Contract | GMA | Invoices and SEs sent to Enigha to submit at Shell Vendor Service | 19th March 2020 |  | Closed
4 | SOP |  |  | H | Nipex Geophysical and Geotechnical Tender for Total E & P | GMA/Tendering Team | Ongoing |  | 6th April 2020 | Open
5 | SOP |  |  | H | ITF Registration for 2020 | GMA | Ongoing |  |  | Open
6 | SOP |  |  | H | INVITATION TO TENDER: DEBRIS SURVEY AND SEWOP POSITIONING SERVICES FOR AMNI PETROLEUM | GMA/Tendering Team | Submitted | 18th March 2020 |  | Closed
7 | SOP |  |  | H | Authorisation Letter for CUG Lines | GMA | Sent to Bimbo | 17th March 2020 |  | Closed
8 | SOP |  |  | H | Registration on JESA Portal | GMA | Done | 20th March 2020 |  | Closed
9 | SOP |  |  | H | Negotiated Quotes with Freelance and Angus Survey for Personnel Supply and Equipment Hire for Tidal Measurement Project | GMA | Quotes Negotiated with Angus Survey | 19th March 2020 |  | Closed
10 | SOP |  |  | H | To Whom It May Concern Letter and Last Six Months Pay Slips for Satish Mudaliar | GMA | Sent | 18th March 2020 |  | Closed
11 | SOP |  |  | H | Request for Payment Advices and Due Dates for Submitted Shell Invoices | GMA | Received from Vendor Service Shell | 18th March 2020 |  | Closed
12 | SOP |  |  | M | Signed Amendment 10 by MD -Closed Bathymetry survey and Seabed survey | GMA | Emailed to Amni | 19th March 2020 |  | Closed
13 | SOP |  |  | H | DPR Permit for Technical Consultancy | GMA | Under Processing on the OGISP/DPR Portal |  |  | Open
14 | SOP |  |  | M | Meeting with Rumuogba Community Development Committee (CDC) | GMA | Meeting was held and Brone was notified of certain development levies to be paid and empowerment of the community youths and logistic support. The Brone GM Admin responded that for employment and CLO, we cannot do anything about that due to the economic situation, we are not employing and we do not need a CLO since we are not running any contract for the community. We can only support them with the little we have towards development. A 300k development fee was mentioned but the GM, Admin for Brone made the committee understand that the levy is too high and it is not something we can pay. The meeting was adjourned and the committe chairman will get back to us on matters discussed. | 20th March 2020 |  | Closed
15 | SOP |  |  | M | Budget PHC Mar Week 4 | GMA/Enigha | Sent to Accounts | 20th March 2020 |  | Closed
16 | SOP |  |  | H | WHT Schedules Used and Unused for Tax Issues | GMA | Ongoing, Used ones are being filed |  |  | Open
17 | SOP |  |  | M | Approval given to the Admin Assist. for Petty Cash Disbursement for this week | GMA | Done |  |  | Closed
18 | PA |  |  | H | Email Responses to various Clients | GMA | Done | 16th-20th Mar 2020 |  | Closed
[9 empty] | Open: | 4
[9 empty] | Closed: | 14
| Actionees (Key): | [5 empty] | Ebika Ayeba-Enenimiete: GM, Contracts & Administration (GMA) |  | Info: | 0
Mr. Bunmi Akomolede: Managing Director (MD)
|  | Priority Key: |  | H | High Finding |  | Mrs. Tiwalade Akomolede: Deputy Managing Director (DMD)
|  |  |  | M | Medium Finding |  | Mr. Sunkanmi Dairo: Management Trainee (MT)
|  |  |  | L | Low Finding |  | Tender Team: Adebisi A., Felix Oyeleke
|  |  |  | Info | Information |  | Accounts: Ufuoma Odogu
Adebisi Adenuga (GMO)
Bimbo Akindiilete (AO)
Mike Mattinson (DDO)
Satish Mudaliar (Team Lead, Survey Engrg.)
Busola Adekanmbi (GM, Finance & Admin, LOS
Tolu Eronmonseh
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 4 Closed 14 Info

## 27-03-2020
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 34
[7 empty] | Current Date: |  | 27.03.2020
[7 empty] | Last updated on: 27/03/2020 |  | 2020-03-27
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Ebika Ayeba-Enenimiete
1 | PA |  |  | H | Reviewed Copy of Business Continuity Plan due COVID-19 Pandemic as Requested by Exxon Mobil | GMA | Sent to ExxonMobil | 27th March 2020 |  | Closed
2 | SOP |  |  | H | Signed Acknowledgement Form & Confidentiality Undertaking for Total Geophysical and Geotechnical Investigation | GMA | Sent to Toal E & P | 27th March 2020 |  | Closed
3 | PA |  |  | H | Geomatics 2020 Calendar for Reprinting Invoice and SE for SPDC CAD Contract | GMA | Invoice and SE sent to Enigha to submit at Shell Vendor Service | 26th March 2020 |  | Closed
4 | SOP |  |  | H | Nipex Geophysical and Geotechnical Tender for Total E & P | GMA/Tendering Team | Ongoing |  | 6th April 2020 | Open
5 | SOP |  |  | H | ITF Registration for 2020 | GMA | Ongoing |  |  | Open
6 | SOP |  |  | H | Updated CVs and Certificates for Freelance Navigator/Surveyor | GMA | Sent to GMO | 23rd March 2020 |  | Closed
7 | SOP |  |  | H | Loan Application Form for Timothy - Filled and comments on Team Lead Column and Outstanding Loan Payment | GMA | Done and sent to GMFA for further action | 23rd March 2020 |  | Closed
8 | SOP |  |  | H | Trade Reference for TES Survey Equipment Services | GMA/GMFA | Pending |  |  | Open
9 | SOP |  |  | H | Requested Documents for 2019 Audited Accounts | GMA | Sent to the Auditor with the documents received from GMFA | 24th March 2020 |  | Closed
10 | SOP |  |  | H | Submitted Reference Check Form sent by Focus Group | GMA | Sent | 23rd March 2020 |  | Closed
11 | SOP |  |  | H | Confirmation and Updated Vendor Information to Oando PLC | GMA | Sent | 23rd March 2020 |  | Closed
12 | SOP |  |  | M | Email responses to applicants sent to enquiries | GMA | Responded | 23rd -27th March 2020 |  | Closed
13 | SOP |  |  | H | DPR Permit for Technical Consultancy | GMA | Under Processing on the OGISP/DPR Portal |  |  | Open
14 | SOP |  |  | M | Follow up on SPDC Geosciences bid submitted wit True Blue Energy | GMA | True Blue Energy confirmed SPDC Response to the tender submission. Awaiting the next stage | 23rd March 2020 |  | Closed
15 | SOP |  |  | M | Instructions to Enigha to follow up with New AC Technicians to check the bad ACs for possible repairs, Fixing and purchase of New Parts. | GMA/Enigha | Ongoing | 23rd March 2020 |  | Open
16 | SOP |  |  | M | Call to Shell Representative for the forth coming close out Contract Meeting Scheduled for 31st March and Documents to be presented at the Shell Close Out Meeting | GMA | Yet to receive the official email saying the meeting has been post poned due to the COVID-19 Pandemic | 23rd March 2020 |  | Open
17 | SOP |  |  | M | Call to R.E.D Services on potential Tenants for the last floor | GMA | Done | 23rd March 2020 |  | Closed
18 | SOP |  |  | H | Final Review of Salaries for March 2020 for and BEG Expatriates salary computation for March 2020 to DMD | GMA | Sent Schedule to DMD | 24th and 25th March 2020 |  | Closed
19 | SOP |  |  | H | Completed salary Schedule for Access Bank Upload for SPDC CAD Contract Staff for March 2020 | GMA | Done | 25th March 2020 |  | Closed
20 | SOP |  |  | H | Uploaded and paid Salaries for Brone staff March 2020 | GMA | Salaries Paid | 25th March 2020 |  | Closed
21 | SOP |  |  | H | Online Transfers to LOS Operations account for operations funds and Logistics account, to logistics account to complete salary payment | GMA | Done | 25th March 2020 |  | Closed
22 | SOP |  |  | H | Follow up on Shell payment; spoke with the Shell representative Mr. Lekan who mentioned some payments have been made. Checked online on the Access Bank platform, payment is yet to come in. | GMA | Payment still Pending | 25th March 2020 |  | Open
23 | SOP |  |  | H | Email to Christian and Obioma for Medical Report Evidence | GMA | Done | 25th March 2020 |  | Closed
24 | SOP |  |  | H | Brone and Bersh Staff Pension Schedules for Remittance for March 2020 | GMA | Done | 26th March 2020 |  | Closed
25 | SOP |  |  | H | Cheque Issuance for pension and Paye Payment for Brone Staff and schedules given to Enigha to take to the Bank | GMA | Done | 26th March 2020 |  | Closed
26 | SOP |  |  | M | Went to the office to follow on the clerical staff and ensure procedures were being observed | GMA | Done | 26th March 2020 |  | Closed
27 | SOP |  |  | M | Email Responses to Vendors and some staff | GMA | Done | 23rd -27th March 2020 |  | Closed
28 | SOP |  |  | M | Confirmation Letter for GMFA | GMA | Done | 27th March 2020 |  | Closed
29 | SOP |  |  | H | Email Response of discount on Exxon Mobil contract Rates with Brone on adapting to Market Realities | GMA | Done | 27th March 2020 |  | Closed
30 | SOP |  |  | M | Budget PHC Mar Week 5 | GMA/Enigha | Sent to Accounts | 27th March 2020 |  | Closed
31 | SOP |  |  | H | WHT Schedules Used and Unused for Tax Issues | GMA | Ongoing, Used ones are being filed |  |  | Open
32 | SOP |  |  | M | Approval given to the Admin Assist. for Petty Cash Disbursement for this week | GMA | Done |  |  | Closed
33 | SOP |  |  | H | Tax Clearance Brone Survey 2020 | GMA | Received from the Auditor | 22nd March 2020 |  | Closed
34 | PA |  |  | H | Email Responses to various Clients | GMA | Done | 23rd-27th Mar 2020 |  | Closed
[9 empty] | Open: | 8
[9 empty] | Closed: | 26
| Actionees (Key): | [5 empty] | Ebika Ayeba-Enenimiete: GM, Contracts & Administration (GMA) |  | Info: | 0
Mr. Bunmi Akomolede: Managing Director (MD)
|  | Priority Key: |  | H | High Finding |  | Mrs. Tiwalade Akomolede: Deputy Managing Director (DMD)
|  |  |  | M | Medium Finding |  | Mr. Sunkanmi Dairo: Management Trainee (MT)
|  |  |  | L | Low Finding |  | Tender Team: Adebisi A., Felix Oyeleke
|  |  |  | Info | Information |  | Accounts: Ufuoma Odogu
Adebisi Adenuga (GMO)
Bimbo Akindiilete (AO)
Mike Mattinson (DDO)
Satish Mudaliar (Team Lead, Survey Engrg.)
Busola Adekanmbi (GM, Finance & Admin, LOS
Tolu Eronmonseh
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 8 Closed 26 Info

## 03-04-2020
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 26
[7 empty] | Current Date: |  | 03.04.2020
[7 empty] | Last updated on: 03/04/2020 |  | 2020-04-03
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Ebika Ayeba-Enenimiete
1 | PA |  |  | H | Brone Weekly Management Meeting | GMA/MGT | Attended | 31st March 2020 |  | Closed
2 | PA |  |  | H | Request for Additional Information To Total E & P - Call-Off Contract for Offshore Geophysical and Geotechnical Site Investigation Survey | GMA | Sent to Nipex Portal and Total | 30th March 2020 |  | Closed
3 | SOP |  |  | H | Requested Pension Alliance Schedule – Sent to Pal Alliance | GMA | Sent tp Pal Pensions | 30th March & April 2, 2020 |  | Closed
4 | PA |  |  | H | Went to the office to check up on things and follow up with the tenant for the 1st floor on their outstanding service charges. | GMA | Done | 30th March 2020 |  | Closed
5 | SOP |  |  | H | Nipex Geophysical and Geotechnical Tender for Total E & P | GMA/Tendering Team | Ongoing |  | 27th April 2020 | Open
6 | SOP |  |  | H | ITF Registration for 2020 | GMA | Funds Paid, awaiting the certificate |  |  | Open
7 | SOP |  |  | H | Follow up Calls with the Auditor on the Audited Accounts for 2019 and sent in additional document to him | GMA | Done | 31st March 2020 |  | Closed
8 | SOP |  |  | H | Pension Schedules, Remittances and Cheques for SPDC Contract Staff | GMA | Done | 31st March 2020 |  | Closed
9 | SOP |  |  | H | Cheques for PAL Pension, AIICO and Leadway for SPDC Staff for Nov-Dec 2019 and Jan - Mar 2020 were Returned, ZPC/IBTC for Nov-Dec 2019 and Jan to Mar 2020 went through | GMA/GMFA | Done | 1st April 2020 |  | Open
10 | SOP |  |  | H | Seabed CPT system Commercial Quotes for Gibbs and Dold CC | GMA/Tendering Team | Submitted | 1st April 2020 |  | Closed
11 | SOP |  |  | H | Paye Deduction Schedule for March 2020 for LOS Staff | GMA | Sent to Ufuoma and Bimbo | 1st April 2020 |  | Closed
12 | SOP |  |  | H | Email correspondence with Shell on SPDC Contract staff salaries for March 2020 and Business Performance Review Meeting | GMA | Sent | 31st March 2020 |  | Closed
13 | SOP |  |  | M | Brone Clarification Questions: Erha 4D M3 Seismic Technical ITT for ESSO | GMA/Tendering Team | Ongoing |  | 9th April 2020 | Closed
14 | SOP |  |  | H | DPR Permit for Technical Consultancy | GMA | Issued |  |  | Closed
15 | SOP |  |  | M | MOA with G-Tec Offshore for Geotechnical Services | GMA | Sent | 3rd April 2020 |  | Closed
16 | SOP |  |  | M | Instructions to Enigha to follow up with New AC Technicians to check the bad ACs for possible repairs, Fixing and purchase of New Parts. | GMA/Enigha | Pending |  |  | Open
17 | SOP |  |  | M | Call to Shell Representative for the forth coming close out Contract Meeting Scheduled for 31st March and Documents to be presented at the Shell Close Out Meeting | GMA | Email from Shell received on the postponement of the meeting due to COVID-19 |  |  | Closed
18 | SOP |  |  | M | Shell Cad Contract Salaries for March 2020 | GMA | Uploaded and Paid | 30th March 2020 |  | Closed
19 | SOP |  |  | H | Online Transfers to Ogar for Boat Hire | GMA | Done | 1st April 2020 |  | Closed
20 | SOP |  |  | M | Went to the office to follow on the clerical staff and ensure procedures were being observed | GMA | Done | 30th Mar and 1st April 2020 |  | Closed
21 | SOP |  |  | M | Email Responses to Vendors and some staff | GMA | Done | 30th Mar to 3rd April 2020 |  | Closed
22 | SOP |  |  | M | Budget PHC April Week 1 | GMA/Enigha | Sent to Accounts | 3rd April 2020 |  | Closed
23 | SOP |  |  | H | WHT Schedules Used and Unused for Tax Issues | GMA | Ongoing, Used ones are being filed |  |  | Open
24 | SOP |  |  | M | Approval given to the Admin Assist. for Petty Cash Disbursement for this week | GMA | Done |  |  | Closed
25 | PA |  |  | M | Seismic Processing and Re-Processing Services Tender for Chevron Nigeria Limited | GMA/Tendering Team | Ongoing |  | 1st May 2020 | Open
26 | PA |  |  | H | Email Responses to various Clients | GMA | Done | 30th Mar to 3rd April 2020 |  | Closed
[9 empty] | Open: | 6
[9 empty] | Closed: | 20
| Actionees (Key): | [5 empty] | Ebika Ayeba-Enenimiete: GM, Contracts & Administration (GMA) |  | Info: | 0
Mr. Bunmi Akomolede: Managing Director (MD)
|  | Priority Key: |  | H | High Finding |  | Mrs. Tiwalade Akomolede: Deputy Managing Director (DMD)
|  |  |  | M | Medium Finding |  | Mr. Sunkanmi Dairo: Management Trainee (MT)
|  |  |  | L | Low Finding |  | Tender Team: Adebisi A., Felix Oyeleke
|  |  |  | Info | Information |  | Accounts: Ufuoma Odogu
Adebisi Adenuga (GMO)
Bimbo Akindiilete (AO)
Mike Mattinson (DDO)
Satish Mudaliar (Team Lead, Survey Engrg.)
Busola Adekanmbi (GM, Finance & Admin, LOS
Tolu Eronmonseh
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 6 Closed 20 Info

## 10-04-2020
|  |  |  | BRONE POSITIONING+SURVEY LTD - ACTION TRACKER |  |  |  |  | Total actions: | 29
[7 empty] | Current Date: |  | 10.04.2020
[7 empty] | Last updated on: 10/04/2020 |  | 2020-04-10
Item No | Issue | Ref | Section or Page | Priority | What | Action Party | Update/Comments | By When | Days to Close | Status
Weekly Report - Ebika Ayeba-Enenimiete
1 | PA |  |  | H | Brone Weekly Management Meeting | GMA/MGT | Attended | 6th April 2020 |  | Closed
2 | PA |  |  | H | MOA for Technical Partnership for Geotechnical Services with Helms Geomarine | GMA | Sent and Executed | 6th April 2020 |  | Closed
3 | SOP |  |  | H | RFQ-ENI-ANGOLA-SC-008 : PROVISION OF SURVEY SERVICES FOR ENI ANGOLA PROJECT for Sapura Energy | GMA/Tendering Team | Ongoing |  | 13th April 2020 | Open
4 | PA |  |  | H | Email Acknowledgement for Sapura Energy Survey Services Tender | GMA | Done | 6th April 2020 |  | Closed
5 | SOP |  |  | H | Nipex Geophysical and Geotechnical Tender for Total E & P | GMA/Tendering Team | Ongoing |  | 27th April 2020 | Open
6 | SOP |  |  | H | ITF Registration for 2020 | GMA | Funds Paid, awaiting the certificate |  |  | Open
7 | SOP |  |  | H | Meeting/Training for Bimbo and Tolu Via Zoom on Bids and Tendering Tips, Packaging and what is expected | GMA | Done | 7th April 2020 |  | Closed
8 | SOP |  |  | M | Chevron Seismic Processing and Re-Processing Tender acknowledgement | GMA | Done | 6th April 2020 |  | Closed
9 | SOP |  |  | H | Cover Letter for Lazarus trip to Port Harcourt for transportation of Tidal Measurement Equipment by road | GMA | Done | 7th April 2020 |  | Closed
10 | SOP |  |  | M | Request Letter to Pal and IBTC Pensions for Pension Schedules Remitted in October 2019 and evidence pension remittance for 2019 | GMA | Submitted | 7th April 2020 |  | Closed
11 | SOP |  |  | H | Pension Schedule for SPDC Cad Contract Staff sent to IBTC as requested | GMA | Sent | 7th April 2020 |  | Closed
12 | SOP |  |  | M | Bids and Tender Templates sent to Bimbo and Tolu to work on the new tenders for Chevron, Total and Sapura | GMA | Sent | 7th April 2020 |  | Closed
13 | SOP |  |  | H | Brone Clarification Questions: Erha 4D M3 Seismic Technical ITT for ESSO | GMA/Tendering Team | Submitted | 9th April 2020 |  | Closed
14 | SOP |  |  | H | Acknowledgement of Email Responses to Queries for AMNI INVITATION TO TENDER: DEBRIS SURVEY AND SEWOP POSITIONING SERVICES | GMA | Email Sent | 9th April 2020 |  | Closed
15 | SOP |  |  | H | MOA with Scandinavian Geo Services AS for ESSO Erha 4D M3 Seismic Services | GMA | Sent and Executed | 8th April 2020 |  | Closed
16 | SOP |  |  | M | Instructions to Enigha to follow up with New AC Technicians to check the bad ACs for possible repairs, Fixing and purchase of New Parts. | GMA/Enigha | Pending |  |  | Open
17 | SOP |  |  | M | Contact Details for Brone Operations and Contracts as requested by Shell HSE Contact for SPDC Contract | GMA | Sent | 8th April 2020 |  | Closed
18 | SOP |  |  | M | REVISED WORKSCOPE FOR RE-SUBMISSION OF TECHNICAL AND COMMERCIAL TENDER FOR AMNI INVITATION TO TENDER: DEBRIS SURVEY AND SEWOP POSITIONING SERVICES | GMA/Tendering Team | Ongoing |  | 14th April 2020 | Open
19 | SOP |  |  | H | Online Transfers to LOS for Operations | GMA | Done | 8th and 10th April 2020 |  | Closed
20 | SOP |  |  | H | Request for Bank Guarantee and Bid Bond Template for Total Geophysical and Geotechnical Tender | GMA | Sent to Mrs. Tope Zenith Bank | 8th April 2020 |  | Closed
21 | SOP |  |  | H | Requested Issued Cover Page of Total ITT by Zenith Bank for the Bank Guarantee | GMA | Sent to Mrs. Tope Zenith Bank | 9th April 2020 |  | Closed
22 | SOP |  |  | M | Email Responses to Vendors and some staff | GMA | Done | 6th to 10th April 2020 |  | Closed
23 | SOP |  |  | M | Budget PHC April Week 2 | GMA/Enigha | Sent to Accounts | 10th April 2020 |  | Closed
24 | SOP |  |  | H | WHT Schedules Used and Unused for Tax Issues | GMA | Ongoing, Used ones are being filed |  |  | Open
25 | SOP |  |  | M | Approval given to the Admin Assist. for Petty Cash Disbursement for this week | GMA | Done |  |  | Closed
26 | PA |  |  | M | Seismic Processing and Re-Processing Services Tender for Chevron Nigeria Limited | GMA/Tendering Team | Ongoing |  | 1st May 2020 | Open
27 | PA |  |  | M | Project Charge Sheet for Amni Andoni River Channel Bathymetry Survey | GMA | Done | 9th April 2020 |  | Closed
28 | PA |  |  | H | SO for Amni Andoni River Channel Bathymetry Survey for invoicing | GMA | Sent to FA | 7th April 2020 |  | Closed
29 | PA |  |  | H | Email Responses to various Clients | GMA | Done | 6th to 10th April 2020 |  | Closed
[9 empty] | Open: | 7
[9 empty] | Closed: | 22
| Actionees (Key): | [5 empty] | Ebika Ayeba-Enenimiete: GM, Contracts & Administration (GMA) |  | Info: | 0
Mr. Bunmi Akomolede: Managing Director (MD)
|  | Priority Key: |  | H | High Finding |  | Mrs. Tiwalade Akomolede: Deputy Managing Director (DMD)
|  |  |  | M | Medium Finding |  | Mr. Sunkanmi Dairo: Management Trainee (MT)
|  |  |  | L | Low Finding |  | Tender Team: Adebisi A., Felix Oyeleke
|  |  |  | Info | Information |  | Accounts: Ufuoma Odogu
Adebisi Adenuga (GMO)
Bimbo Akindiilete (AO)
Mike Mattinson (DDO)
Satish Mudaliar (Team Lead, Survey Engrg.)
Busola Adekanmbi (GM, Finance & Admin, LOS
Tolu Eronmonseh
Note on B4: 1 SOP- Standard Operating Procedure 2 PA - Project Admin 3 MS - Marine Systems
Note on K4: Statuses are: Open 7 Closed 22 Info